## CustomerPipeline
# | Customer | Program | Sales | AcctManger | RequestType | Hours | DeplAssoc | TargetDate | LaunchDate | MaxDate | Complete | AT-Wave | Notes
1 | Wingstop | Wingstop FS & BS Program | Michelle Hudson | Amanda Coulombe | New Launch | 40
3 | Hard Rock Café | Hard Rock Resort Food Safety Program | Rob Siler | Amanda Coulombe | New Launch | 24
6 | Smokey Bones |  | Rob Siler | Steve Steinberg
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
201
202
203
204
205
206
207
208
209
210
211
212
213
214
215
216
217
218
219
220
221
222
223
224
225
226
227
228
229
230
231
232
233
234
235
236
237
238
239
240
241
242
243
244
245
246
247
248
249
250
251
252
253
254
255
256
257
258
259
260
261
262
263
264
265
266
267
268
269
270
271
272
273
274
275
276
277
278
279
280
281
282
283
284
285
286
287
288
289
290
291
292
293
294
295
296
297
298
299
300
301
302
303
304
305
306
307
308
309
310
311
312
313
314
315
316
317
318
319
320
321
322
323
324
325
326
327
328
329
330
331
332
333
334
335
336
337
338
339
340
341
342
343
344
345
346
347
348
349
350
351
352
353
354
355
356
357
358
359
360
361
362
363
364
365
366
367
368
369
370
371
372
373
374
375
376
377
378
379
380
381
382
383
384
385
386
387
388
389
390
391
392
393
394
395
396
397
398
399
400
401
402
403
404
405
406
407
408
409
410
411
412
413
414
415
416
417
418
419
420
421
422
423
424
425
426
427
428
429
430
431
432
433
434
435
436
437
438
439
440
441
442
443
444
445
446
447
448
449
450
451
452
453
454
455
456
457
458
459
460
461
462
463
464
465
466
467
468
469
470
471
472
473

## DeploymentRequests
# | Customer | Program | Sales | AcctManager | RequestType | Hours | DeplAssoc | TargetDate | ReqLaunchDate | MaxDate | Complete | AT-Wave | Notes | $$$_Rank
1 | Dunkin Brands | Dunkin Donuts Pilot | Brian Nolan | Emily Naufel | Request | 40 | RM/MG | 2014-06-30 | 2014-06-30 | 2014-06-30 | Y |  |  | 219
2 | Hard Rock Café | Hard Rock Café Food Safety Program | John Bestler | Amanda Coulombe | New Launch | 24 | RM | 2014-07-01 | 2014-07-01 | 2014-07-01 | Y |  |  | 36
3 | TGI Friday's | TGIF Food Safety Program | Michelle Hudson | Eric Hightower | New Launch | 40 | RM | 2014-07-01 | 2014-07-01 | 2014-07-01 | Y |  |  | 17
4 | Brookdale | Brookdale Senior Living Program | John Bestler | Steve Steinberg | New Launch | 40 | RM | 2014-07-07 | 2014-07-07 | 2014-07-07 | Y |  |  | 7
5 | CKE | CKE Workplace Safety | John Bestler | Amanda Coulombe | New Launch | 40 | AT | 2014-07-07 | 2014-07-07 | 2014-07-07 | Y |  |  | 4
6 | Famous Dave's | Famous Dave's Food Safety Program | Justin Prestinario | Eric Hightower | New Launch | 24 | AT | 2014-07-07 | 2014-07-07 | 2014-07-07 | Y |  |  | 43
7 | TGI Friday's | TGIF Food Safety Program | Michelle Hudson | Eric Hightower | Request | 8 | RM | 2014-07-09 | 2014-07-09 | 2014-07-09 | Y |  |  | 17
8 | Golden Corral | Golden Corral Food Safety | Brian Nolan | Emily Naufel | Request | 12 | RM | 2014-07-14 | 2014-07-14 | 2014-07-14 | Y |  |  | 21
9 | Ocean Properties | Ocean Properties Food Safety Program | John Bestler | Steve Steinberg | New Launch | 40 | MG | 2014-07-14 | 2014-07-14 | 2014-07-14 | Y |  |  | 86
10 | Smashburger | Smashburger Food Safety Audits | Keith Woith | Eric Hightower | New Launch | 40 | MG | 2014-07-15 | 2014-07-15 | 2014-07-15 | Y |  |  | 219
11 | Avendra Hospitality | Avendra Hospitality Food Safety Program | Brian Nolan | Amanda Coulombe | Request | 4 | RM | 2014-07-18 | 2014-07-18 | 2014-07-18 | Y |  |  | 74
12 | Famous Dave's | Famous Dave's Food Safety Program | Justin Prestinario | Eric Hightower | Request | 24 | MG | 2014-07-18 | 2014-07-18 | 2014-07-18 | Y |  |  | 43
13 | Golden Corral | Golden Corral Food Safety | Brian Nolan | Emily Naufel | Request | 24 | MG | 2014-07-18 | 2014-07-18 | 2014-07-18 | Y |  |  | 21
14 | Starbucks | Starbucks La Boulange Food Safety Program | Justin Prestinario | Tim Cassidy | Request | 6 | MG | 2014-07-18 | 2014-07-18 | 2014-07-18 | Y |  |  | 1
15 | Brinker | Brinker 2015 Audit Program | Michelle Hudson | Steve Steinberg | Request | 16 | MG | 2014-07-21 | 2014-07-21 | 2014-07-21 | Y |  |  | 219
16 | CKE | CKE Food Safety | John Bestler | Amanda Coulombe | Request | 8 | RM | 2014-07-31 | 2014-07-31 | 2014-07-31 | Y |  |  | 4
17 | Dairy Queen | Dairy Queen Pride Program | Justin Prestinario | Amanda Coulombe | Request | 8 | RM | 2014-07-31 | 2014-07-31 | 2014-07-31 | Y |  |  | 8
18 | Brookdale | Brookdale Senior Living Program | John Bestler | Steve Steinberg | Relaunch | 40 | RM | 2014-08-01 | 2014-08-01 | 2014-08-01 | Y |  |  | 7
19 | Burger King | Burger King GPV Program | John Bestler | Steve Steinberg | New Launch | 80 | RM | 2014-08-01 | 2014-08-01 | 2014-08-01 | Y |  |  | 20
20 | Cotton Patch Café | Cotton Patch Café Food Safety Program | Michelle Hudson | Emily Naufel | New Launch | 24 | AT | 2014-08-01 | 2014-08-01 | 2014-08-01 | Y |  |  | 97
21 | Dunkin Brands | Dunkin Donuts Pilot | Brian Nolan | Emily Naufel | Request | 40 | RM/MG | 2014-08-01 | 2014-08-01 | 2014-08-01 | Y |  |  | 219
22 | Ignite Restaurants | Ignite Food Safety Evaluation Program | Michelle Hudson | Amanda Coulombe | New Launch | 40 | MG | 2014-08-06 | 2014-08-06 | 2014-08-06 | Y |  |  | 54
23 | Interstate Hotels and Resorts | Interstate Beverage Program | Brian Nolan | Eric Hightower | New Launch | 40 | MG | 2014-08-08 | 2014-08-08 | 2014-08-08 | Y |  |  | 48
24 | Interstate Hotels and Resorts | Interstate Food Safety Program | Brian Nolan | Eric Hightower | New Launch | 40 | MG | 2014-08-08 | 2014-08-08 | 2014-08-08 | Y |  |  | 48
25 | Fogo De Chao | Fogo de Chao Food Safety | Michelle Hudson | Eric Hightower | New Launch | 24 | RM | 2014-08-18 | 2014-08-18 | 2014-08-18 | Y |  |  | 55
26 | Burgerville | Burgerville Food Safety and Workplace Safety | Keith Woith | Emily Naufel | New Launch | 24 | MG | 2014-08-25 | 2014-08-01 | 2014-08-25 | Y |  |  | 219
27 | Landry's | Landry's Food Safety Program | Keith Woith | Tim Cassidy | New Launch | 40 | RM | 2014-08-26 | 2014-08-15 | 2014-08-26 | Y |  |  | 107
28 | Compass Group | Compass Food Safety Program | Brian Nolan | Eric Hightower | Relaunch | 80 | RM/MG | 2014-09-01 | 2014-09-01 | 2014-09-01 | Y |  |  | 11
29 | Compass Group | Compass HD Program | Brian Nolan | Eric Hightower | Relaunch | 80 | RM/MG | 2014-09-01 | 2014-09-01 | 2014-09-01 | Y |  |  | 11
30 | Creative Dining Services | Creative Dining Services Food Safety Program | John Bestler | Amanda Coulombe | New Launch | 24 | MG | 2014-09-01 | 2014-09-01 | 2014-09-01 | Y |  |  | 123
31 | New York Office of Mental Health | NYSOMH Food Safety Program | Brian Nolan | Emily Naufel | New Launch | 24 | RM | 2014-09-01 | 2014-09-01 | 2014-09-01 | Y |  |  | 219
32 | EcoSure | Time Tracker Form | All | All | New Launch | 24 | AD | 2014-09-22 | 2014-09-22 | 2014-09-22 | Y |  |  | 603
33 | Sodexo | Sodexo Food Safety & HS Program | Brian Nolan | Eric Hightower | Relaunch | 80 | MG | 2014-09-22 | 2014-09-22 | 2014-09-22 | Y |  |  | 9
34 | Buffalo Wild Wings | Buffalo Wild Wings - CO & Franchise Food Safety Program | Justin Prestinario | Emily Naufel | Relaunch | 24 | AD | 2014-09-23 | 2014-09-23 | 2014-09-23 | Y |  |  | 15
35 | Starbucks | Starbucks Company Food Safety Program | Justin Prestinario | Tim Cassidy | Relaunch | 80 | RM | 2014-09-29 | 2014-09-29 | 2014-09-29 | Y |  |  | 1
36 | Aramark | ARAMARK Food Safety Program | Brian Nolan | Amanda Coulombe | Relaunch | 80 | AD | 2014-10-01 | 2014-10-01 | 2014-10-01 | Y |  |  | 16
37 | Brookdale | Brookdale Senior Living Program | John Bestler | Steve Steinberg | Relaunch | 40 | RM | 2014-10-01 | 2014-10-01 | 2014-10-01 | Y |  |  | 7
38 | Compass Group | Compass Workplace Safety Program | Brian Nolan | Eric Hightower | Relaunch | 40 | RM | 2014-10-01 | 2014-10-01 | 2014-10-01 | Y |  |  | 11
39 | Dairy Queen | Dairy Queen Pride Program | Justin Prestinario | Amanda Coulombe | Relaunch | 40 | MG | 2014-10-01 | 2014-10-01 | 2014-10-01 | Y |  |  | 8
40 | Johnny Rockets | Johnny Rockets Food Safety Program | Keith Woith | Tim Cassidy | Request | 24 | AD | 2014-10-01 | 2014-10-01 | 2014-10-01 | Y |  |  | 219
41 | Newk's | Newks Food Safety Program | Michelle Hudson | Steve Steinberg | New Launch | 40 | MG | 2014-10-01 | 2014-10-01 | 2014-10-01 | Y |  |  | 69
42 | Sage Hospitality | Sage Hospitality Food Safety Program | Keith Woith | Emily Naufel | New Launch | 24 | AD | 2014-10-01 | 2014-10-01 | 2014-10-01 | Y |  |  | 88
43 | Veteran's Canteen Services | VCS Food Safety & Barbershop Program | Rob Siler | Tim Cassidy | New Launch | 24 | AD | 2014-10-01 | 2014-10-01 | 2014-10-01 | Y |  |  | 70
44 | Chick-fil-A | Chick-fil-A Catering Program | Rob Siler | Emily Naufel | Relaunch | 24 | AD | 2014-10-10 | 2014-10-10 | 2014-10-10 | Y |  |  | 44
45 | Cheddar's | Cheddar's Casual Cafe Food Safety Evaluations | Michelle Hudson | Amanda Coulombe | Relaunch | 8 | RM | 2014-10-15 | 2014-10-15 | 2014-10-15 | Y |  |  | 39
46 | Tommy Bahama | Tommy Bahama Food Safety Program | Rob Siler | Tim Cassidy | New Launch | 24 | MG | 2014-10-15 | 2014-10-15 | 2014-10-15 | Y |  |  | 134
47 | Burger King | Burger King GPV Program | John Bestler | Steve Steinberg | Relaunch | 24 | RM | 2014-10-15 | 2014-10-20 | 2014-10-20 | Y |  |  | 20
48 | Compass Group | Compass Avenue C | Brian Nolan | Eric Hightower | New Launch | 40 | RM/MG | 2014-10-20 | 2014-10-15 | 2014-10-20 | Y |  |  | 11
49 | Desert Island Properties | Desert Island Food Safety Program | Keith Woith | Steve Steinberg | New Launch | 24 | RM | 2014-10-20 | 2014-10-20 | 2014-10-20 | Y |  |  | 120
50 | Twin Peaks | Twin Peaks Food Safety Program | Michelle Hudson | Eric Hightower | New Launch | 80 | RM | 2014-10-20 | 2014-10-20 | 2014-10-20 | Y |  |  | 52
51 | Mohonk | Mohonk Resort Food Safety Program | Brian Nolan | Emily Naufel | New Launch | 24 | AD | 2014-10-27 | 2014-10-27 | 2014-10-27 | Y |  |  | 89
52 | DineEquity | Transportation Audit | Keith Woith | Steve Steinberg | New Launch | 40 | AD | 2014-11-01 | 2014-11-01 | 2014-11-01 | Y |  |  | 5
53 | Compass Group | Compass Canada English Form | Brian Nolan | Eric Hightower | Relaunch | 24 | RM | 2014-11-03 | 2014-11-03 | 2014-11-03 | Y |  |  | 11
54 | McDonald's | McDonalds Food Safety/ECS Program | Justin Prestinario | Eric Hightower | Relaunch | 16 | MG | 2014-11-12 | 2014-11-12 | 2014-11-12 | Y |  |  | 3
55 | General Mills | General Mills Quarterly Retrieval | Division | Eric Hightower | New Launch | 24 | AD | 2014-11-13 | 2014-11-13 | 2014-11-13 | Y |  |  | 142
56 | Compass Group | Compass Workplace Safety Program | Brian Nolan | Eric Hightower | Request | 8 | AD | 2014-11-24 | 2014-11-24 | 2014-11-24 | Y |  |  | 11
57 | Cornell University | Cornell Food Safety Program | Brian Nolan | Eric Hightower | New Launch | 24 | MG | 2014-12-01 | 2014-12-01 | 2014-12-01 | Y |  |  | 110
58 | Quizno's | Quiznos Food Safety Program | Keith Woith | Eric Hightower | New Launch | 16 | MG | 2014-12-01 | 2014-12-01 | 2014-12-01 | Y |  |  | 219
59 | Arby's | Arby's Food Safety Program | Rob Siler | Amanda Coulombe | Relaunch | 40 | AD | 2015-01-01 | 2015-01-01 | 2015-01-01 | Y |  |  | 19
60 | Brinker | Brinker AD Program | Michelle Hudson | Steve Steinberg | New Launch | 24 | AD | 2015-01-01 | 2015-01-01 | 2015-01-01 | Y |  |  | 219
61 | Caribou / Einstein | Caribou Coffee Assessment (Brand Standards) | Justin Prestinario | Tim Cassidy | Relaunch | 50 | AD | 2015-01-01 | 2015-01-01 | 2015-01-01 | Y |  |  | 18
62 | Cinemark | Cinemark Food Safety Program | Michelle Hudson | Tim Cassidy | Relaunch | 8 | AD | 2015-01-01 | 2015-01-01 | 2015-01-01 | Y |  |  | 29
63 | Compass Group | Compass Food Safety Program | Brian Nolan | Eric Hightower | Relaunch | 40 | AD | 2015-01-01 | 2015-01-01 | 2015-01-01 | Y |  |  | 11
64 | Corner Bakery | Corner Bakery Food Safety Evaluations | Michelle Hudson | Steve Steinberg | Relaunch | 40 | RM | 2015-01-01 | 2015-01-01 | 2015-01-01 | Y |  |  | 40
65 | Corner Store | Corner Store Food Safety Program | Michelle Hudson | Steve Steinberg | Relaunch | 0 | AD | 2015-01-01 | 2015-01-01 | 2015-01-01 | Y |  |  | 27
66 | Darden | Darden Food Safety Program - Puerto Rico | John Bestler | Amanda Coulombe | Relaunch | 0 | AD | 2015-01-01 | 2015-01-01 | 2015-01-01 | Y |  |  | 14
67 | Entertainment Cruises | Entertainment Cruises Food Saftey | John Bestler | Eric Hightower | New Launch | 24 | RM | 2015-01-01 | 2015-01-01 | 2015-01-01 | Y |  |  | 56
68 | Famous Dave's | Famous Dave's Food Safety Program | Justin Prestinario | Eric Hightower | Relaunch | 0 | MG | 2015-01-01 | 2015-01-01 | 2015-01-01 | Y |  |  | 43
69 | Friendly's | Friendly's Food Safety Program | Brian Nolan | Emily Naufel | Relaunch | 40 | BA | 2015-01-01 | 2015-01-01 | 2015-01-01 | Y |  |  | 41
70 | Golden Corral | Golden Corral Food Safety | Brian Nolan | Emily Naufel | Relaunch | 8 | RM | 2015-01-01 | 2015-01-01 | 2015-01-01 | Y |  |  | 21
71 | Guckenheimer | Guckenheimer Food Safety & Workplace Safety Program | Keith Woith | Emily Naufel | Relaunch | 40 | TA | 2015-01-01 | 2015-01-01 | 2015-01-01 | Y |  |  | 42
72 | Hilton | Hilton Add-on Program | Brian Nolan | Eric Hightower | Relaunch | 0 | RM | 2015-01-01 | 2015-01-01 | 2015-01-01 | Y |  |  | 25
73 | Hilton | Hilton Beverage Program | Brian Nolan | Eric Hightower | Relaunch | 40 | RM | 2015-01-01 | 2015-01-01 | 2015-01-01 | Y |  |  | 25
74 | Hilton | Hilton Food Safety Program | Brian Nolan | Eric Hightower | Relaunch | 0 | RM | 2015-01-01 | 2015-01-01 | 2015-01-01 | Y |  |  | 25
75 | Hooters of America | Hooters Food Safety Program | Rob Siler | Emily Naufel | Relaunch | 0 | AD | 2015-01-01 | 2015-01-01 | 2015-01-01 | Y |  |  | 30
76 | Johnny Rockets | Johnny Rockets Food Safety Program | Keith Woith | Tim Cassidy | Relaunch | 0 | AD | 2015-01-01 | 2015-01-01 | 2015-01-01 | Y |  |  | 219
77 | Kona Grill | Kona Grill Food Safety Program | Keith Woith | Tim Cassidy | New Launch | 24 | BA | 2015-01-01 | 2015-01-01 | 2015-01-01 | Y |  |  | 77
78 | Lazy Dog Café | Lazy Dog Cafe Food Safety Program | Division | Steve Steinberg | Relaunch | 0 | TA | 2015-01-01 | 2015-01-01 | 2015-01-01 | Y |  |  | 83
79 | McDonald's | McDonalds PlayPlace Program | Justin Prestinario | Eric Hightower | Relaunch | 40 | MG | 2015-01-01 | 2015-01-01 | 2015-01-01 | Y |  |  | 3
80 | Smashburger | Smashburger Food Safety Audits | Keith Woith | Eric Hightower | Relaunch | 0 | BA | 2015-01-01 | 2015-01-01 | 2015-01-01 | Y |  |  | 219
81 | Starbucks | Starbucks LIC Food Safety Program | Justin Prestinario | Tim Cassidy | Relaunch | 24 | AD | 2015-01-01 | 2015-01-01 | 2015-01-01 | Y |  |  | 1
82 | TGI Friday's | TGIF Food Safety Program | Michelle Hudson | Eric Hightower | Relaunch | 40 | RM | 2015-01-01 | 2015-01-01 | 2015-01-01 | Y |  |  | 17
83 | YUM! Brands | Pizza Hut - Co/FZ Program (and Operator App) | Michelle Hudson | Emily Naufel | Relaunch | 300 | RM/MG | 2015-01-01 | 2015-01-01 | 2015-01-01 | Y |  |  | 2
84 | YUM! Brands | Pizza Hut - LIC Program | Michelle Hudson | Emily Naufel | Relaunch | 150 | RM/MG | 2015-01-01 | 2015-01-01 | 2015-01-01 | Y |  |  | 2
85 | YUM! Brands | Pizza Hut - Target Program | Michelle Hudson | Emily Naufel | Relaunch | 30 | RM/MG | 2015-01-01 | 2015-01-01 | 2015-01-01 | Y |  |  | 2
86 | Creative Dining Services | Creative Dining Services Food Safety Program | John Bestler | Amanda Coulombe | Relaunch | 24 | BA | 2015-01-01 | 2015-01-15 | 2015-01-15 | Y |  |  | 123
87 | Burger King | Burger King GPV Program | John Bestler | Steve Steinberg | Relaunch | 40 | AD | 2015-01-05 | 2015-01-01 | 2015-01-05 | Y |  |  | 20
88 | EcoSure | Time Tracker Form | All | All | New Launch | 24 | AD | 2015-01-08 | 2015-01-08 | 2015-01-08 | Y |  |  | 603
89 | DineEquity | Applebee's eCaPS Program | Keith Woith | Steve Steinberg | Relaunch | 80 | MG | 2015-01-12 | 2015-01-12 | 2015-01-12 | Y |  |  | 5
90 | DineEquity | IHOP OAR Program | Keith Woith | Steve Steinberg | Relaunch | 80 | MG | 2015-01-12 | 2015-01-12 | 2015-01-12 | Y |  |  | 5
91 | Bloomin' Brands | Bloomin Brands Food Safety Program | Rob Siler | Steve Steinberg | Relaunch | 0 | MG | 2015-01-15 | 2015-01-01 | 2015-01-15 | Y |  |  | 13
92 | Village Tavern | Village Tavern Food Safety Program | Rob Siler | Emily Naufel | New Launch | 24 | TA | 2015-01-15 | 2015-01-15 | 2015-01-15 | Y |  |  | 114
93 | Village Tavern | Village Tavern Workplace Safety Program | Rob Siler | Emily Naufel | New Launch | 24 | TA | 2015-01-15 | 2015-01-15 | 2015-01-15 | Y |  |  | 114
94 | Hilton | Hilton Add-on Program | Brian Nolan | Eric Hightower | Relaunch | 40 | RM | 2015-01-22 | 2015-01-22 | 2015-01-22 | Y |  |  | 25
95 | Humber College | Humber College Food Safety Program | Justin Prestinario | Emily Naufel | New Launch | 24 | BA | 2015-01-22 | 2015-01-22 | 2015-01-22 | Y |  |  | 192
96 | Brookdale | Brookdale Senior Living Program | John Bestler | Steve Steinberg | Relaunch | 40 | RM | 2015-01-26 | 2015-01-26 | 2015-01-26 | Y |  |  | 7
97 | Buffalo Wild Wings | Buffalo Wild Wings - CO & Franchise Food Safety Program | Justin Prestinario | Emily Naufel | Relaunch | 24 | AD | 2015-02-01 | 2015-02-01 | 2015-02-01 | Y |  |  | 15
98 | District Tap | District Tap Food Safety Program | John Bestler | Amanda Coulombe | New Launch | 16 | TA | 2015-02-01 | 2015-02-01 | 2015-02-01 | Y |  |  | 603
99 | McDonald's | McDonalds Food Safety/ECS Program | Justin Prestinario | Eric Hightower | Relaunch | 80 | MG | 2015-02-01 | 2015-02-01 | 2015-02-01 | Y |  |  | 3
100 | On The Border | On the Border Food Safety Program | Michelle Hudson | Steve Steinberg | New Launch | 40 | BA | 2015-02-01 | 2015-02-01 | 2015-02-01 | Y |  |  | 46
101 | Vi | Vi Food Safety Program | John Bestler | Amanda Coulombe | Relaunch | 0 | RM | 2015-02-01 | 2015-02-01 | 2015-02-01 | Y |  |  | 101
102 | CKE | CKE Food Safety | John Bestler | Amanda Coulombe | Relaunch | 80 | RM | 2015-02-03 | 2015-02-03 | 2015-02-03 | Y |  |  | 4
103 | CKE | CKE Mexico | John Bestler | Amanda Coulombe | Relaunch | 40 | RM | 2015-02-03 | 2015-02-03 | 2015-02-03 | Y |  |  | 4
104 | CKE | CKE Playground Program | John Bestler | Amanda Coulombe | Relaunch | 0 | RM | 2015-02-03 | 2015-02-03 | 2015-02-03 | Y |  |  | 4
105 | CKE | CKE Workplace Safety | John Bestler | Amanda Coulombe | Relaunch | 40 | RM | 2015-02-03 | 2015-02-03 | 2015-02-03 | Y |  |  | 4
106 | Arni's Restaurants | Arni's Food Safety Program | John Bestler | Amanda Coulombe | Relaunch | 0 | RM | 2015-02-09 | 2015-01-01 | 2015-02-09 | Y |  |  | 219
107 | Arni's Restaurants | Arni's Work Place Safety Program | John Bestler | Amanda Coulombe | Relaunch | 0 | RM | 2015-02-09 | 2015-01-01 | 2015-02-09 | Y |  |  | 219
108 | Avendra Hospitality | Avendra Hospitality Food Safety Program | Brian Nolan | Amanda Coulombe | Relaunch | 0 | MG | 2015-02-09 | 2015-01-01 | 2015-02-09 | Y |  |  | 74
109 | Burgerville | Burgerville Food Safety and Workplace Safety | Keith Woith | Emily Naufel | Relaunch | 0 | BA | 2015-02-09 | 2015-01-01 | 2015-02-09 | Y |  |  | 219
110 | Fogo De Chao | Fogo de Chao Food Safety | Michelle Hudson | Eric Hightower | Relaunch | 0 | TA | 2015-02-09 | 2015-01-01 | 2015-02-09 | Y |  |  | 55
111 | Granite City | Granite City Cleanliness Assessments | Justin Prestinario | Tim Cassidy | Relaunch | 0 | TA | 2015-02-09 | 2015-01-01 | 2015-02-09 | Y |  |  | 50
112 | King's Seafood | King's Seafood Food Safety Program | Keith Woith | Tim Cassidy | Relaunch | 0 | MG | 2015-02-09 | 2015-01-01 | 2015-02-09 | Y |  |  | 132
113 | My Fit Foods | My Fit Foods Food Safety Program | Michelle Hudson | Steve Steinberg | Relaunch | 0 | AD | 2015-02-09 | 2015-01-01 | 2015-02-09 | Y |  |  | 213
114 | Omni Hotels | Omni Hotels Food Safety Program | Michelle Hudson | Tim Cassidy | Relaunch | 24 | BA | 2015-02-09 | 2015-01-01 | 2015-02-09 | Y |  |  | 57
115 | Tavistock | Tavistock Food Safety Program | Keith Woith | Steve Steinberg | Relaunch | 0 | RM | 2015-02-09 | 2015-01-01 | 2015-02-09 | Y |  |  | 106
116 | Margaritaville | Margaritaville Food Safety Program | Rob Siler | Amanda Coulombe | New Launch | 24 | BA | 2015-02-15 | 2015-02-15 | 2015-02-15 | Y |  |  | 103
117 | Metz & Associates | Metz Culinary Management | Brian Nolan | Amanda Coulombe | Relaunch | 0 | MG | 2015-02-15 | 2015-02-15 | 2015-02-15 | Y |  |  | 59
118 | Marcus Hotels | Marcus Hotels Food Safety Program | John Bestler | Tim Cassidy | New Launch | 24 | AD | 2015-02-23 | 2015-02-23 | 2015-02-23 | Y |  |  | 131
119 | Bass Pro Shop | Bass Pro 2009 Food Safety Evaluations | John Bestler | Amanda Coulombe | Relaunch | 24 | AD | 2015-03-01 | 2015-01-01 | 2015-03-01 | Y |  |  | 76
120 | Granite City | Granite City Food Safety Assessments | Justin Prestinario | Tim Cassidy | Relaunch | 24 | TA | 2015-03-01 | 2015-01-01 | 2015-03-01 | Y |  |  | 50
121 | Omni Hotels | Omni Hotels Food Safety Program | Michelle Hudson | Tim Cassidy | New Launch | 0 | RM | 2015-03-01 | 2015-03-01 | 2015-03-01 | Y |  |  | 57
122 | Omni Hotels | Omni Hotels Food Safety Program | Michelle Hudson | Tim Cassidy | New Launch | 0 | RM | 2015-03-01 | 2015-03-01 | 2015-03-01 | Y |  |  | 57
123 | Burger King | Burger King Bun Sampling Program | John Bestler | Steve Steinberg | New Launch | 24 | BA | 2015-03-09 | 2015-01-01 | 2015-03-09 | Y |  |  | 20
124 | MapCo | Mapco Food Safety Program | Brian Nolan | Eric Hightower | Relaunch | 0 | TA | 2015-03-09 | 2015-01-01 | 2015-03-09 | Y |  |  | 219
125 | Ohio State University | Ohio State Food Safety Program | John Bestler | Eric Hightower | Relaunch | 0 | AD | 2015-03-09 | 2015-01-01 | 2015-03-09 | Y |  |  | 162
126 | OTG Management | OTG Management 2008 Food Safety Evals | Brian Nolan | Amanda Coulombe | Relaunch | 0 | BA | 2015-03-09 | 2015-01-01 | 2015-03-09 | Y |  |  | 219
127 | Pantry (Auntie M's) | Pantry Audits Food Safety Program | Brian Nolan | Tim Cassidy | Relaunch | 24 | MG | 2015-03-09 | 2015-01-01 | 2015-03-09 | Y |  |  | 78
128 | Travel Centers of America | Travel Centers of America Food Safety Evaluation | John Bestler | Eric Hightower | Relaunch | 0 | BA | 2015-03-09 | 2015-01-01 | 2015-03-09 | Y |  |  | 65
129 | White Lodging | White Lodging Food Safety Program | John Bestler | Amanda Coulombe | Relaunch | 0 | TA | 2015-03-09 | 2015-01-01 | 2015-03-09 | Y |  |  | 108
130 | Z Foods | Z Foods Food Safety Program | Brian Nolan | Amanda Coulombe | Relaunch | 0 | RM | 2015-03-09 | 2015-01-01 | 2015-03-09 | Y |  |  | 602
131 | Peter Piper Pizza | Peter Piper Pizza Mexico Food Safety Audits | Keith Woith | Amanda Coulombe | New Launch | 40 | AD | 2015-03-09 | 2015-02-01 | 2015-03-09 | Y |  |  | 67
132 | Tilted Kilt | Tilted Kilt Food Safety Evaluations | Keith Woith | Steve Steinberg | Relaunch | 24 | MG | 2015-03-09 | 2015-02-15 | 2015-03-09 | Y |  |  | 196
133 | Areas USA | Areas USA Food Safety Program | John Bestler | Steve Steinberg | New Launch | 80 | AD | 2015-03-09 | 2015-03-01 | 2015-03-09 | Y |  |  | 93
134 | National Food Laboratory | National Food Labs Product Retrievals | John Bestler | Tim Cassidy | New Launch | 24 | RM | 2015-03-09 | 2015-03-01 | 2015-03-09 | Y |  |  | 219
135 | Compass Group | Compass Food Safety Program | Brian Nolan | Eric Hightower | Relaunch | 40 | AD | 2015-03-16 | 2015-03-01 | 2015-03-16 | Y |  |  | 11
136 | Compass Group | Compass HD Program | Brian Nolan | Eric Hightower | Relaunch | 0 | AD | 2015-03-16 | 2015-03-01 | 2015-03-16 | Y |  |  | 11
137 | Compass Group | Compass Workplace Safety Program | Brian Nolan | Eric Hightower | Relaunch | 0 | AD | 2015-03-16 | 2015-03-01 | 2015-03-16 | Y |  |  | 11
138 | YUM! Brands | Pizza Hut - LIC Program | Michelle Hudson | Emily Naufel | Relaunch | 4 | MG | 2015-03-20 | 2015-03-20 | 2015-03-20 | Y |  |  | 2
139 | Starwood | Starwood Beverage Program | Brian Nolan | Eric Hightower | Relaunch | 24 | RM | 2015-03-23 | 2015-03-01 | 2015-03-23 | Y |  |  | 166
140 | Starwood | Starwood Food Safety Program | Brian Nolan | Eric Hightower | Relaunch | 24 | RM | 2015-03-23 | 2015-03-01 | 2015-03-23 | Y |  |  | 166
141 | Wyndham Hotels | Wyndham Food Safety Program | Brian Nolan | Tim Cassidy | New Launch | 0 | MG | 2015-03-23 | 2015-03-01 | 2015-03-23 | Y |  |  | 80
142 | Village Tavern | Village Tavern Food Safety Program | Rob Siler | Emily Naufel | Request | 16 | AD | 2015-03-23 | 2015-03-23 | 2015-03-23 | Y |  |  | 114
143 | Dickey's BBQ | Dickey's BBQ Food Safety & Brand Standards Program | Michelle Hudson | Tim Cassidy | New Launch | 40 | AD | 2015-03-25 | 2015-04-01 | 2015-04-01 | Y |  |  | 219
144 | YUM! Brands | Pizza Hut - LIC Program | Michelle Hudson | Emily Naufel | Relaunch | 30 | MG | 2015-03-27 | 2015-03-27 | 2015-03-27 | Y |  |  | 2
145 | Compass Group | Compass Food Safety Program | Brian Nolan | Eric Hightower | Relaunch | 24 | AD | 2015-03-31 | 2015-03-31 | 2015-03-31 | Y |  |  | 11
146 | Ace Restaurant Group | Ace Restaurants Food Safety Program | Brian Nolan | Eric Hightower | New Launch | 24 | BA | 2015-03-31 | 2015-06-01 | 2015-06-01 | Y |  |  | 219
147 | Adak Restaurants | Adak Restaurants Food Safety Program | John Bestler | Eric Hightower | New Launch | 24 | BA | 2015-03-31 | 2015-06-01 | 2015-06-01 | Y |  |  | 219
148 | Bicos Restaurant Group | Bicos Restaurant Group Food Safety Program | Keith Woith | Eric Hightower | New Launch | 0 | TA | 2015-03-31 | 2015-06-01 | 2015-06-01 | Y |  |  | 203
149 | CKE | CKE Bun Retrieval | John Bestler | Amanda Coulombe | New Launch | 24 | TA | 2015-03-31 | 2015-06-01 | 2015-06-01 | Y |  |  | 4
150 | Delta Hotels and Resort | Delta Hotels and Resort Food Safety Program | Justin Prestinario | Steve Steinberg | New Launch | 24 | TA | 2015-03-31 | 2015-06-01 | 2015-06-01 | Y |  |  | 219
151 | Donovan's Steak & Chop House | Donovan's Food Safety Program | Keith Woith | Steve Steinberg | New Launch | 24 | BA | 2015-03-31 | 2015-06-01 | 2015-06-01 | Y |  |  | 161
152 | Four Winds Casino | Four Winds Casino Food Safety Program | John Bestler | Steve Steinberg | New Launch | 24 | MG | 2015-03-31 | 2015-06-01 | 2015-06-01 | Y |  |  | 136
153 | Garbanzo | Garbanzo Food Safety Program | Keith Woith | Tim Cassidy | New Launch | 24 | TA | 2015-03-31 | 2015-06-01 | 2015-06-01 | Y |  |  | 205
154 | Genji Inc. | Genji Food Safety Program | Brian Nolan | Amanda Coulombe | New Launch | 0 | TA | 2015-03-31 | 2015-06-01 | 2015-06-01 | Y |  |  | 186
155 | Pizza Ranch | Pizza Ranch Food Safety Program | Justin Prestinario | Eric Hightower | New Launch | 24 | TA | 2015-03-31 | 2015-06-01 | 2015-06-01 | Y |  |  | 58
156 | LaRosa's | LaRosa's Food Safety Program | John Bestler | Steve Steinberg | Relaunch | 0 | RM | 2015-04-01 | 2015-01-01 | 2015-04-01 | Y |  |  | 87
157 | 85 ᵒC Café | 85 Degrees Celsius Café Food Safety Program | Keith Woith | Steve Steinberg | New Launch | 24 | AD | 2015-04-01 | 2015-03-01 | 2015-04-01 | Y |  |  | 98
158 | Fox Restaurant Concepts | Fox Restaurant QSR Evaluation | Keith Woith | Tim Cassidy | New Launch | 24 | TA | 2015-04-01 | 2015-03-01 | 2015-04-01 | Y |  |  | 68
159 | Fox Restaurant Concepts | Fox Restaurant Workplace Safety Program | Keith Woith | Tim Cassidy | New Launch | 24 | TA | 2015-04-01 | 2015-03-01 | 2015-04-01 | Y |  |  | 68
160 | Bloomin' Brands | Bloomin Brands Food Safety Program | Rob Siler | Steve Steinberg | Relaunch | 4 | AD | 2015-04-01 | 2015-04-01 | 2015-04-01 | Y |  |  | 13
161 | Burger King | Burger King GPV Program | John Bestler | Steve Steinberg | Relaunch | 0 | RM | 2015-04-01 | 2015-04-01 | 2015-04-01 | Y |  |  | 20
162 | Burger King | Burger King Playground Inspection Program | John Bestler | Steve Steinberg | Relaunch | 0 | MG | 2015-04-01 | 2015-04-01 | 2015-04-01 | Y |  |  | 20
163 | Cinemark | Cinemark Food Safety Program | Michelle Hudson | Tim Cassidy | Relaunch | 0 | AD | 2015-04-01 | 2015-04-01 | 2015-04-01 | Y |  |  | 29
164 | ClubCorp | Club Corp Food Safety | Michelle Hudson | Emily Naufel | Relaunch | 24 | MG | 2015-04-01 | 2015-04-01 | 2015-04-01 | Y |  |  | 63
165 | Delaware North | Delaware North Food Safety Program | Brian Nolan | Steve Steinberg | Relaunch | 0 | RM | 2015-04-01 | 2015-04-01 | 2015-04-01 | Y |  |  | 94
166 | Fairmont Hotels | Fairmont Food Safety Program | Justin Prestinario | Eric Hightower | New Launch | 40 | RM | 2015-04-01 | 2015-04-01 | 2015-04-01 | Y |  |  | 47
167 | Fairmont Hotels | Fairmont Guest Experience Program | Justin Prestinario | Eric Hightower | New Launch | 24 | RM | 2015-04-01 | 2015-04-01 | 2015-04-01 | Y |  |  | 47
168 | Golden Corral | Golden Corral Food Safety | Brian Nolan | Emily Naufel | Relaunch | 40 | MG | 2015-04-01 | 2015-04-01 | 2015-04-01 | Y |  |  | 21
169 | Mohonk | Mohonk Resort Brand Standards Program | Brian Nolan | Emily Naufel | New Launch | 24 | RM | 2015-04-01 | 2015-04-01 | 2015-04-01 | Y |  |  | 89
170 | Peet's Coffee & Tea | Peet's Coffee & Tea Food Safety Evaluations | Keith Woith | Amanda Coulombe | Relaunch | 0 | AD | 2015-04-01 | 2015-04-01 | 2015-04-01 | Y |  |  | 51
171 | Brinker | Brinker 2015 Audit Program | Michelle Hudson | Steve Steinberg | Relaunch | 24 | MG | 2015-04-10 | 2015-04-10 | 2015-04-10 | Y |  |  | 219
172 | HoneyBaked Ham | Honeybaked Ham Food Safety Program | Rob Siler | Emily Naufel | New Launch | 80 | MG | 2015-04-13 | 2015-04-13 | 2015-04-13 | Y |  |  | 37
173 | Caribou / Einstein | Caribou Coffee Assessment (Brand Standards) | Justin Prestinario | Tim Cassidy | Relaunch | 24 | AD | 2015-04-16 | 2015-04-16 | 2015-04-16 | Y |  |  | 18
174 | Sage Hospitality | Sage Hospitality Food Safety Program | Keith Woith | Emily Naufel | Relaunch | 8 | AD | 2015-04-20 | 2015-04-20 | 2015-04-20 | Y |  |  | 88
175 | Carlson Hotels Worldwide | Carlson Hotels Food Safety Program | Michelle Hudson | Eric Hightower | New Launch | 0 | BA | 2015-04-30 | 2015-06-01 | 2015-06-01 | Y |  |  | 219
176 | Millenium Resorts | Millennium Hotels Food Safety Evaluation Program | Keith Woith | Eric Hightower | New Launch | 0 | TA | 2015-04-30 | 2015-06-01 | 2015-06-01 | Y |  |  | 219
177 | O'Reilly Group | O’Reilly Food Safety Program | John Bestler | Eric Hightower | New Launch | 0 | BA | 2015-04-30 | 2015-06-01 | 2015-06-01 | Y |  |  | 219
178 | Ping Pong | Ping Pong Food Safety Program | Brian Nolan | Amanda Coulombe | New Launch | 0 | TA | 2015-04-30 | 2015-06-01 | 2015-06-01 | Y |  |  | 219
179 | Ping Pong | Ping Pong Workplace Safety Program | Brian Nolan | Amanda Coulombe | New Launch | 0 | TA | 2015-04-30 | 2015-06-01 | 2015-06-01 | Y |  |  | 219
180 | Quaker Steak & Lube | Quaker Steak & Lube 2008 Food Safety Evaluations | Brian Nolan | Steve Steinberg | New Launch | 24 | TA | 2015-04-30 | 2015-06-01 | 2015-06-01 | Y |  |  | 219
181 | Salem Senior | Salem Senior - 2008 Food Safety Evaluations | Brian Nolan | Amanda Coulombe | New Launch | 24 | TA | 2015-04-30 | 2015-06-01 | 2015-06-01 | Y |  |  | 219
182 | Willow Valley Resort | Willow Valley Food Safety Program | Brian Nolan | Steve Steinberg | New Launch | 24 | TA | 2015-04-30 | 2015-06-01 | 2015-06-01 | Y |  |  | 146
183 | Pinkberry | Pinkberry Food Safety Program | Keith Woith | Amanda Coulombe | Relaunch | 0 | AD | 2015-05-01 | 2015-04-15 | 2015-05-01 | Y |  |  | 219
184 | Checkers | Checkers Food Safety Program | Rob Siler | Steve Steinberg | Relaunch | 24 | RM | 2015-05-01 | 2015-05-01 | 2015-05-01 | Y |  |  | 22
185 | Corner Store | Corner Store Food Safety Program | Michelle Hudson | Steve Steinberg | Relaunch | 0 | AD | 2015-05-01 | 2015-05-01 | 2015-05-01 | Y |  |  | 27
186 | Cotton Patch Café | Cotton Patch Café Food Safety Program | Michelle Hudson | Emily Naufel | Request | 24 | AD | 2015-05-01 | 2015-05-01 | 2015-05-01 | Y |  |  | 97
187 | Hyatt Hotels | Hyatt Food Safety Program | John Bestler | Steve Steinberg | Relaunch | 40 | MG | 2015-05-01 | 2015-05-01 | 2015-05-01 | Y |  |  | 53
188 | Kona Grill | Kona Grill Food Safety Program | Keith Woith | Tim Cassidy | Relaunch | 24 | AD | 2015-05-01 | 2015-05-01 | 2015-05-01 | Y |  |  | 77
189 | Ocean Properties | Ocean Properties Food Safety Program | John Bestler | Steve Steinberg | Relaunch | 24 | MG | 2015-05-01 | 2015-05-01 | 2015-05-01 | Y |  |  | 86
190 | Silver Cloud | Silver Cloud Food Safety Program | Keith Woith | Eric Hightower | New Launch | 24 | AD | 2015-05-01 | 2015-05-01 | 2015-05-01 | Y |  |  | 178
191 | Tavistock | Tavistock Food Safety Program | Keith Woith | Steve Steinberg | Relaunch | 0 | RM | 2015-05-01 | 2015-05-01 | 2015-05-01 | Y |  |  | 106
192 | YUM! Brands | Pizza Hut - Co/FZ Program (and Operator App) | Michelle Hudson | Emily Naufel | Relaunch | 250 | RM | 2015-05-01 | 2015-05-01 | 2015-05-01 | Y |  |  | 2
193 | Starbucks | Starbucks Company Food Safety Program | Justin Prestinario | Tim Cassidy | Relaunch | 24 | AD | 2015-05-11 | 2015-05-11 | 2015-05-11 | Y |  |  | 1
194 | Starbucks | Starbucks LIC Food Safety Program | Justin Prestinario | Tim Cassidy | Relaunch | 24 | AD | 2015-05-11 | 2015-05-11 | 2015-05-11 | Y |  |  | 1
195 | CKE | CKE Mexico | John Bestler | Amanda Coulombe | Relaunch | 24 | RM | 2015-05-18 | 2015-05-01 | 2015-05-18 | Y |  |  | 4
196 | CKE | CKE Food Safety | John Bestler | Amanda Coulombe | Request | 24 | RM | 2015-05-18 | 2015-05-15 | 2015-05-18 | Y |  |  | 4
197 | Veteran's Canteen Services | VCS Food Safety & Barbershop Program | Rob Siler | Tim Cassidy | Relaunch | 24 | AD | 2015-05-25 | 2015-05-01 | 2015-05-25 | Y |  |  | 70
198 | Il Fornaio | Il Fornaio Food Safety Program | Michelle Hudson | Tim Cassidy | New Launch | 24 | AD | 2015-05-31 | 2015-06-01 | 2015-06-01 | Y |  |  | 100
199 | Royal Sonesta Hotel | Royal Sonesta Hotels Food Safety Program | Brian Nolan | Steve Steinberg | New Launch | 0 | BA | 2015-05-31 | 2015-06-01 | 2015-06-01 | Y |  |  | 219
200 | Select Restaurants | Select Restaurants Food Safety Program | John Bestler | Eric Hightower | New Launch | 24 | TA | 2015-05-31 | 2015-06-01 | 2015-06-01 | Y |  |  | 141
201 | The Resort at Pelican Hill | The Resort at Pelican Hill Food Safety Program | Keith Woith | Eric Hightower | New Launch | 0 | TA | 2015-05-31 | 2015-06-01 | 2015-06-01 | Y |  |  | 150
202 | Twisted Rooster | Twisted Rooster Food Safety Program 2012 | John Bestler | Steve Steinberg | New Launch | 0 | TA | 2015-05-31 | 2015-06-01 | 2015-06-01 | Y |  |  | 219
203 | Weber Grill | Weber Grill Food Safety | John Bestler | Tim Cassidy | New Launch | 24 | TA | 2015-05-31 | 2015-06-01 | 2015-06-01 | Y |  |  | 117
204 | Hyatt Hotels | Hyatt Hospitality Cleanliness Audit | John Bestler | Steve Steinberg | Relaunch | 40 | MG | 2015-06-01 | 2015-05-01 | 2015-06-01 | Y |  |  | 53
205 | 7-Eleven | 7-11 Canada Food Safety Program | Justin Prestinario | Amanda Coulombe | New Launch | 40 | AD | 2015-06-01 | 2015-06-01 | 2015-06-01 | Y |  |  | 219
206 | Bloomin' Brands | Bloomin Brands Food Safety Program | Rob Siler | Steve Steinberg | Relaunch | 40 | RM | 2015-06-01 | 2015-06-01 | 2015-06-01 | Y |  |  | 13
207 | Buffalo Wild Wings | Buffalo Wild Wings - CO & Franchise Food Safety Program | Justin Prestinario | Emily Naufel | Relaunch | 40 | AD | 2015-06-01 | 2015-06-01 | 2015-06-01 | Y |  |  | 15
208 | Ignite Restaurants | Ignite Food Safety Evaluation Program | Michelle Hudson | Amanda Coulombe | Relaunch | 0 | AD | 2015-06-01 | 2015-06-01 | 2015-06-01 | Y |  |  | 54
209 | Starwood | Starwood Storage & Receiving Program | Brian Nolan | Eric Hightower | Relaunch | 24 | RM | 2015-06-01 | 2015-06-01 | 2015-06-01 | Y |  |  | 166
210 | YUM! Brands | Pizza Hut - Co/FZ Program (and Operator App) | Michelle Hudson | Emily Naufel | Relaunch | 24 | RM | 2015-06-01 | 2015-06-01 | 2015-06-01 | Y |  |  | 2
211 | Twin Peaks | Twin Peaks Food Safety Program | Michelle Hudson | Eric Hightower | Relaunch | 32 | MG | 2015-06-08 | 2015-06-01 | 2015-06-08 | Y |  |  | 52
212 | Compass Group | Compass Food Safety Program | Brian Nolan | Eric Hightower | Relaunch | 32 | AD | 2015-06-15 | 2015-06-01 | 2015-06-15 | Y |  |  | 11
213 | Hilton | Hilton Beverage Program | Brian Nolan | Eric Hightower | Relaunch | 16 | RM | 2015-06-15 | 2015-06-01 | 2015-06-15 | Y |  |  | 25
214 | Brookdale | Brookdale Senior Living Program | John Bestler | Steve Steinberg | Relaunch | 40 | RM | 2015-06-15 | 2015-06-15 | 2015-06-15 | Y |  |  | 7
215 | Dickey's BBQ | Dickey's BBQ Food Safety & Brand Standards Program | Michelle Hudson | Tim Cassidy | Relaunch | 24 | AD | 2015-06-15 | 2015-06-15 | 2015-06-15 | Y |  |  | 219
216 | New York Office of Mental Health | NYSOMH Food Safety Program | Brian Nolan | Emily Naufel | Relaunch | 24 | MG | 2015-06-15 | 2015-08-03 | 2015-08-03 | Y |  |  | 219
217 | Linchris Hotels | Linchris Hotel Corporate Food Safety Program | Brian Nolan | Eric Hightower | New Launch | 24 | AD | 2015-06-21 | 2015-06-01 | 2015-06-21 | Y |  |  | 138
218 | Quorum | Quorum Food Safety Program | Keith Woith | Eric Hightower | New Launch | 24 | MG | 2015-06-21 | 2015-06-01 | 2015-06-21 | Y |  |  | 187
219 | Seaport Boston | Seaport Boston Food Safety Program | Brian Nolan | Steve Steinberg | New Launch | 24 | RM | 2015-06-21 | 2015-06-01 | 2015-06-21 | Y |  |  | 160
220 | SilverBirch Hotels | Silver Birch Food Safety Program | Justin Prestinario | Eric Hightower | New Launch | 24 | AD | 2015-06-22 | 2015-06-01 | 2015-06-22 | Y |  |  | 167
221 | Compass Group | Compass Canada English Form | Brian Nolan | Eric Hightower | Relaunch | 24 | MG | 2015-06-29 | 2015-06-15 | 2015-06-29 | Y |  |  | 11
222 | 85 ᵒC Café | 85 Degrees Celsius Café Food Safety Program | Keith Woith | Steve Steinberg | Relaunch | 0 | MG | 2015-07-01 | 2015-07-01 | 2015-07-01 | Y |  |  | 98
223 | Aramark | ARAMARK Food Safety Program | Brian Nolan | Amanda Coulombe | Relaunch | 0 | AD | 2015-07-01 | 2015-07-01 | 2015-07-01 | Y |  |  | 16
224 | Burger King | Burger King GPV Program | John Bestler | Steve Steinberg | Relaunch | 24 | RM | 2015-07-01 | 2015-07-01 | 2015-07-01 | Y |  |  | 20
225 | Dairy Queen | Dairy Queen Pride Program | Justin Prestinario | Amanda Coulombe | Relaunch | 40 | RM | 2015-07-01 | 2015-07-01 | 2015-07-01 | Y |  |  | 8
226 | DineEquity | Applebee's eCaPS Program | Keith Woith | Steve Steinberg | Relaunch | 80 | MG | 2015-07-01 | 2015-07-01 | 2015-07-01 | Y |  |  | 5
227 | DineEquity | IHOP OAR Program | Keith Woith | Steve Steinberg | Relaunch | 80 | MG | 2015-07-01 | 2015-07-01 | 2015-07-01 | Y |  |  | 5
228 | Fox Restaurant Concepts | Fox Restaurant QSR Evaluation | Keith Woith | Tim Cassidy | Relaunch | 24 | AD | 2015-07-01 | 2015-07-01 | 2015-07-01 | Y |  |  | 68
229 | Fox Restaurant Concepts | Fox Restaurant Workplace Safety Program | Keith Woith | Tim Cassidy | Relaunch | 24 | AD | 2015-07-01 | 2015-07-01 | 2015-07-01 | Y |  |  | 68
230 | Friendly's | Friendly's Food Safety Program | Brian Nolan | Emily Naufel | Relaunch | 24 | AD | 2015-07-01 | 2015-07-01 | 2015-07-01 | Y |  |  | 41
231 | Golden Corral | Golden Corral Food Safety | Brian Nolan | Emily Naufel | Relaunch | 0 | RM | 2015-07-01 | 2015-07-01 | 2015-07-01 | Y |  |  | 21
232 | Guckenheimer | Guckenheimer Food Safety & Workplace Safety Program | Keith Woith | Emily Naufel | Relaunch | 0 | AD | 2015-07-01 | 2015-07-01 | 2015-07-01 | Y |  |  | 42
233 | On The Border | On the Border Food Safety Program | Michelle Hudson | Steve Steinberg | Relaunch | 40 | RM | 2015-07-01 | 2015-07-01 | 2015-07-01 | Y |  |  | 46
234 | Starbucks | Starbucks Standardization Form Program | Justin Prestinario | Tim Cassidy | New Launch | 24 | AD | 2015-07-01 | 2015-07-01 | 2015-07-01 | Y |  |  | 1
235 | Glory Days | Glory Days Food Safety | Brian Nolan | Amanda Coulombe | New Launch | 24 | MG | 2015-07-08 | 2015-06-01 | 2015-07-08 | Y |  |  | 99
236 | Mambo | Mambo Food Safety Program | Michelle Hudson | Amanda Coulombe | New Launch | 24 | AD | 2015-07-08 | 2015-06-01 | 2015-07-08 | Y |  |  | 604
237 | Max Restaurant Group | Max Restaurant Group 2008 Food Safety Evaluation | Brian Nolan | Amanda Coulombe | New Launch | 24 | AD | 2015-07-08 | 2015-06-01 | 2015-07-08 | Y |  |  | 113
238 | Nando's | Nandos Food Safety Program | Brian Nolan | Amanda Coulombe | New Launch | 24 | RM | 2015-07-08 | 2015-06-01 | 2015-07-08 | Y |  |  | 219
239 | Nando's | Nandos Workplace Safety Program | Brian Nolan | Amanda Coulombe | New Launch | 24 | RM | 2015-07-08 | 2015-06-01 | 2015-07-08 | Y |  |  | 219
240 | Lawry's | Lawry's Food Safety Program | Keith Woith | Emily Naufel | New Launch | 24 | AD | 2015-07-13 | 2015-07-13 | 2015-07-13 | Y |  |  | 147
241 | Batali & Bastianich Hospitality Group | Batali & Bastianich Hospitality Group Food Safety Program | Brian Nolan | Emily Naufel | New Launch | 24 | AD | 2015-07-15 | 2015-07-15 | 2015-07-15 | Y |  |  | 219
242 | Sodexo | Sodexo Food Safety & HS Program | Brian Nolan | Eric Hightower | New Launch | 50 | MG | 2015-07-20 | 2015-07-20 | 2015-07-20 | Y |  |  | 9
243 | Interstate Hotels and Resorts | Interstate Beverage Program | Brian Nolan | Eric Hightower | Relaunch | 24 | MG | 2015-08-01 | 2015-06-01 | 2015-08-01 | Y |  |  | 48
244 | Interstate Hotels and Resorts | Interstate Food Safety Program | Brian Nolan | Eric Hightower | Relaunch | 24 | MG | 2015-08-01 | 2015-06-01 | 2015-08-01 | Y |  |  | 48
245 | Grand American Hotel | Grand America Food Safety Program | Keith Woith | Emily Naufel | New Launch | 24 | AD | 2015-08-01 | 2015-08-01 | 2015-08-01 | Y |  |  | 180
246 | Ignite Restaurants | Ignite Food Safety Evaluation Program | Michelle Hudson | Amanda Coulombe | Relaunch | 40 | RM | 2015-08-01 | 2015-08-01 | 2015-08-01 | Y |  |  | 54
247 | Panera Bread | Panera Bread Food Safety Program | John Bestler | Tim Cassidy | New Launch | 24 | AD | 2015-08-01 | 2015-08-01 | 2015-08-01 | Y |  |  | 10
248 | Pizza Ranch | Pizza Ranch Food Safety Program | Justin Prestinario | Eric Hightower | New Launch | 24 | AD | 2015-08-01 | 2015-08-01 | 2015-08-01 | Y |  |  | 58
249 | Dairy Queen | Dairy Queen Pride Program | Justin Prestinario | Amanda Coulombe | Relaunch | 30 | MG | 2015-08-06 | 2015-08-06 | 2015-08-06 | Y |  |  | 8
250 | Village Tavern | Village Tavern Food Safety Program | Rob Siler | Emily Naufel | Relaunch | 24 | RM | 2015-08-07 | 2015-08-07 | 2015-08-07 | Y |  |  | 114
251 | Wyndham Hotels | Wyndham Food Safety Program | Brian Nolan | Tim Cassidy | New Launch | 40 | RM | 2015-08-10 | 2015-08-01 | 2015-08-10 | Y |  | Missing store list | 80
252 | Caribou / Einstein | Caribou Coffee Assessment (Brand Standards) | Justin Prestinario | Tim Cassidy | Relaunch | 24 | AD | 2015-08-10 | 2015-08-10 | 2015-08-10 | Y |  |  | 18
253 | Shopper Events LLC | Shopper Events Food Safety Program | Keith Woith | Steve Steinberg | New Launch | 24 | MG | 2015-08-10 | 2015-08-10 | 2015-08-10 | Y |  |  | 45
254 | Brookdale | Brookdale Senior Living Program | John Bestler | Steve Steinberg | Relaunch | 40 | RM | 2015-08-12 | 2015-08-12 | 2015-08-12 | Y |  |  | 7
255 | Chick-fil-A | Chick-fil-A Catering Program | Rob Siler | Emily Naufel | Relaunch | 24 | AD | 2015-08-15 | 2015-08-15 | 2015-08-15 | Y |  | Moved up from 10/1 | 44
256 | Chick-fil-A | Chick-fil-A CPE Program | Rob Siler | Emily Naufel | Relaunch | 24 | AD | 2015-08-15 | 2015-08-15 | 2015-08-15 | Y |  | Moved up from 10/1 | 44
257 | Hard Rock Café | Hard Rock Café Food Safety Program | John Bestler | Amanda Coulombe | Relaunch | 0 | MG | 2015-08-15 | 2015-08-15 | 2015-08-15 | Y |  | Cancelled per Steph, 7/22 | 36
258 | Mohonk | Mohonk Resort Brand Standards Program | Brian Nolan | Emily Naufel | Relaunch | 24 | MG | 2015-08-15 | 2015-08-15 | 2015-08-15 | Y |  |  | 89
259 | Brookhaven | Brookhaven at Lexington Food Safety Evaluations | Brian Nolan | Amanda Coulombe | New Launch | 24 | KY | 2015-08-17 | 2015-08-17 | 2015-08-17 | Y |  | AccuSpec - Not Converting; Now converting 7/16 | 603
260 | Taco Mac | Taco Mac Food Safety Program | Rob Siler | Emily Naufel | New Launch | 24 | RM | 2015-08-24 | 2015-08-24 | 2015-08-24 | Y |  | Requested for 8/15 on 7/16 | 85
261 | On The Border | On the Border Food Safety Program | Michelle Hudson | Steve Steinberg | Relaunch | 24 | KY | 2015-08-30 | 2015-08-30 | 2015-08-30 | Y |  |  | 46
262 | Macaroni Grill | MacGrill Food Safety Program | Michelle Hudson | Amanda Coulombe | New Launch | 40 | RM | 2015-09-01 | 2015-08-10 | 2015-09-01 | Y |  | SC on vacation; no one avail to test; Pushed back from 8/1 > 8/10 > 9/1 by AT due to lack of customer responsiveness; signed off on 8/19 | 62
263 | RaceTrac | RaceTrac Food Safety Evaluations | Brian Nolan | Emily Naufel | New Launch | 24 | RM | 2015-09-01 | 2015-08-10 | 2015-09-01 | Y |  |  | 34
264 | Cinemark | Cinemark Brand Standards Program | Michelle Hudson | Tim Cassidy | New Launch | 40 | AD | 2015-09-01 | 2015-09-01 | 2015-09-01 | Y |  | Moved from 8/1 to 9/1 (JC - 6/11) | 29
265 | Compass Group | Compass Food Safety Program | Brian Nolan | Eric Hightower | Relaunch | 40 | AD | 2015-09-01 | 2015-09-01 | 2015-09-01 | Y |  |  | 11
266 | Compass Group | Compass HD Program | Brian Nolan | Eric Hightower | Relaunch | 40 | AD | 2015-09-01 | 2015-09-01 | 2015-09-01 | Y |  | No changes per JM - 6/30 | 11
267 | Compass Group | Compass Workplace Safety Program | Brian Nolan | Eric Hightower | Relaunch | 0 | AD | 2015-09-01 | 2015-09-01 | 2015-09-01 | Y |  |  | 11
268 | Greenville School System | Greenville Food Safety Program | Rob Siler | Amanda Coulombe | Relaunch | 0 | RM | 2015-09-01 | 2015-09-01 | 2015-09-01 | Y |  |  | 79
269 | Sodexo | Sodexo Food Safety & HS Program | Brian Nolan | Eric Hightower | New Launch | 40 | MG | 2015-09-01 | 2015-09-01 | 2015-09-01 | Y |  |  | 9
270 | YUM! Brands | Pizza Hut - Co/FZ Program (and Operator App) | Michelle Hudson | Emily Naufel | Relaunch | 40 | RM | 2015-09-01 | 2015-09-01 | 2015-09-01 | Y |  |  | 2
271 | CKE | CKE Food Safety | John Bestler | Amanda Coulombe | Relaunch | 0 | MG | 2015-09-10 | 2015-09-10 | 2015-09-10 | Y |  | No changes per Fred (7/22) | 4
272 | CKE | CKE Workplace Safety | John Bestler | Amanda Coulombe | Relaunch | 40 | MG | 2015-09-10 | 2015-09-10 | 2015-09-10 | Y |  |  | 4
273 | Dickey's BBQ | Dickey's BBQ Food Safety & Brand Standards Program | Michelle Hudson | Tim Cassidy | New Launch | 80 | AD | 2015-09-14 | 2015-09-14 | 2015-09-14 | Y |  |  | 219
274 | HMS Host | HMS Host Food Safety Program | Brian Nolan | Emily Naufel | New Launch | 50 | RM | 2015-09-14 | 2015-09-14 | 2015-09-14 | Y |  |  | 219
275 | Twin Peaks | Twin Peaks Food Safety Program | Michelle Hudson | Eric Hightower | Relaunch | 80 | MG | 2015-09-14 | 2015-09-14 | 2015-09-14 | Y |  | A bunch of form updates; no scoring changes (MO 7/23) | 52
276 | Twin Peaks | Twin Peaks Food Safety Program | Michelle Hudson | Eric Hightower | Relaunch | 16 | BH | 2015-09-18 | 2015-09-18 | 2015-09-18 | Y |  |  | 52
277 | Buffalo Wild Wings | Buffalo Wild Wings - CO & Franchise Food Safety Program | Justin Prestinario | Emily Naufel | Relaunch | 0 | MG | 2015-09-23 | 2015-09-23 | 2015-09-23 | Y |  | No changes per JM (7/28) | 15
278 | Buffalo Wild Wings | Buffalo Wild Wings - CO & Franchise Food Safety Program | Justin Prestinario | Emily Naufel | Relaunch | 24 | KY | 2015-09-23 | 2015-11-15 | 2015-11-15 | Y |  | CO & Fr originally req. 9/23; Fr pushed back to 11/15 (JP 7/23); No changes CO (JM 7/28); both programs w/ updates 9/23 (JM 8/26) | 15
279 | Starbucks | Starbucks Company Food Safety Program | Justin Prestinario | Tim Cassidy | Relaunch | 80 | RM | 2015-09-26 | 2015-09-26 | 2015-09-26 | Y |  |  | 1
280 | Starbucks | Starbucks Roastery Food Safety Program | Justin Prestinario | Tim Cassidy | Request | 0 | RM | 2015-09-26 | 2015-09-26 | 2015-09-26 | Y |  | This form to be combined with SBUX CO form as triggered questions (MO 8/31) | 1
281 | 85 ᵒC Café | 85 Degrees Celsius Café Food Safety Program | Keith Woith | Steve Steinberg | Relaunch | 0 | MG | 2015-10-01 | 2015-10-01 | 2015-10-01 | Y |  | No changes per EP email (9/3) | 98
282 | Aramark | ARAMARK Food Safety Program | Brian Nolan | Amanda Coulombe | Relaunch | 40 | AD | 2015-10-01 | 2015-10-01 | 2015-10-01 | Y |  |  | 16
283 | Areas USA | Areas USA Food Safety Program | John Bestler | Steve Steinberg | Relaunch | 0 | AD | 2015-10-01 | 2015-10-01 | 2015-10-01 | Y |  | No changes per MH - 7/30 | 93
284 | Brinker | Brinker 2015 Audit Program | Michelle Hudson | Steve Steinberg | Relaunch | 0 | MG | 2015-10-01 | 2015-10-01 | 2015-10-01 | Y |  | No longer a customer | 219
285 | Burger King | Burger King GPV Program | John Bestler | Steve Steinberg | Relaunch | 0 | AD | 2015-10-01 | 2015-10-01 | 2015-10-01 | Y |  | No changes per MH - 8/17 | 20
286 | Golden Corral | Golden Corral Food Safety | Brian Nolan | Emily Naufel | Relaunch | 24 | RM | 2015-10-01 | 2015-10-01 | 2015-10-01 | Y |  |  | 21
287 | Starwood | Starwood Beverage Program | Brian Nolan | Eric Hightower | Relaunch | 24 | KY | 2015-10-01 | 2015-10-01 | 2015-10-01 | Y |  | Reasigned to KY from RM; RM to validate setup | 166
288 | Starwood | Starwood Storage & Receiving Program | Brian Nolan | Eric Hightower | Relaunch | 24 | KY | 2015-10-01 | 2015-10-01 | 2015-10-01 | Y |  | Reasigned to KY from RM; RM to validate setup | 166
289 | Stripes | Stripes Food Safety Program | Michelle Hudson | Steve Steinberg | New Launch | 24 | MG | 2015-10-01 | 2015-10-01 | 2015-10-01 | Y |  | Appears to be a custom form; AT to meet with customer end of Aug; more info then; launch date may get pushed back (MO - 8/17) | 26
290 | Dairy Queen | Dairy Queen Pride Program | Justin Prestinario | Amanda Coulombe | Relaunch | 12 | RM | 2015-10-13 | 2015-10-13 | 2015-10-13 | Y |  |  | 8
291 | HMS Host | HMS Host Food Safety Program | Brian Nolan | Emily Naufel | New Launch | 16 | RM | 2015-10-15 | 2015-10-15 | 2015-10-15 | Y |  |  | 219
292 | Arcis Golf | Arcis Golf Food Safety Program | Michelle Hudson | Steve Steinberg | New Launch | 0 | KY | 2015-11-01 | 2015-09-01 | 2015-11-01 | Y |  | Standard FS Program; formerly "Eagle Golf"; 100% standard form/100 minus 5-3-1/standard email body (AT meeting; 8/12); pushed back to 10/1 by SS due to lack of customer info (MO 8/20); no contractor or meeting with contact - moving forward with standard 5/3/1 rollout (MO 9/14); program marked as complete due to no movement, will insert into schedule when Sales/AT ready to restart rollout (MO 10/12) | 603
293 | Café Zupa's | Café Zupas Food Safety Program | Keith Woith | Eric Hightower | New Launch | 24 | KY | 2015-11-01 | 2015-11-01 | 2015-11-01 | Y |  |  | 81
294 | John's Incredible Pizza | John's Incredible Pizza Food Safety Program | Keith Woith | Tim Cassidy | New Launch | 24 | JFH | 2015-11-01 | 2015-11-01 | 2015-11-01 | Y |  | Standard FS form per SH email from KW (8/24) | 125
295 | On The Border | On the Border Food Safety Program | Michelle Hudson | Steve Steinberg | New Launch | 0 | KY | 2015-11-01 | 2015-11-01 | 2015-11-01 | Y |  | No changes per EP email (MO 9/16) | 46
296 | Buffalo Wild Wings | Buffalo Wild Wings - CO & Franchise Food Safety Program | Justin Prestinario | Emily Naufel | Relaunch | 40 | KY | 2015-11-06 | 2015-11-06 | 2015-11-06 | Y |  |  | 15
297 | Compass Group | Compass Canada English Form | Brian Nolan | Eric Hightower | Relaunch | 40 | AD | 2015-11-09 | 2015-12-01 | 2015-12-01 | Y |  | Pushed back from 9/1 to 10/1, then asked for 1/1 but MO stated cannot due until Feb; JM asks for 12/1 which AD agrees to (MO 9/21); now requested to be moved up earlier, AD was ok with 11/9 (MO 9/24) | 11
298 | Compass Group | Compass Canada French Form | Brian Nolan | Eric Hightower | Relaunch | 40 | AD | 2015-11-09 | 2015-12-01 | 2015-12-01 | Y |  | Pushed back from 9/1 to 10/1, then asked for 1/1 but MO stated cannot due until Feb; JM asks for 12/1 which AD agrees to (MO 9/21); now requested to be moved up earlier, AD was ok with 11/9 (MO 9/24) | 11
299 | HoneyBaked Ham | Honeybaked Ham Holiday Program - Food Safety Program | Rob Siler | Emily Naufel | New Launch | 80 | BH | 2015-11-13 | 2015-11-13 | 2015-11-13 | Y |  |  | 37
300 | HoneyBaked Ham | Honeybaked Ham Holiday Program - PopUp Retail | Rob Siler | Emily Naufel | New Launch | 80 | BH | 2015-11-13 | 2015-11-13 | 2015-11-13 | Y |  |  | 37
301 | Jamba Juice | Jamba Juice Express Food Safety Program - iForm | Keith Woith | Tim Cassidy | New Launch | 0 | AD | 2015-11-15 | 2015-11-15 | 2015-11-15 | Y |  | No Express soft launch (SH 10/21) | 28
302 | Jamba Juice | Jamba Juice Express Food Safety Program - Steton Form | Keith Woith | Tim Cassidy | New Launch | 0 | AD | 2015-11-15 | 2015-11-15 | 2015-11-15 | Y |  | No Express soft launch (SH 10/21) | 28
303 | Jamba Juice | Jamba Juice Traditional Food Safety Program - iForm | Keith Woith | Tim Cassidy | New Launch | 0 | AD | 2015-11-15 | 2015-11-15 | 2015-11-15 | Y |  | Removed; we're only going to build the iForm for the full launch (SH 10/21) | 28
304 | Trusthouse (Aladdin) | TrustHouse Food Safety Program | Brian Nolan | Eric Hightower | New Launch | 24 | MG | 2015-11-15 | 2015-11-15 | 2015-11-15 | Y |  | (Formerly Aladdin's) Standard FS plus a few questions; still no hierarchy as of 9/9 (NC); MG still no information (9/9); pushed back to 11/15 due to no information and no current expecation of when it will be received (MO - 9/10) | 137
305 | Noodle's | Noodles Food Safety Program | Keith Woith | Steve Steinberg | New Launch | 80 | MG | 2015-11-19 | 2015-11-19 | 2015-11-19 | Y |  | No information other than custom form; SS emailing Keith - 8/17; SH/MO meeting on 10/7 - soft launch cancelled, only 1/1 | 32
306 | City BBQ | City BBQ Food Safety Program | John Bestler | Emily Naufel | New Launch | 40 | BH | 2015-11-23 | 2015-11-23 | 2015-11-23 | Y |  |  | 95
307 | iPic Theaters | iPic Food Safety Program | Rob Siler | Steve Steinberg | New Launch | 40 | BH | 2015-11-25 | 2015-11-25 | 2015-11-25 | Y |  |  | 102
308 | Chipotle | Chipotle Food Safety Program | Keith Woith | Amanda Coulombe | New Launch | 32 | BH | 2015-12-28 | 2015-12-28 | 2015-12-28 | Y |  | Deployment to determine most efficient setup for quick rollout | 6
309 | 85 ᵒC Café | 85 Degrees Celsius Café Food Safety Program | Keith Woith | Steve Steinberg | Relaunch | 12 | MG | 2016-01-01 | 2016-01-01 | 2016-01-01 | Y |  |  | 98
310 | Ace Restaurant Group | Ace Restaurants Food Safety Program | Brian Nolan | Eric Hightower | Relaunch | 12 | KY | 2016-01-01 | 2016-01-01 | 2016-01-01 | Y |  | No changes per EH email (MO 9/16) | 219
311 | Adak Restaurants | Adak Restaurants Food Safety Program | John Bestler | Eric Hightower | Relaunch | 12 | KY | 2016-01-01 | 2016-01-01 | 2016-01-01 | Y |  | No changes per EH email (MO 9/16) | 219
312 | Arby's | Arby's Food Safety Program | Rob Siler | Amanda Coulombe | Relaunch | 40 | MG | 2016-01-01 | 2016-01-01 | 2016-01-01 | Y |  |  | 19
313 | Areas USA | Areas USA Food Safety Program | John Bestler | Steve Steinberg | Relaunch | 24 | JFH | 2016-01-01 | 2016-01-01 | 2016-01-01 | Y |  |  | 93
314 | Batali & Bastianich Hospitality Group | Batali & Bastianich Hospitality Group Food Safety Program | Brian Nolan | Emily Naufel | Relaunch | 24 | JFH | 2016-01-01 | 2016-01-01 | 2016-01-01 | Y |  |  | 219
315 | Bloomin' Brands | Bloomin Brands Food Safety Program | Rob Siler | Steve Steinberg | Relaunch | 40 | AD | 2016-01-01 | 2016-01-01 | 2016-01-01 | Y |  |  | 13
316 | Burger King | Burger King Bun Sampling Program | John Bestler | Steve Steinberg | Relaunch | 12 | MG | 2016-01-01 | 2016-01-01 | 2016-01-01 | Y |  | No changes to form or RefNum per AF email (MO 9/21) | 20
317 | Burger King | Burger King GPV Program | John Bestler | Steve Steinberg | Relaunch | 24 | BH | 2016-01-01 | 2016-01-01 | 2016-01-01 | Y |  |  | 20
318 | Burger King | Burger King Playground Inspection Program | John Bestler | Steve Steinberg | Relaunch | 12 | MG | 2016-01-01 | 2016-01-01 | 2016-01-01 | Y |  | No changes per SH (9/9) | 20
319 | Burgerville | Burgerville Food Safety and Workplace Safety | Keith Woith | Emily Naufel | Relaunch | 24 | KY | 2016-01-01 | 2016-01-01 | 2016-01-01 | Y |  |  | 219
320 | Caribou / Einstein | Caribou Coffee Assessment (Brand Standards) | Justin Prestinario | Tim Cassidy | Relaunch | 24 | KY | 2016-01-01 | 2016-01-01 | 2016-01-01 | Y |  |  | 18
321 | Checkers | Checkers Food Safety Program | Rob Siler | Steve Steinberg | Relaunch | 40 | AD | 2016-01-01 | 2016-01-01 | 2016-01-01 | Y |  |  | 22
322 | Cornell University | Cornell Food Safety Program | Brian Nolan | Eric Hightower | Relaunch | 24 | KY | 2016-01-01 | 2016-01-01 | 2016-01-01 | Y |  |  | 110
323 | Corner Bakery | Corner Bakery Food Safety Evaluations | Michelle Hudson | Steve Steinberg | Relaunch | 24 | RM | 2016-01-01 | 2016-01-01 | 2016-01-01 | Y |  |  | 40
324 | Corner Store | Corner Store Food Safety Program | Michelle Hudson | Steve Steinberg | Relaunch | 24 | JFH | 2016-01-01 | 2016-01-01 | 2016-01-01 | Y |  |  | 27
325 | Culinaire Hospitality | Culinaire Food Safety Program | Brian Nolan | Eric Hightower | Relaunch | 24 | JFH | 2016-01-01 | 2016-01-01 | 2016-01-01 | Y |  |  | 152
326 | Dairy Queen | Dairy Queen Pride Program | Justin Prestinario | Amanda Coulombe | Relaunch | 32 | KY | 2016-01-01 | 2016-01-01 | 2016-01-01 | Y |  |  | 8
327 | Dairy Queen | Dairy Queen Pride Program | Justin Prestinario | Amanda Coulombe | Relaunch | 32 | AD | 2016-01-01 | 2016-01-01 | 2016-01-01 | Y |  |  | 8
328 | Dickey's BBQ | Dickey's BBQ Food Safety & Brand Standards Program | Michelle Hudson | Tim Cassidy | Relaunch | 24 | AD | 2016-01-01 | 2016-01-01 | 2016-01-01 | Y |  |  | 219
329 | Fairmont Hotels | Fairmont Food Safety Program | Justin Prestinario | Eric Hightower | Relaunch | 24 | BH | 2016-01-01 | 2016-01-01 | 2016-01-01 | Y |  | Customer still working through changes (EH 10/19); determining when new launch date should be dependent on when we get final scope | 47
330 | Fogo De Chao | Fogo de Chao Food Safety | Michelle Hudson | Eric Hightower | Relaunch | 24 | MG | 2016-01-01 | 2016-01-01 | 2016-01-01 | Y |  |  | 55
331 | Friendly's | Friendly's Food Safety Program | Brian Nolan | Emily Naufel | Relaunch | 24 | AD | 2016-01-01 | 2016-01-01 | 2016-01-01 | Y |  |  | 41
332 | Garbanzo | Garbanzo Food Safety Program | Keith Woith | Tim Cassidy | Relaunch | 24 | JFH | 2016-01-01 | 2016-01-01 | 2016-01-01 | Y |  |  | 205
333 | General Mills | General Mills Quarterly Retrieval | Division | Eric Hightower | Relaunch | 0 | BH | 2016-01-01 | 2016-01-01 | 2016-01-01 | Y |  | No changes per EH email; time tracker form (MO 9/16) | 142
334 | Golden Corral | Golden Corral Food Safety | Brian Nolan | Emily Naufel | Relaunch | 24 | AD | 2016-01-01 | 2016-01-01 | 2016-01-01 | Y |  |  | 21
335 | Granite City | Granite City Food Safety Assessments | Justin Prestinario | Tim Cassidy | Relaunch | 24 | BH | 2016-01-01 | 2016-01-01 | 2016-01-01 | Y |  |  | 50
336 | Guckenheimer | Guckenheimer Food Safety & Workplace Safety Program | Keith Woith | Emily Naufel | Relaunch | 24 | RM | 2016-01-01 | 2016-01-01 | 2016-01-01 | Y |  |  | 42
337 | Hard Rock Café | Hard Rock Café Food Safety Program | John Bestler | Amanda Coulombe | Relaunch | 24 | MG | 2016-01-01 | 2016-01-01 | 2016-01-01 | Y |  |  | 36
338 | Hilton | Hilton Beverage Program | Brian Nolan | Eric Hightower | Relaunch | 40 | KY | 2016-01-01 | 2016-01-01 | 2016-01-01 | Y |  |  | 25
339 | Hilton | Hilton Core Menu Program | Brian Nolan | Eric Hightower | Relaunch | 24 | KY | 2016-01-01 | 2016-01-01 | 2016-01-01 | Y |  |  | 25
340 | Hilton | Hilton Food Safety Program | Brian Nolan | Eric Hightower | Relaunch | 24 | KY | 2016-01-01 | 2016-01-01 | 2016-01-01 | Y |  |  | 25
341 | Hooters of America | Hooters Food Safety Program | Rob Siler | Emily Naufel | Relaunch | 24 | KY | 2016-01-01 | 2016-01-01 | 2016-01-01 | Y |  | Changes completed in November but AT requsted launch be pushed back to 3/1 due to unforeseen circumstances (MO - 12/16; CC email); Pushed back to 5/1 per JC (MO 12/31); AT requested current form be made live to use 2016 reference numbers, expecting more changes on 3/1 so both relaunches will happen (MO 1/4) | 30
342 | Il Fornaio | Il Fornaio Food Safety Program | Michelle Hudson | Tim Cassidy | Relaunch | 24 | RM | 2016-01-01 | 2016-01-01 | 2016-01-01 | Y |  |  | 100
343 | Johnny Rockets | Johnny Rockets Food Safety Program | Keith Woith | Tim Cassidy | Relaunch | 0 | AD | 2016-01-01 | 2016-01-01 | 2016-01-01 | Y |  | Removed per TC 8/6 | 219
344 | King's Seafood | King's Seafood Food Safety Program | Keith Woith | Tim Cassidy | Relaunch | 24 | BH | 2016-01-01 | 2016-01-01 | 2016-01-01 | Y |  |  | 132
345 | Kona Grill | Kona Grill Food Safety Program | Keith Woith | Tim Cassidy | Relaunch | 24 | KY | 2016-01-01 | 2016-01-01 | 2016-01-01 | Y |  |  | 77
346 | Landry's | Landry's Food Safety Program | Keith Woith | Tim Cassidy | Relaunch | 24 | JFH | 2016-01-01 | 2016-01-01 | 2016-01-01 | Y |  |  | 107
347 | LaRosa's | LaRosa's Food Safety Program | John Bestler | Steve Steinberg | Relaunch | 24 | BH | 2016-01-01 | 2016-01-01 | 2016-01-01 | Y |  |  | 87
348 | Lawry's | Lawry's Food Safety Program | Keith Woith | Emily Naufel | Relaunch | 24 | BH | 2016-01-01 | 2016-01-01 | 2016-01-01 | Y |  |  | 147
349 | Linchris Hotels | Linchris Hotel Corporate Food Safety Program | Brian Nolan | Eric Hightower | Relaunch | 24 | BH | 2016-01-01 | 2016-01-01 | 2016-01-01 | Y |  |  | 138
350 | LTP Management Group | LTP Food Safety Program | Rob Siler | Eric Hightower | Relaunch | 24 | JFH | 2016-01-01 | 2016-01-01 | 2016-01-01 | Y |  |  | 176
351 | Marcus Hotels | Marcus Hotels Food Safety Program | John Bestler | Tim Cassidy | Relaunch | 24 | JFH | 2016-01-01 | 2016-01-01 | 2016-01-01 | Y |  |  | 131
352 | McDonald's | McDonalds PlayPlace Program | Justin Prestinario | Eric Hightower | Relaunch | 40 | KY | 2016-01-01 | 2016-01-01 | 2016-01-01 | Y |  |  | 3
353 | Newk's | Newks Food Safety Program | Michelle Hudson | Steve Steinberg | Relaunch | 24 | JFH | 2016-01-01 | 2016-01-01 | 2016-01-01 | Y |  |  | 69
354 | Noodle's | Noodles Food Safety Program | Keith Woith | Steve Steinberg | Relaunch | 40 | MG | 2016-01-01 | 2016-01-01 | 2016-01-01 | Y |  |  | 32
355 | Ohio State University | Ohio State Food Safety Program | John Bestler | Eric Hightower | Relaunch | 24 | BH | 2016-01-01 | 2016-01-01 | 2016-01-01 | Y |  |  | 162
356 | Omni Hotels | Omni Hotels Food Safety Program | Michelle Hudson | Tim Cassidy | Relaunch | 24 | JFH | 2016-01-01 | 2016-01-01 | 2016-01-01 | Y |  |  | 57
357 | O'Reilly Group | O’Reilly Food Safety Program | John Bestler | Eric Hightower | Relaunch | 0 | BH | 2016-01-01 | 2016-01-01 | 2016-01-01 | Y |  | No changes per EH email; program cancelled (MO 9/15) | 219
358 | Pantry (Auntie M's) | Pantry Audits Food Safety Program | Brian Nolan | Tim Cassidy | Relaunch | 24 | JFH | 2016-01-01 | 2016-01-01 | 2016-01-01 | Y |  |  | 78
359 | Peet's Coffee & Tea | Peet's Coffee & Tea Food Safety Evaluations | Keith Woith | Amanda Coulombe | Relaunch | 24 | RM | 2016-01-01 | 2016-01-01 | 2016-01-01 | Y |  |  | 51
360 | Pizza Ranch | Pizza Ranch Food Safety Program | Justin Prestinario | Eric Hightower | Relaunch | 24 | AD | 2016-01-01 | 2016-01-01 | 2016-01-01 | Y |  |  | 58
361 | Potbelly's | Potbelly's Food Safety Program | John Bestler | Amanda Coulombe | New Launch | 24 | AD | 2016-01-01 | 2016-01-01 | 2016-01-01 | Y |  |  | 33
362 | Quest Food Management Services | Quest Food Safety Program (Maine HS) | John Bestler | Emily Naufel | New Launch | 40 | AD | 2016-01-01 | 2016-01-01 | 2016-01-01 | Y |  |  | 173
363 | Quorum | Quorum Food Safety Program | Keith Woith | Eric Hightower | Relaunch | 24 | KY | 2016-01-01 | 2016-01-01 | 2016-01-01 | Y |  |  | 187
364 | Select Restaurants | Select Restaurants Food Safety Program | John Bestler | Eric Hightower | Relaunch | 24 | KY | 2016-01-01 | 2016-01-01 | 2016-01-01 | Y |  |  | 141
365 | Silver Cloud | Silver Cloud Food Safety Program | Keith Woith | Eric Hightower | Relaunch | 12 | BH | 2016-01-01 | 2016-01-01 | 2016-01-01 | Y |  |  | 178
366 | Sodexo | Sodexo Food Safety & HS Program | Brian Nolan | Eric Hightower | Relaunch | 50 | MG | 2016-01-01 | 2016-01-01 | 2016-01-01 | Y |  |  | 9
367 | Stanford University | Stanford Food Safety Program | Keith Woith | Eric Hightower | Relaunch | 24 | BH | 2016-01-01 | 2016-01-01 | 2016-01-01 | Y |  |  | 118
368 | Stanford University | Stanford Workplace Safety Program | Keith Woith | Eric Hightower | Relaunch | 24 | BH | 2016-01-01 | 2016-01-01 | 2016-01-01 | Y |  |  | 118
369 | Starbucks | Starbucks LIC Food Safety Program | Justin Prestinario | Tim Cassidy | Relaunch | 24 | AD | 2016-01-01 | 2016-01-01 | 2016-01-01 | Y |  |  | 1
370 | Stripes | Stripes Food Safety Program | Michelle Hudson | Steve Steinberg | Relaunch | 24 | RM | 2016-01-01 | 2016-01-01 | 2016-01-01 | Y |  | Per RM email, project/ref num setup needs to be fixed for testing to be complete (MO 12/28) | 26
371 | TGI Friday's | TGIF Food Safety Program | Michelle Hudson | Eric Hightower | Relaunch | 40 | RM | 2016-01-01 | 2016-01-01 | 2016-01-01 | Y |  | Per RM email, project/ref num setup needs to be fixed for testing to be complete (MO 12/28); JC replied on 12/28 confirming test audits look good (MO 12/28) | 17
372 | Tommy Bahama | Tommy Bahama Food Safety Program | Rob Siler | Tim Cassidy | Relaunch | 24 | RM | 2016-01-01 | 2016-01-01 | 2016-01-01 | Y |  |  | 134
373 | Travel Centers of America | Travel Centers of America Food Safety Evaluation | John Bestler | Eric Hightower | Relaunch | 24 | AD | 2016-01-01 | 2016-01-01 | 2016-01-01 | Y |  |  | 65
374 | Twin Peaks | Twin Peaks Food Safety Program | Michelle Hudson | Eric Hightower | Relaunch | 24 | JFH | 2016-01-01 | 2016-01-01 | 2016-01-01 | Y |  | Replaced 1/1 launch with 11/25 launch per CC; this is designed to fit in an additional cycle of evals before the end of the year (MO 11/11); changed their mind and now only a 1/1 relaunch is needed (MO 11/16) | 52
375 | Veteran's Canteen Services | VCS Food Safety & Barbershop Program | Rob Siler | Tim Cassidy | Relaunch | 24 | KY | 2016-01-01 | 2016-01-01 | 2016-01-01 | Y |  |  | 70
376 | Village Tavern | Village Tavern Food Safety Program | Rob Siler | Emily Naufel | Relaunch | 24 | MG | 2016-01-01 | 2016-01-01 | 2016-01-01 | Y |  |  | 114
377 | Village Tavern | Village Tavern Workplace Safety Program | Rob Siler | Emily Naufel | Relaunch | 24 | MG | 2016-01-01 | 2016-01-01 | 2016-01-01 | Y |  |  | 114
378 | Weber Grill | Weber Grill Food Safety | John Bestler | Tim Cassidy | Relaunch | 24 | RM | 2016-01-01 | 2016-01-01 | 2016-01-01 | Y |  |  | 117
379 | YUM! Brands | Pizza Hut - Co/FZ Program (and Operator App) | Michelle Hudson | Emily Naufel | Relaunch | 200 | RM | 2016-01-01 | 2016-01-01 | 2016-01-01 | Y |  |  | 2
380 | YUM! Brands | Pizza Hut - LIC Program | Michelle Hudson | Emily Naufel | Relaunch | 50 | RM | 2016-01-01 | 2016-01-01 | 2016-01-01 | Y |  |  | 2
381 | YUM! Brands | Pizza Hut - Target Program | Michelle Hudson | Emily Naufel | Relaunch | 50 | RM | 2016-01-01 | 2016-01-01 | 2016-01-01 | Y |  |  | 2
382 | DineEquity | Applebee's eCaPS Program | Keith Woith | Steve Steinberg | Relaunch | 40 | MG | 2016-01-11 | 2016-01-01 | 2016-01-11 | Y |  | Actual start is 1/11; launch date adjusted to allow for setup and testing of hierarchy changes (MO 1/4) | 5
383 | DineEquity | IHOP OAR Program | Keith Woith | Steve Steinberg | Relaunch | 40 | MG | 2016-01-11 | 2016-01-01 | 2016-01-11 | Y |  | Actual start is 1/11; launch date adjusted to allow for setup and testing of hierarchy changes (MO 1/4) | 5
384 | CKE | CKE Food Safety | John Bestler | Amanda Coulombe | Relaunch | 80 | MG | 2016-01-15 | 2016-01-15 | 2016-01-15 | Y |  |  | 4
385 | CKE | CKE Playground Program | John Bestler | Amanda Coulombe | Relaunch | 24 | MG | 2016-01-15 | 2016-01-15 | 2016-01-15 | Y |  |  | 4
386 | CKE | CKE Workplace Safety | John Bestler | Amanda Coulombe | Relaunch | 40 | MG | 2016-01-15 | 2016-01-15 | 2016-01-15 | Y |  |  | 4
387 | Il Fornaio | Il Fornaio Food Safety Program | Michelle Hudson | Tim Cassidy | Relaunch | 0 | - | 2016-01-17 | 2017-01-01 | 2017-01-01 | Y |  | Due to 6/1/16 launch being pushed back to 11/1 (due to no scope as of 5/25) removing their 1/1/17 relaunch per TC's direction (MO 5/25) | 100
388 | EcoSure | Ecolab Workplace Safety Coolant Evaluation Forms | All | All | New Launch | 24 | RM | 2016-01-18 | 2016-01-18 | 2016-01-18 | Y |  | Meeting with CM, RM and WPS on 1/21; no action items per RM; WPS to reach out at some point if next steps needed (MO 1/25) | 603
389 | Famous Dave's | Famous Dave's Food Safety Program | Justin Prestinario | Eric Hightower | Relaunch | 24 | JFH | 2016-01-20 | 2016-01-01 | 2016-01-20 | Y |  | Completed & signed off on however customer demanded 2 new question additions on 12/17; AT agreed to push back start date to 1/8 to accommodate (MO - 12/17); start date pushed back again tho successfully launched on 1/20 (MO - 1/25) | 43
390 | Tavistock | Tavistock Food Safety Program | Keith Woith | Steve Steinberg | Relaunch | 16 | BH | 2016-01-20 | 2016-01-20 | 2016-01-20 | Y |  | A few last minute form updates requested by MH (MO - 1/11) | 106
391 | Pizza Ranch | Pizza Ranch Food Safety Program | Justin Prestinario | Eric Hightower | Relaunch | 8 | BH | 2016-01-29 | 2016-01-29 | 2016-01-29 | Y |  |  | 58
392 | RaceTrac | RaceTrac Food Safety Evaluations | Brian Nolan | Emily Naufel | Relaunch | 40 | RM | 2016-02-01 | 2015-10-01 | 2016-02-01 | Y |  | Moved from 10/1; moved from 12/1 to 1/1 per AV conversation, changes to be provided by 10/23 instead of 10/15 (MO 10/12); moved from 1/1 to 2/1 per RM due to customer needing more time (MO 12/28) | 34
393 | McDonald's | McDonalds Food Safety/ECS Program | Justin Prestinario | Eric Hightower | Relaunch | 40 | AD | 2016-02-01 | 2016-01-01 | 2016-02-01 | Y |  | Pushed back to 2/1 per EH (10/19) | 3
394 | Jamba Juice | Jamba Juice Traditional Food Safety Program - Steton Form | Keith Woith | Tim Cassidy | New Launch | 40 | AD | 2016-02-01 | 2016-01-11 | 2016-02-01 | Y |  |  | 28
395 | Buffalo Wild Wings | Buffalo Wild Wings - CO & Franchise Food Safety Program | Justin Prestinario | Emily Naufel | Relaunch | 24 | KY | 2016-02-01 | 2016-02-01 | 2016-02-01 | Y |  |  | 15
396 | Cotton Patch Café | Cotton Patch Café Food Safety Program | Michelle Hudson | Emily Naufel | Relaunch | 24 | JFH | 2016-02-01 | 2016-02-01 | 2016-02-01 | Y |  | Reference numbers and potentially 2015 form | 97
397 | Entertainment Cruises | Entertainment Cruises Food Saftey | John Bestler | Eric Hightower | Relaunch | 24 | JFH | 2016-02-01 | 2016-02-01 | 2016-02-01 | Y |  | AT said customer wishes to push back from 1/1 to 2/1 to communicate program changes (MO 12/22) | 56
398 | Honeybaked Ham | Honeybaked Ham Food Safety Program | Rob Siler | Emily Naufel | Relaunch | 24 | BH | 2016-02-01 | 2016-02-01 | 2016-02-01 | Y |  | Customer requesting changes after announced cycle - MH 8/31 | 37
399 | Jackson's | Jacksons Food Safety Program | Keith Woith | Amanda Coulombe | New Launch | 40 | BH | 2016-02-01 | 2016-02-01 | 2016-02-01 | Y |  | Standard FS with changes | 71
400 | Taco Mac | Taco Mac Food Safety Program | Rob Siler | Emily Naufel | Relaunch | 24 | BH | 2016-02-01 | 2016-02-01 | 2016-02-01 | Y |  |  | 85
401 | Twin Peaks | Twin Peaks Food Safety Program | Michelle Hudson | Eric Hightower | Relaunch | 24 | JFH | 2016-02-01 | 2016-02-01 | 2016-02-01 | Y |  | They will probably want more changes | 52
402 | Ignite Restaurants | Ignite Food Safety Evaluation Program | Michelle Hudson | Amanda Coulombe | Relaunch | 16 | KY | 2016-02-03 | 2016-02-03 | 2016-02-03 | Y |  | Accidentally left off schedule by AC, requested express relaunch which DEPL Team fit in (MO 1/25) | 54
403 | Macaroni Grill | MacGrill Food Safety Program | Michelle Hudson | Amanda Coulombe | Relaunch | 16 | JFH | 2016-02-03 | 2016-02-03 | 2016-02-03 | Y |  | Accidentally left off schedule by AC, requested express relaunch which DEPL Team fit in (MO 1/25); set live on 1/29 (MO 1/29) | 62
404 | Unidine | Unidine Food Safety Program | Brian Nolan | Steve Steinberg | New Launch | 24 | MG | 2016-02-08 | 2016-02-08 | 2016-02-08 | Y |  | 100% standard | 171
405 | Arni's Restaurants | Arni's Food Safety Program | John Bestler | Amanda Coulombe | Relaunch | 0 | AD | 2016-02-10 | 2016-02-10 | 2016-02-10 | Y |  | Program cancelled per AC 2016 remaining request email (10/29) | 219
406 | Arni's Restaurants | Arni's Work Place Safety Program | John Bestler | Amanda Coulombe | Relaunch | 0 | AD | 2016-02-10 | 2016-02-10 | 2016-02-10 | Y |  | Program cancelled per AC 2016 remaining request email (10/29) | 219
407 | Avendra Hospitality | Avendra Hospitality Food Safety Program | Brian Nolan | Amanda Coulombe | Relaunch | 24 | JFH | 2016-02-10 | 2016-02-10 | 2016-02-10 | Y |  | New master form udpates only (MO 1/7) | 74
408 | Mambo | Mambo Food Safety Program | Michelle Hudson | Amanda Coulombe | Relaunch | 24 | KY | 2016-02-10 | 2016-02-10 | 2016-02-10 | Y |  | KY knocked this out while waiting on signof for other 1/1 rollouts (MO 12/29) | 604
409 | Max Restaurant Group | Max Restaurant Group 2008 Food Safety Evaluation | Brian Nolan | Amanda Coulombe | Relaunch | 24 | BH | 2016-02-10 | 2016-02-10 | 2016-02-10 | Y |  |  | 113
410 | Noodle's | Noodles Food Safety Program | Keith Woith | Steve Steinberg | Relaunch | 24 | MG | 2016-02-10 | 2016-02-10 | 2016-02-10 | Y |  |  | 32
411 | On the Border | On the Border Food Safety Program | Michelle Hudson | Steve Steinberg | Relaunch | 24 | RM | 2016-02-12 | 2016-03-01 | 2016-03-01 | Y |  | Looking to change criticality point value by end of January, and still relaunch on 3/1 (MO 1/4); pulled up launch to 2/12 per AT's request since we didn't do a 2nd cycle (MO 2/2) | 46
412 | Pret A Manger | Pret A Manger Food Safety Program | Brian Nolan | Steve Steinberg | New Launch | 80 | BH | 2016-02-15 | 2016-02-01 | 2016-02-15 | Y |  | Pushing back to 2/8 to allow time for hierarchy build/load to Steton and testing; may be new form changes (MO 1/25); pushing back to 2/15 due to more changes as late as 2/5 (MO 2/8) | 64
413 | RaceTrac | RaceTrac Food Safety Evaluations | Brian Nolan | Emily Naufel | Request | 16 | BH | 2016-02-15 | 2016-02-15 | 2016-02-15 | Y |  | Custom onsite to pull in informational Positive Compliments question | 34
414 | Starbucks | Starbucks Company Food Safety Program | Justin Prestinario | Tim Cassidy | Relaunch | 0 | MG | 2016-02-15 | 2016-02-15 | 2016-02-15 | Y |  | Just a few question updated per JC (MO - 9/10); no changes per JC, waiting for 3/28 launch instead (MO 12/31) | 1
415 | Guckenheimer | Guckenheimer Food Safety & Workplace Safety Program | Keith Woith | Emily Naufel | Request | 8 | KY | 2016-02-16 | 2016-02-16 | 2016-02-16 | Y |  | AT forgot to request ref num updates for 1/1 rollout, making these now (MO 2/8) | 42
416 | Margaritaville | Margaritaville Food Safety Program | Rob Siler | Amanda Coulombe | Relaunch | 24 | KY | 2016-02-16 | 2016-02-16 | 2016-02-16 | Y |  |  | 103
417 | Metz & Associates | Metz Culinary Management | Brian Nolan | Amanda Coulombe | Relaunch | 24 | JFH | 2016-02-16 | 2016-02-16 | 2016-02-16 | Y |  |  | 59
418 | Centerplate | Centerplate Food Safety | Rob Siler | Emily Naufel | Relaunch | 24 | JFH | 2016-03-01 | 2016-02-01 | 2016-03-01 | Y |  | Update reference numbers and possibly 2015 form | 156
419 | Cheddar's | Cheddar's Casual Cafe Food Safety Evaluations | Michelle Hudson | Amanda Coulombe | Relaunch | 24 | KY | 2016-03-01 | 2016-02-01 | 2016-03-01 | Y |  | Reference numbers and potentially 2015 form | 39
420 | Gibson's Steakhouse | Gibsons Restaurant Group Audits | John Bestler | Emily Naufel | Relaunch | 24 | JFH | 2016-03-01 | 2016-02-01 | 2016-03-01 | Y |  | Reference numbers and potentially 2015 form | 127
421 | Mohonk | Mohonk Resort Brand Standards Program | Brian Nolan | Emily Naufel | Relaunch | 8 | MG | 2016-03-01 | 2016-02-01 | 2016-03-01 | Y |  | Update reference numbers | 89
422 | Mohonk | Mohonk Resort Food Safety Program | Brian Nolan | Emily Naufel | Relaunch | 24 | MG | 2016-03-01 | 2016-02-01 | 2016-03-01 | Y |  | Update reference numbers and 2015 form | 89
423 | Sage Hospitality | Sage Hospitality Food Safety Program | Keith Woith | Emily Naufel | Relaunch | 24 | BH | 2016-03-01 | 2016-02-01 | 2016-03-01 | Y |  | Update reference numbers and possibly 2015 form | 88
424 | Swissotel | Swissotel Food Safety | John Bestler | Emily Naufel | Relaunch | 0 | JFH | 2016-03-01 | 2016-02-01 | 2016-03-01 | Y |  | Program cancelled per MS (8/11) | 219
425 | Academia Barilla | Academia Barilla Food Safety | John Bestler | Steve Steinberg | Relaunch | 24 | BH | 2016-03-01 | 2016-03-01 | 2016-03-01 | Y |  |  | 157
426 | Bass Pro Shop | Bass Pro 2009 Food Safety Evaluations | John Bestler | Amanda Coulombe | Relaunch | 24 | MG | 2016-03-01 | 2016-03-01 | 2016-03-01 | Y |  |  | 76
427 | Buffalo Wild Wings | Buffalo Wild Wings - CO & Franchise Food Safety Program | Justin Prestinario | Emily Naufel | Relaunch | 24 | KY | 2016-03-01 | 2016-03-01 | 2016-03-01 | Y |  | BWW gave us reaudit business so new ref num needs to be added (MO 2/15) | 15
428 | Compass Group | Compass Canada English Form | Brian Nolan | Eric Hightower | Relaunch | 24 | AD | 2016-03-01 | 2016-03-01 | 2016-03-01 | Y |  | Added late due to new contact just sending over 2 question changes per JM email (MO 2/15) | 11
429 | Compass Group | Compass Canada French Form | Brian Nolan | Eric Hightower | Relaunch | 24 | AD | 2016-03-01 | 2016-03-01 | 2016-03-01 | Y |  | Added late due to new contact just sending over 2 question changes per JM email (MO 2/15) | 11
430 | Compass Group | Compass Food Safety Program | Brian Nolan | Eric Hightower | Relaunch | 24 | AD | 2016-03-01 | 2016-03-01 | 2016-03-01 | Y |  |  | 11
431 | Compass Group | Compass HD Program | Brian Nolan | Eric Hightower | Relaunch | 16 | AD | 2016-03-01 | 2016-03-01 | 2016-03-01 | Y |  | KP confirmed no changes (MO 2/10); AD cleaned up RefNums (MO 3/3) | 11
432 | Compass Group | Compass J&W Program | Brian Nolan | Eric Hightower | Relaunch | 24 | AD | 2016-03-01 | 2016-03-01 | 2016-03-01 | Y |  |  | 11
433 | Compass Group | Compass Workplace Safety Program | Brian Nolan | Eric Hightower | Relaunch | 24 | AD | 2016-03-01 | 2016-03-01 | 2016-03-01 | Y |  |  | 11
434 | HMS Host | HMS Host Food Safety Program | Brian Nolan | Emily Naufel | Relaunch | 0 | RM | 2016-03-01 | 2016-03-01 | 2016-03-01 | Y |  | Tentative if we win the business; moved from 2/1 to 3/1 per weekly meeting (MO - 1/7); removed all together for RM/EN email chain (MO 1/11) | 219
435 | Hyatt Hotels | Hyatt Food Safety Program | John Bestler | Steve Steinberg | Relaunch | 40 | MG | 2016-03-01 | 2016-03-01 | 2016-03-01 | Y |  |  | 53
436 | Hyatt Hotels | Hyatt Hospitality Cleanliness Audit | John Bestler | Steve Steinberg | Relaunch | 0 | MG | 2016-03-01 | 2016-03-01 | 2016-03-01 | Y |  | Program cancelled per MS (11/2) | 53
437 | iPic Theaters | iPic Food Safety Program | Rob Siler | Steve Steinberg | Relaunch | 0 | KY | 2016-03-01 | 2016-03-01 | 2016-03-01 | Y |  | No changes per AF email fwd. by KY (MO 1/25) | 102
438 | Ocean Properties | Ocean Properties Food Safety Program | John Bestler | Steve Steinberg | Relaunch | 24 | BH | 2016-03-01 | 2016-03-01 | 2016-03-01 | Y |  |  | 86
439 | Popeye's | Popeyes Food Safety Program | Rob Siler | Emily Naufel | New Launch | 100 | KY | 2016-03-01 | 2016-03-01 | 2016-03-01 | Y |  |  | 12
440 | Starbucks | Starbucks LIC Food Safety Program | Justin Prestinario | Tim Cassidy | Relaunch | 24 | AD | 2016-03-01 | 2016-03-01 | 2016-03-01 | Y |  |  | 1
441 | Vi | Vi Food Safety Program | John Bestler | Amanda Coulombe | Relaunch | 16 | JFH | 2016-03-01 | 2016-03-01 | 2016-03-01 | Y |  | Adding 1 question | 101
442 | Delta Hotels and Resort | Delta Hotels and Resort Food Safety Program | Justin Prestinario | Steve Steinberg | Relaunch | 24 | KY | 2016-03-01 | 2016-04-01 | 2016-04-01 | Y |  | Moved up to 3/1 per MN request; KY ok with it; just ref num changes (MO 2/1) | 219
443 | Vi | Vi Beverage Program | John Bestler | Amanda Coulombe | Relaunch | 24 | JFH | 2016-03-02 | 2016-02-02 | 2016-03-02 | Y |  | SC to req from MG an exsiting Bev form as a starting point (MO - 1/7) | 101
444 | Compass Group | Compass Food Safety Program | Brian Nolan | Eric Hightower | Relaunch | 40 | AD | 2016-03-08 | 2016-03-08 | 2016-03-08 | Y |  | FRED/Steton scoring comparison; FRED updated to remove 'hard-cap' and instead dynamically calculate points possible; Jen's team helped with comparison and rescore (MO 3/9) | 11
445 | YUM! Brands | Pizza Hut - Co/FZ Program (and Operator App) | Michelle Hudson | Emily Naufel | Relaunch | 16 | RM | 2016-03-08 | 2016-03-08 | 2016-03-08 | Y |  | Updating point values for ME.2C and ME.4H; updating question text (MO 3/5) | 2
446 | YUM! Brands | Pizza Hut - Co/FZ Program (and Operator App) | Michelle Hudson | Emily Naufel | Relaunch | 16 | MG | 2016-03-08 | 2016-03-08 | 2016-03-08 | Y |  | Updating onsite code to reference FormID / display message if wrong form is used (MO 3/4) | 2
447 | YUM! Brands | Pizza Hut - LIC Program | Michelle Hudson | Emily Naufel | Relaunch | 16 | MG | 2016-03-08 | 2016-03-08 | 2016-03-08 | Y |  | Updating onsite code to reference FormID / display message if wrong form is used (MO 3/4) | 2
448 | OTG Management | OTG Management 2008 Food Safety Evals | Brian Nolan | Amanda Coulombe | Relaunch | 24 | KY | 2016-03-09 | 2016-03-09 | 2016-03-09 | Y |  |  | 219
449 | Peter Piper Pizza | Peter Piper Pizza Mexico Food Safety Audits | Keith Woith | Amanda Coulombe | Relaunch | 40 | AD | 2016-03-09 | 2016-03-09 | 2016-03-09 | Y |  |  | 67
450 | White Lodging | White Lodging Food Safety Program | John Bestler | Amanda Coulombe | Relaunch | 24 | JFH | 2016-03-09 | 2016-03-09 | 2016-03-09 | Y |  |  | 108
451 | Z Foods | Z Foods Food Safety Program | Brian Nolan | Amanda Coulombe | Relaunch | 24 | RM | 2016-03-09 | 2016-03-09 | 2016-03-09 | Y |  |  | 602
452 | Compass Group | Compass Food Safety Program | Brian Nolan | Eric Hightower | Relaunch | 40 | AD | 2016-03-11 | 2016-03-11 | 2016-03-11 | Y |  | Compass onsite update; removing code to display score (MO 3/9) | 11
453 | CKE | CKE Mexico | John Bestler | Amanda Coulombe | Relaunch | 40 | MG | 2016-03-15 | 2016-01-15 | 2016-03-15 | Y |  | Pushed back to 2/15 per conversation with MG (MO 1/15); moved to 2/23 per FL (MO 2/10) | 4
454 | Starbucks | Starbucks Company Food Safety Program - French | Justin Prestinario | Tim Cassidy | Relaunch | 24 | RM | 2016-03-21 | 2015-10-15 | 2016-03-21 | Y |  |  | 1
455 | McDonald's | McDonalds PlayPlace Program | Justin Prestinario | Eric Hightower | Relaunch | 16 | JFH | 2016-03-25 | 2016-03-25 | 2016-03-25 | Y |  | Rush request for one additional informational question (MO 3/17) | 3
456 | Starbucks | Starbucks Company Food Safety Program | Justin Prestinario | Tim Cassidy | Relaunch | 24 | MG | 2016-03-28 | 2016-03-28 | 2016-03-28 | Y |  |  | 1
457 | Genji Inc. | Genji Food Safety Program | Brian Nolan | Amanda Coulombe | New Launch | 24 | BH | 2016-03-31 | 2016-03-31 | 2016-03-31 | Y |  |  | 186
458 | Brookdale | Brookdale Senior Living Program | John Bestler | Steve Steinberg | Relaunch | 60 | RM | 2016-04-01 | 2016-01-01 | 2016-04-01 | Y |  | Per MH email, pushed back from 1/1 to 2/1 (10/29); pushed back from 2/1 to 3/1 (MO 3/1); pushed back from 3/1 to 3/14 per SS (MO 2/15); pushed back from 3/14 to 4/1 for SH email (MO 2/26) | 7
459 | Aramark | ARAMARK Food Safety Program | Brian Nolan | Amanda Coulombe | Relaunch | 40 | RM | 2016-04-01 | 2016-03-01 | 2016-04-01 | Y |  | Per AC email on 9/21, a complete form and program overhaul; Pushed back from 1/1 to 2/1 (weekly mtg MO 10/14) | 16
460 | Panera Bread | Panera Bread Food Safety Program | John Bestler | Tim Cassidy | Relaunch | 24 | BH | 2016-04-01 | 2016-03-01 | 2016-04-01 | Y |  | Launch date pushed back to 3/15 per BH conversation with CC (MO 2/23) | 10
461 | Aramark | ARAMARK Food Safety Program | Brian Nolan | Amanda Coulombe | Relaunch | 0 | KY | 2016-04-01 | 2016-04-01 | 2016-04-01 | Y |  | Moved to 4/30 due to 3/1 soft launch and timing (MO 2/10); removed from schedule due to 3 Aramark launches happening in 3 month span (4/1, 4/25, 7/1), removed Aramark 7/1 launch and created a single 6/1 launch instead (MO 3/4) | 16
462 | Chipotle | Chipotle Food Safety Program | Keith Woith | Amanda Coulombe | Relaunch | 32 | MG | 2016-04-01 | 2016-04-01 | 2016-04-01 | Y |  | Deployment to determine most efficient setup for quick rollout | 6
463 | ClubCorp | Club Corp Food Safety | Michelle Hudson | Emily Naufel | Relaunch | 24 | MG | 2016-04-01 | 2016-04-01 | 2016-04-01 | Y |  |  | 63
464 | Compass Group | Compass Canada English Form | Brian Nolan | Eric Hightower | Relaunch | 16 | AD | 2016-04-01 | 2016-04-01 | 2016-04-01 | Y |  | Re-added due to item being missed in testing (criticality change of 1 question) MO 3/17 | 11
465 | Compass Group | Compass Canada French Form | Brian Nolan | Eric Hightower | Relaunch | 16 | AD | 2016-04-01 | 2016-04-01 | 2016-04-01 | Y |  | Re-added due to item being missed in testing (criticality change of 1 question) MO 3/17 | 11
466 | Dickey's BBQ | Dickey's BBQ Food Safety & Brand Standards Program | Michelle Hudson | Tim Cassidy | Relaunch | 0 | AD | 2016-04-01 | 2016-04-01 | 2016-04-01 | Y |  | Removed per TC (MO 3/10) | 219
467 | Entertainment Cruises | Entertainment Cruises Food Saftey | John Bestler | Eric Hightower | Relaunch | 24 | KY | 2016-04-01 | 2016-04-01 | 2016-04-01 | Y |  | CC request to delete 1 question (MO 2/15) | 56
468 | Famous Dave's | Famous Dave's Food Safety Program | Justin Prestinario | Eric Hightower | Relaunch | 0 | MG | 2016-04-01 | 2016-04-01 | 2016-04-01 | Y |  | We are anticipating a new client contact may want changes; just reference number updates and 2 new questions, can we pull this up (MO - 4/1); no changes per RH from MG email (MO 2/26) | 43
469 | Newk's | Newks Food Safety Program | Michelle Hudson | Steve Steinberg | Relaunch | 40 | RM | 2016-04-01 | 2016-04-01 | 2016-04-01 | Y |  |  | 69
470 | Old Spaghetti Factory | Old Spaghetti Factory Food Safety Program | Keith Woith | Tim Cassidy | New Launch | 40 | RM | 2016-04-01 | 2016-04-01 | 2016-04-01 | Y |  |  | 219
471 | Pantry (Auntie M's) | Pantry Audits Food Safety Program | Brian Nolan | Tim Cassidy | Relaunch | 0 | MG | 2016-04-01 | 2016-04-01 | 2016-04-01 | Y |  | Cancelled per KM; MG email (MO 2/24) | 78
472 | RaceTrac | RaceTrac Food Safety Evaluations | Brian Nolan | Emily Naufel | Relaunch | 0 | BH | 2016-04-01 | 2016-04-01 | 2016-04-01 | Y |  | No chanes per email from AV on 2/25; fwd from BH on 3/10 (MO 3/10) | 34
473 | Stripes | Stripes Food Safety Program | Michelle Hudson | Steve Steinberg | Relaunch | 24 | BH | 2016-04-01 | 2016-04-01 | 2016-04-01 | Y |  |  | 26
474 | TGI Friday's | TGIF Food Safety Program | Michelle Hudson | Eric Hightower | Relaunch | 24 | BH | 2016-04-01 | 2016-04-01 | 2016-04-01 | Y |  | Moved back from 4/1 to 7/1 per EH's email (MO 2/10) | 17
475 | Tropical Smoothie Café | Tropical Smoothie Café Food Safety Program | Brian Nolan | Tim Cassidy | New Launch | 40 | BH | 2016-04-01 | 2016-04-18 | 2016-04-18 | Y |  | Pulled up to 4/1 due to salesperson giving verbal commitment to customer (MO 3/10); SH stated reaudits will be done on a different form; standard form? (MO 3/23) | 31
476 | Caribou / Einstein | Caribou Co-Branded Program | Justin Prestinario | Tim Cassidy | New Launch | 24 | BH | 2016-04-04 | 2016-02-15 | 2016-04-04 | Y |  | Pushing back to 3/1 due to no information (MO 2/2); pushing back to 41 due to no information (MO 2/17); pushed back from 4/1 to 4/4 due to continuous last minute changes (MO 3/31) | 18
477 | McDonald's | McDonalds Food Safety/ECS Program | Justin Prestinario | Eric Hightower | Relaunch | 24 | AD | 2016-04-04 | 2016-04-04 | 2016-04-04 | Y |  | A few form change requests from MK (MO 3/8) | 3
478 | Popeye's | Popeyes Food Safety Program | Rob Siler | Emily Naufel | Relaunch | 40 | KY | 2016-04-04 | 2016-04-04 | 2016-04-04 | Y |  |  | 12
479 | Tilted Kilt | Tilted Kilt Food Safety Evaluations | Keith Woith | Steve Steinberg | Relaunch | 24 | AD | 2016-04-04 | 2016-04-04 | 2016-04-04 | Y |  | Added during 2016 schedule valdation (MO 3/3) | 196
480 | Starwood | Starwood Beverage Program | Brian Nolan | Eric Hightower | Relaunch | 40 | JFH | 2016-04-15 | 2016-03-01 | 2016-04-15 | Y |  | Currently paper; Moved back from 3/1 to 4/1 per EH due to Exec review timing - MO 12/21; pushed back to 4/15 due to customer changes (MO 3/3) | 166
481 | Starwood | Starwood Food Safety Program | Brian Nolan | Eric Hightower | Relaunch | 40 | JFH | 2016-04-15 | 2016-03-01 | 2016-04-15 | Y |  | Moved back from 3/1 to 4/1 per EH due to Exec review timing - MO 12/21; pushed back to 4/15 due to customer changes (MO 3/3) | 166
482 | Starwood | Starwood Storage & Receiving Program | Brian Nolan | Eric Hightower | Relaunch | 40 | JFH | 2016-04-15 | 2016-03-01 | 2016-04-15 | Y |  | Moved back from 3/1 to 4/1 per EH due to Exec review timing - MO 12/21; pushed back to 4/15 due to customer changes (MO 3/3) | 166
483 | Popeye's | Popeyes Food Safety Program | Rob Siler | Emily Naufel | Relaunch | 16 | KY | 2016-04-18 | 2016-04-18 | 2016-04-18 | Y |  | Need to add "Appreciation" question to score group so it can be edited in FRED (MO 4/14) | 12
484 | Jackson's | Jacksons Food Safety Program | Keith Woith | Amanda Coulombe | Relaunch | 40 | KY | 2016-04-25 | 2016-04-01 | 2016-04-25 | Y |  | Standard FS with changes; no word from customer on scope so pushing back per AT request (MO 2/29) | 71
485 | Sauce | Sauce Pizza and Wine Food Safety Program | Keith Woith | Tim Cassidy | New Launch | 24 | JFH | 2016-04-25 | 2016-04-25 | 2016-04-25 | Y |  | Per SH email, spinoff of Fox and wants exact copy of FS program (no WPS) - MO 2/10 | 130
486 | Jamba Juice | Jamba Juice Traditional Food Safety Program - iForm | Keith Woith | Tim Cassidy | Relaunch | 24 | AD | 2016-04-27 | 2016-01-01 | 2016-04-27 | Y |  | Pushing back from 3/1 to 3/14 (MO 1/28); pushing back to 4/27 (MO 2/25) | 28
487 | Jamba Juice | Jamba Juice Traditional Food Safety Program - Steton Form | Keith Woith | Tim Cassidy | Relaunch | 24 | AD | 2016-04-27 | 2016-01-01 | 2016-04-27 | Y |  | Pushing back from 3/1 to 3/14 (MO 1/28); pushing back to 4/27 (MO 2/25) | 28
488 | Jamba Juice | Jamba Juice Express Food Safety Program - iForm | Keith Woith | Tim Cassidy | New Launch | 0 | AD | 2016-04-27 | 2016-02-01 | 2016-04-27 | Y |  | pushing back to 4/27 (MO 2/25); removed from schedule per SH/TP meeting (MO 4/6) | 28
489 | Jamba Juice | Jamba Juice Express Food Safety Program - Steton Form | Keith Woith | Tim Cassidy | New Launch | 0 | AD | 2016-04-27 | 2016-02-01 | 2016-04-27 | Y |  | pushing back to 4/27 (MO 2/25); removed from schedule per SH/TP meeting (MO 4/6) | 28
490 | Sunkist | Sunkist Retrieval | Keith Woith | Eric Hightower | New Launch | 24 | KY | 2016-05-01 | 2016-02-01 | 2016-05-01 | Y |  | Moved back from 2/1 to 5/1 due to IHG launch; moved back up to February after IHG didn't materialize | 82
491 | Starbucks | Starbucks Roastery Food Safety Program | Justin Prestinario | Tim Cassidy | New Launch | 0 | MG | 2016-05-01 | 2016-02-15 | 2016-05-01 | Y |  | Reincarnation of La Boulange form (MO - 9/10); changes not ready for 2/15, pushed bacm to 3/9 to coincide with CO launch (MO 12/31); pushed back to 5/1 per JC due to customer being unable to provide scope on time (MO 3/9) | 1
492 | Hooters of America | Hooters Food Safety Program | Rob Siler | Emily Naufel | Relaunch | 24 | KY | 2016-05-01 | 2016-03-01 | 2016-05-01 | Y |  | We are anticipating a new client contact may want changes; per KY Deployment is all done but the AT is holding off on making the form live…our last step (MO 5/4) | 30
493 | Caribou / Einstein | Caribou Coffee Assessment (Brand Standards) | Justin Prestinario | Tim Cassidy | Relaunch | 24 | AD | 2016-05-01 | 2016-05-01 | 2016-05-01 | Y |  |  | 18
494 | DineEquity | IHOP OAR Program | Keith Woith | Steve Steinberg | Relaunch | 80 | AD | 2016-05-01 | 2016-05-01 | 2016-05-01 | Y |  |  | 5
495 | Kendall Senior Living | Kendal Senior Living Workplace Safety Program | Brian Nolan | Amanda Coulombe | New Launch | 40 | BH | 2016-05-01 | 2016-05-01 | 2016-05-01 | Y |  | Added per SH on 1/28; standard FS and WPS (MO 1/28); lots of delays, received signoff on 6/14 | 140
496 | Kendall Senior Living | Kendal Senior Living Food Safety Program | Brian Nolan | Amanda Coulombe | New Launch | 40 | BH | 2016-05-01 | 2016-05-01 | 2016-05-01 | Y |  | Added per SH on 1/28; standard FS and WPS (MO 1/28); lots of delays, received signoff on 6/14 | 140
497 | McDonald's | McDonalds PlayPlace Program | Justin Prestinario | Eric Hightower | Relaunch | 40 | JFH | 2016-05-01 | 2016-05-01 | 2016-05-01 | Y |  |  | 3
498 | YUM! Brands | Pizza Hut - Co/FZ Program | Michelle Hudson | Emily Naufel | Relaunch | 24 | RM | 2016-05-01 | 2016-05-01 | 2016-05-01 | Y |  | They are moving to quarterly we may not be updating the form quarterly | 2
499 | YUM! Brands | Pizza Hut - Operator App | Michelle Hudson | Emily Naufel | Relaunch | 24 | RM | 2016-05-01 | 2016-05-01 | 2016-05-01 | Y |  | They are moving to quarterly we may not be updating the form quarterly | 2
500 | YUM! Brands | Pizza Hut - Co/FZ Onsite | Michelle Hudson | Emily Naufel | Relaunch | 24 | MG | 2016-05-01 | 2016-05-01 | 2016-05-01 | Y |  | They are moving to quarterly we may not be updating the form quarterly | 2
501 | YUM! Brands | Pizza Hut - LIC Program | Michelle Hudson | Emily Naufel | Relaunch | 24 | RM | 2016-05-01 | 2016-05-01 | 2016-05-01 | Y |  | They are moving to quarterly we may not be updating the form quarterly | 2
502 | YUM! Brands | Pizza Hut - Target Program | Michelle Hudson | Emily Naufel | Relaunch | 24 | RM | 2016-05-01 | 2016-05-01 | 2016-05-01 | Y |  | They are moving to quarterly we may not be updating the form quarterly | 2
503 | CKE | CKE Playground Program | John Bestler | Amanda Coulombe | Relaunch | 0 | MG | 2016-05-10 | 2016-05-10 | 2016-05-10 | Y |  | Per FL email, no playground changes (MO 4/6) | 4
504 | CKE | CKE Workplace Safety | John Bestler | Amanda Coulombe | Relaunch | 40 | MG | 2016-05-10 | 2016-05-10 | 2016-05-10 | Y |  |  | 4
505 | McDonald's | McDonalds Food Safety/ECS Program | Justin Prestinario | Eric Hightower | Relaunch | 16 | KY | 2016-05-15 | 2016-05-01 | 2016-05-15 | Y |  | MK requested question removal 1.10.4 on 4/6 (MO 4/6) | 3
506 | Ocean Properties | Ocean Properties Food Safety Program | John Bestler | Steve Steinberg | Relaunch | 24 | KY | 2016-05-15 | 2016-05-01 | 2016-05-15 | Y |  | Ad hoc request from SS (MO 4/11) | 86
507 | Panera Bread | Panera Bread Food Safety Program | John Bestler | Tim Cassidy | Relaunch | 40 | BH | 2016-05-15 | 2016-05-01 | 2016-05-15 | Y |  | Additional pass/fail scoring threshold needed; reversion form and update calc (MO 4/7) | 10
508 | CKE | CKE Food Safety | John Bestler | Amanda Coulombe | Relaunch | 24 | MG | 2016-05-15 | 2016-05-15 | 2016-05-15 | Y |  |  | 4
509 | CKE | CKE Mexico | John Bestler | Amanda Coulombe | Relaunch | 24 | MG | 2016-05-15 | 2016-05-15 | 2016-05-15 | Y |  |  | 4
510 | Trusthouse (Aladdin) | TrustHouse Food Safety Program | Brian Nolan | Eric Hightower | Relaunch | 24 | BH | 2016-05-15 | 2016-05-15 | 2016-05-15 | Y |  | (Formerly Aladdin's) Standard FS plus a few questions; still no hierarchy as of 9/9 (NC); MG still no information (9/9); pushed back to 11/15 due to no information and no current expecation of when it will be received (MO - 9/10) | 137
511 | Starbucks | Starbucks Company Food Safety Program | Justin Prestinario | Tim Cassidy | Relaunch | 16 | AD | 2016-05-20 | 2016-05-20 | 2016-05-20 | Y |  | Request to update font size on onsite | 1
512 | Checkers | Checkers Food Safety Program | Rob Siler | Steve Steinberg | Relaunch | 24 | BH | 2016-05-31 | 2016-05-31 | 2016-05-31 | Y |  | Checkers onsite/custom calc logic updates (MO 5/11) | 22
513 | Glory Days | Glory Days Food Safety | Brian Nolan | Amanda Coulombe | Relaunch | 24 | RM | 2016-05-31 | 2016-05-31 | 2016-05-31 | Y |  |  | 99
514 | Cinemark | Cinemark Brand Standards Program | Michelle Hudson | Tim Cassidy | New Launch | 0 | RM | 2016-06-01 | 2016-04-01 | 2016-06-01 | Y |  | JC communicated 2 specialists need to perform test visits to collect data and review with the customer; training team does not have capacity to update the help text, which is a requirement for the specialists to conduct these, so no timeline available for when this will be complete; will need to be pushed back (MO 2/18); pushed back to 6/1 per JC in meeting (MO 2/25); removed from schedule per TC due to no possibility of having scope change soon (MO 4/15) | 29
515 | Aramark | ARAMARK Food Safety Program | Brian Nolan | Amanda Coulombe | Relaunch | 0 | MG | 2016-06-01 | 2016-06-01 | 2016-06-01 | Y |  | Created due to removing 4/25 and 7/1 rollouts (split them; MO 3/4); Per SC in meeting on 3/30 no changes 6/1 and will just relaunch on 10/1 | 16
516 | Buffalo Wild Wings | Buffalo Wild Wings - CO & Franchise Food Safety Program | Justin Prestinario | Emily Naufel | Relaunch | 24 | MG | 2016-06-01 | 2016-06-01 | 2016-06-01 | Y |  |  | 15
517 | Compass Group | Compass Food Safety Program | Brian Nolan | Eric Hightower | Relaunch | 16 | AD | 2016-06-01 | 2016-06-01 | 2016-06-01 | Y |  | AT requested question be updated to required on 4/1 (MO 4/6) | 11
518 | Compass Group | Compass J&W Program | Brian Nolan | Eric Hightower | Relaunch | 16 | AD | 2016-06-01 | 2016-06-01 | 2016-06-01 | Y |  | AT requested question be updated to required on 4/1 (MO 4/6) | 11
519 | Dairy Queen | Dairy Queen Pride Program | Justin Prestinario | Amanda Coulombe | Relaunch | 0 | AD | 2016-06-01 | 2016-06-01 | 2016-06-01 | Y |  | Was 5/1 & 7/1; split the difference and doing one 6/1 rollout (MO 2/10); per email from Fred no customer changes, just internal, so we're going to hold off until the next customer change request (MO 4/22) | 8
520 | Hilton | Hilton Cookie Program | Brian Nolan | Eric Hightower | New Launch | 0 | MG | 2016-06-01 | 2016-06-01 | 2016-06-01 | Y |  | New custom form to evaluate cookies at DoubleTree locations (MO 3/3); no changes and removed from schedule per weekly meeting on 5/6 (MO 5/6); going to substitute TGIF form who wants to change a few informational questions to scored (MO 5/6) | 25
521 | Hooters of America | Hooters Food Safety Program | Rob Siler | Emily Naufel | Relaunch | 0 | AD | 2016-06-01 | 2016-06-01 | 2016-06-01 | Y |  | Changes completed in November but AT requsted launch be pushed back to 3/1 due to unforeseen circumstances (MO - 12/16; CC email); Pushed back to 5/1 per JC (MO 12/31); Pushed back to 6/1 assuming we win RFP (MO 3/3); per CC Lync on 4/13 can be removed (MO 4/13) | 30
522 | Interstate Hotels and Resorts | Interstate Beverage Program | Brian Nolan | Eric Hightower | Relaunch | 24 | KY | 2016-06-01 | 2016-06-01 | 2016-06-01 | Y |  | Pushed back to May per EH (10/19); Pushed back to 6/1 per MK (MO 12/31); signed off on by 5/31 but not launching until September (MO 5/31) | 48
523 | Interstate Hotels and Resorts | Interstate Food Safety Program | Brian Nolan | Eric Hightower | Relaunch | 24 | KY | 2016-06-01 | 2016-06-01 | 2016-06-01 | Y |  | Pushed back to May per EH (10/19); Pushed back to 6/1 per MK (MO 12/31); reference number only changes (M) 3/24); signed off on by 5/31 but not launching until September (MO 5/31) | 48
524 | Peet's Coffee & Tea | Peet's Coffee & Tea Food Safety Evaluations | Keith Woith | Amanda Coulombe | Relaunch | 24 | KY | 2016-06-01 | 2016-06-01 | 2016-06-01 | Y |  |  | 51
525 | Snooze | Snooze Food Safety Program | Keith Woith | Amanda Coulombe | New Launch | 40 | BH | 2016-06-01 | 2016-06-01 | 2016-06-01 | Y |  | SH notified KW close to signing, no details available other than desire to launch in Q2 (MO 3/21); SH emailed all vested parties on 3/22 stating earliest we can launch is August (MO 3/21) | 112
526 | Taco Mac | Taco Mac Food Safety Program | Rob Siler | Emily Naufel | Relaunch | 0 | AD | 2016-06-01 | 2016-06-01 | 2016-06-01 | Y |  | No changes per JM email on 4/8 (MO 4/8) | 85
527 | Tropical Smoothie Café | Tropical Smoothie Café Food Safety Program | Brian Nolan | Tim Cassidy | Relaunch | 0 | BH | 2016-06-01 | 2016-06-01 | 2016-06-01 | Y |  | Added 3/23; not 100% certain but belief is customer wants us to do reaudits on our standard form (MO 3/25); originally was going to use 2 forms but per conversation with JK decided to add ~50 questions back to main TCS form; BH ok with it and 6/1 still a go (MO 5/5); pulled off the schedule due to lack of customer response (6/9) | 31
528 | Red Lobster | Red Lobster Food Safety Program | John Bestler | Amanda Coulombe | New Launch | 24 | RM | 2016-06-06 | 2016-05-30 | 2016-06-06 | Y |  | Transferring from their own Steton instance; standard form - AC email (1/8); pulled up from 5/30 to 5/15 (MO 2/10) | 23
529 | Brookdale | Brookdale Senior Living Program | John Bestler | Steve Steinberg | Relaunch | 60 | RM | 2016-06-08 | 2016-06-01 | 2016-06-08 | Y |  | "Phase 2" multi-product line rollout; launch pushed back to 6/8 per RM (MO 5/23) | 7
530 | Famous Dave's | Famous Dave's Food Safety Program | Justin Prestinario | Eric Hightower | Relaunch | 24 | RM | 2016-06-10 | 2016-06-10 | 2016-06-10 | Y |  | Just added on 5/6, form determined to always be setup incorrectly (MO 5/6) | 43
531 | Twin Peaks | Twin Peaks Food Safety Program | Michelle Hudson | Eric Hightower | Relaunch | 24 | MG | 2016-06-15 | 2016-06-01 | 2016-06-15 | Y |  | A few minor PL changes per CC; unexpected request (MO 3/18); more unexpected changes came in, pushed back from 6/1 to 6/15 (MO 5/23) | 52
532 | Aramark | ARAMARK Time Tracker Form | Brian Nolan | Amanda Coulombe | Relaunch | 24 | AD | 2016-06-26 | 2016-06-26 | 2016-06-26 | Y |  | Time tracker form needed per SC due to specialists not filling out EcoSure Time Tracker correctly (6/1) | 16
533 | Aramark | ARAMARK SAFE Food Safety Program | Brian Nolan | Amanda Coulombe | Relaunch | 40 | KY | 2016-06-26 | 2016-06-26 | 2016-06-26 | Y |  | Urgent request from SC (6/1) | 16
534 | LaRosa's | LaRosa's Food Safety Program | John Bestler | Steve Steinberg | Relaunch | 24 | MG | 2016-06-27 | 2016-06-01 | 2016-06-27 | Y |  | Added during 2016 schedule valdation (MO 3/3); score group is being removed so also box groups; FRED being updated to handle this; launch pushed back to 6/27 per MG email who connected with MH (MO 5/23) | 87
535 | Aramark | ARAMARK Food Safety Program | Brian Nolan | Amanda Coulombe | Relaunch | 0 | - | 2016-07-01 | 2016-07-01 | 2016-07-01 | Y |  | Removed from schedule due to 3 Aramark launches happening in 3 month span (4/1, 4/25, 7/1), removed Aramark 7/1 launch and created a single 6/1 launch instead (MO 3/4) | 16
536 | Bloomin' Brands | Bloomin Brands Food Safety Program | Rob Siler | Steve Steinberg | Relaunch | 40 | RM | 2016-07-01 | 2016-07-01 | 2016-07-01 | Y |  |  | 13
537 | Burgerville | Burgerville Food Safety and Workplace Safety | Keith Woith | Emily Naufel | Relaunch | 24 | BH | 2016-07-01 | 2016-07-01 | 2016-07-01 | Y |  |  | 219
538 | Caribou / Einstein | Caribou Co-Branded Program | Justin Prestinario | Tim Cassidy | Relaunch | 24 | AD | 2016-07-01 | 2016-07-01 | 2016-07-01 | Y |  | Per TC requested a relaunch be added for 7/1 (MO 3/31) | 18
539 | Checkers | Checkers Food Safety Program | Rob Siler | Steve Steinberg | Relaunch | 24 | BH | 2016-07-01 | 2016-07-01 | 2016-07-01 | Y |  | Ad Hoc request from SS for internal changes, maybe some customer (MO 4/11) | 22
540 | Checkers | Checkers Food Safety Program | Rob Siler | Steve Steinberg | Relaunch | 24 | BH | 2016-07-01 | 2016-07-01 | 2016-07-01 | Y |  | Checkers calc/onsite validation logic update | 22
541 | Cheddar's | Cheddar's Casual Cafe Food Safety Evaluations | Michelle Hudson | Amanda Coulombe | Relaunch | 24 | MG | 2016-07-01 | 2016-07-01 | 2016-07-01 | Y |  |  | 39
542 | Chipotle | Chipotle Food Safety Program | Keith Woith | Amanda Coulombe | Relaunch | 32 | AD | 2016-07-01 | 2016-07-01 | 2016-07-01 | Y |  | 7/1 and 10/1 launches requested by AC on 4/22 (MO 4/22) | 6
543 | DineEquity | Applebee's eCaPS Program | Keith Woith | Steve Steinberg | Relaunch | 80 | MG | 2016-07-01 | 2016-07-01 | 2016-07-01 | Y |  |  | 5
544 | Fox Restaurant Concepts | Fox Restaurant Workplace Safety Program | Keith Woith | Tim Cassidy | Relaunch | 0 | KY | 2016-07-01 | 2016-07-01 | 2016-07-01 | Y |  | No changes per TC, remove from schedule (MO 5/26) | 68
545 | Friendly's | Friendly's Food Safety Program | Brian Nolan | Emily Naufel | Relaunch | 24 | RM | 2016-07-01 | 2016-07-01 | 2016-07-01 | Y |  |  | 41
546 | Golden Corral | Golden Corral Food Safety | Brian Nolan | Emily Naufel | Relaunch | 24 | MG | 2016-07-01 | 2016-07-01 | 2016-07-01 | Y |  | Added during 2016 schedule valdation (MO 3/3) | 21
547 | Hilton | Hilton Food Safety Program | Brian Nolan | Eric Hightower | Relaunch | 0 | RM | 2016-07-01 | 2016-07-01 | 2016-07-01 | Y |  | Added during 2016 schedule valdation (MO 3/3); per RH email on 5/11 cancelling this rollout and replacing with TGIF (MO 5/12) | 25
548 | Jamba Juice | Jamba Juice Traditional Food Safety Program - iForm | Keith Woith | Tim Cassidy | Relaunch | 0 | AD | 2016-07-01 | 2016-07-01 | 2016-07-01 | Y |  | Per TC email on 4/1, swapping out this for Caribou Co-Branded program (MO 4/4); removed from schedule per SH/TP meeting (MO 4/6) | 28
549 | Jamba Juice | Jamba Juice Traditional Food Safety Program - Steton Form | Keith Woith | Tim Cassidy | Relaunch | 0 | AD | 2016-07-01 | 2016-07-01 | 2016-07-01 | Y |  | Move traditional programs to mid-September (MO 4/6); removed from schedule per SH/TP meeting (MO 4/6) | 28
550 | Noodle's | Noodles Food Safety Program | Keith Woith | Steve Steinberg | Relaunch | 24 | MG | 2016-07-01 | 2016-07-01 | 2016-07-01 | Y |  | Added during 2016 schedule valdation (MO 3/3) | 32
551 | Noodle's | Noodles Self-Assessment Program | Keith Woith | Steve Steinberg | Relaunch | 24 | MG | 2016-07-01 | 2016-07-01 | 2016-07-01 | Y |  | Added during 2016 schedule valdation (MO 3/3); added on 5/26 (MO 5/31) | 32
552 | Omni Hotels | Omni Hotels Food Safety Program | Michelle Hudson | Tim Cassidy | Relaunch | 0 | KY | 2016-07-01 | 2016-07-01 | 2016-07-01 | Y |  | Removed per meeting on 5/12 (MO 5/12) | 57
553 | On the Border | On the Border Food Safety Program | Michelle Hudson | Steve Steinberg | Relaunch | 24 | KY | 2016-07-01 | 2016-07-01 | 2016-07-01 | Y |  | Added during 2016 schedule valdation (MO 3/3) | 46
554 | Potbelly's | Potbelly's Food Safety Program | John Bestler | Amanda Coulombe | Relaunch | 24 | AD | 2016-07-01 | 2016-07-01 | 2016-07-01 | Y |  | EZ requesting be added for June relaunch (MO 1/11); AC asked to push back to 7/1 during 2016 schedule validation (MO 3/4) | 33
555 | Stripes | Stripes Food Safety Program | Michelle Hudson | Steve Steinberg | Relaunch | 0 | BH | 2016-07-01 | 2016-07-01 | 2016-07-01 | Y |  | No changtes per MH (6/2) | 26
556 | TGI Friday's | TGIF Food Safety Program | Michelle Hudson | Eric Hightower | Relaunch | 24 | RM | 2016-07-01 | 2016-07-01 | 2016-07-01 | Y |  | Added in place of Hilton FS per RH request, emailed on 5/11 (MO 5/12) | 17
557 | Verve Senior Living | Verve Senior Living Food Safety Program | Justin Prestinario | Steve Steinberg | New Launch | 40 | RM | 2016-07-01 | 2016-07-01 | 2016-07-01 | Y |  | New sale added 2/24 (MO 3/3) | 92
558 | Pizza Ranch | Pizza Ranch Food Safety Program | Justin Prestinario | Eric Hightower | Relaunch | 16 | AD | 2016-07-12 | 2016-07-01 | 2016-07-12 | Y |  | One question removal requested by CC (MO 4/6) | 58
559 | Fox Restaurant Concepts | Fox Restaurant QSR Evaluation | Keith Woith | Tim Cassidy | Relaunch | 20 | KY | 2016-07-15 | 2016-07-01 | 2016-07-15 | Y |  | No changes per TC, remove from schedule (MO 5/26); per AM customer now wants FDA updates; added back to schedule for 7/15 provided we get final form changes by 6/24 (6/14) | 68
560 | Starwood | Starwood Storage & Receiving Program | Brian Nolan | Eric Hightower | Relaunch | 12 | BH | 2016-07-15 | 2016-07-15 | 2016-07-15 | Y |  | Type in question text, requested by RH on 6/13; committed to RH on 6/27 | 166
561 | Burger King | Burger King Playground Inspection Program | John Bestler | Steve Steinberg | Relaunch | 24 | AD | 2016-07-15 | 2016-08-01 | 2016-08-01 | Y |  | Requested by MH to pull up to 7/1, asked if 7/15 was acceptable (6/8); reassigned from BH to KY (6/13) | 20
562 | Pret A Manger | Pret A Manger Food Safety Program | Brian Nolan | Steve Steinberg | Relaunch | 40 | BH | 2016-07-18 | 2016-07-01 | 2016-07-18 | Y |  | Added during 2016 schedule valdation (MO 3/3); rush request per EP on 5/11 to relaunch 6/1, customer wants to reduce form from 3.5 hours to 1.5, go from 2 to 4 cycles, threatening to put on hold; BH ok with 6/1 provided we get final form content by 5/17 (MO 5/11); email from EL on 5/17 states customer changed mind and now wants to revert back to original launch date of 7/1 (MO 5/18); customer changed their mind again and now wants to just remove form content to reduce TOS rather than migrate to standard form; Training needs to work with customer on this so will determine an actual launch date once they finalize that process; launch will be 2-3 weeks after this date, but pushed back to 8/1 for now (6/20); customer insistent we launch on 7/18, BH semi-confident we can hit that date (7/11) | 64
563 | Steak 'n Shake | Steak 'n Shake Food Safety Program | John Bestler | Tim Cassidy | New Launch | 40 | RM | 2016-07-18 | 2016-07-01 | 2016-07-18 | Y |  | Launch moved back to 7/18 due to scope delay (6/20) | 24
564 | Ignite Restaurants | Ignite Food Safety Evaluation Program | Michelle Hudson | Amanda Coulombe | Relaunch | 16 | MG | 2016-08-01 | 2016-07-01 | 2016-08-01 | Y |  | Emergency PL removal per AC request on 5/26 (MO 5/26) | 54
565 | Jackson's | Jacksons Food Safety Program | Keith Woith | Amanda Coulombe | Relaunch | 0 | RM | 2016-08-01 | 2016-07-01 | 2016-08-01 | Y |  | Standard FS with changes; per EZ's email on 5/27 customer has no changes so remove from schedule (MO 5/31) | 71
566 | Village Tavern | Village Tavern Food Safety Program | Rob Siler | Emily Naufel | Relaunch | 24 | AD | 2016-08-01 | 2016-07-01 | 2016-08-01 | Y |  |  | 114
567 | Village Tavern | Village Tavern Workplace Safety Program | Rob Siler | Emily Naufel | Relaunch | 24 | AD | 2016-08-01 | 2016-07-01 | 2016-08-01 | Y |  |  | 114
568 | Briad | Briad Food Safety Program | Keith Woith | Tim Cassidy | New Launch | 24 | BH | 2016-08-01 | 2016-08-01 | 2016-08-01 | Y |  | Just got form changes; added to schedule (6/13) | 115
569 | City BBQ | City BBQ Food Safety Program | John Bestler | Emily Naufel | Relaunch | 24 | RM | 2016-08-01 | 2016-08-01 | 2016-08-01 | Y |  | Won all business, a few form changes before launching per EN; launching 9/1 but will do work as August rollout (6/27) | 95
570 | Cornell University | Cornell Food Safety Program | Brian Nolan | Eric Hightower | Request | 24 | RM | 2016-08-01 | 2016-08-01 | 2016-08-01 | Y |  |  | 110
571 | Piada Group | Piada Group Food Safety Program | John Bestler | Emily Naufel | New Launch | 40 | MG | 2016-08-01 | 2016-08-01 | 2016-08-01 | Y |  | Added per AT meeting by EN (6/9); reassigned to MG from KY due to minimal CKE changes (6/30) | 96
572 | Creative Dining Services | Creative Dining Services Food Safety Program | John Bestler | Amanda Coulombe | Relaunch | 0 | BH | 2016-08-01 | 2016-09-01 | 2016-09-01 | Y |  | No changes per FL email on 5/11; instead will be launching on 1/15/17 (MO 5/11) | 123
573 | DineEquity | IHOP OAR Program | Keith Woith | Steve Steinberg | Relaunch | 0 | BH | 2016-08-01 | 2016-09-01 | 2016-09-01 | Y |  | No changes per AT | 5
574 | Greenville School System | Greenville Food Safety Program | Rob Siler | Amanda Coulombe | Relaunch | 24 | AD | 2016-08-01 | 2016-09-01 | 2016-09-01 | Y |  |  | 79
575 | CKE | CKE Food Safety | John Bestler | Amanda Coulombe | Relaunch | 4 | MG | 2016-08-01 | 2016-09-10 | 2016-09-10 | Y |  | Only HT changes per FL (6/27) | 4
576 | CKE | CKE Mexico | John Bestler | Amanda Coulombe | Relaunch | 4 | MG | 2016-08-01 | 2016-09-10 | 2016-09-10 | Y |  | Only HT changes per FL (6/27) | 4
577 | CKE | CKE Playground Program | John Bestler | Amanda Coulombe | Relaunch | 0 | MG | 2016-08-01 | 2016-09-10 | 2016-09-10 | Y |  | No changes for FL (6/27) | 4
578 | CKE | CKE Workplace Safety | John Bestler | Amanda Coulombe | Relaunch | 24 | MG | 2016-08-01 | 2016-09-10 | 2016-09-10 | Y |  |  | 4
579 | EcoSure | SafeGuard Food Safety Program (Quick Launch) | Division | All | New Launch | 16 | RM | 2016-08-08 | 2016-05-31 | 2016-08-08 | Y |  | No customer web or users, just the ability for our field to find a store, leave a printout and upload the results (M O 5/11); program pushed back indefinitely for time being; per RM, AK says CM working with Leadership and Finance to determine costs and other setup needed to distinguish different restaurant types (MO 5/26) | 603
580 | Pinnacle Entertainment Group | Pinnacle Casino Food Safety Program | Keith Woith | Emily Naufel | New Launch | 40 | BH | 2016-08-08 | 2016-07-01 | 2016-08-08 | Y |  | Just requested by SH on 5/31 (MO 5/31); KY completed most of rollout however hierarchy not loaded until week of 7/25 so launch pushed back to 8/8 | 73
581 | 85 ᵒC Café | 85 Degrees Celsius Café Food Safety Program | Keith Woith | Steve Steinberg | Relaunch | 24 | MG | 2016-08-08 | 2016-08-01 | 2016-08-08 | Y |  | No scope provided until week of 7/25 so launch pushed back to 8/8 | 98
582 | Panera Bread | Panera Bread Brand Standards Program | John Bestler | Tim Cassidy | New Launch | 100 | BH | 2016-08-08 | 2016-08-01 | 2016-08-08 | Y |  |  | 10
583 | RaceTrac | RaceTrac Food Safety Evaluations | Brian Nolan | Emily Naufel | Relaunch | 24 | RM | 2016-08-08 | 2016-09-01 | 2016-09-01 | Y |  | Launch pushed back to 9/1 per EN due to delay in first cycle go live (MO 3/24); targeting signoff asap but still waiting on more changes per RM email (7/26); very challenging getting changes from the customer, signoff not happening until last week of August | 34
584 | Hooters of America | Hooters Food Safety Program | Rob Siler | Emily Naufel | Relaunch | 24 | JF | 2016-08-10 | 2016-08-08 | 2016-08-10 | Y |  | Form updates requested by CC on 7/18 for an 8/8 launch; mentioned in previous emails but no details provided other than upcoming form changes; CC wants to push back launch to 8/10 due to her being on vacation until 8/8 (7/29) | 30
585 | Sauce | Sauce Pizza and Wine Food Safety Program | Keith Woith | Tim Cassidy | Relaunch | 24 | JF | 2016-08-15 | 2016-08-15 | 2016-08-15 | Y |  | AM requested customer be setup with CAM on 7/18 | 130
586 | Twin Peaks | Twin Peaks Food Safety Program | Michelle Hudson | Eric Hightower | Relaunch | 16 | JF | 2016-08-15 | 2016-08-15 | 2016-08-15 | Y |  | CC requested a reaudit reference number be added on 7/26 | 52
587 | Caribou / Einstein | Caribou Coffee Assessment (Brand Standards) | Justin Prestinario | Tim Cassidy | Relaunch | 24 | AD | 2016-08-15 | 2016-09-01 | 2016-09-01 | Y |  |  | 18
588 | Popeye's | Popeyes Food Safety Program | Rob Siler | Emily Naufel | Relaunch | 40 | JF | 2016-08-27 | 2016-08-27 | 2016-08-27 | Y |  | Added during 2016 schedule valdation (MO 3/3) | 12
589 | Compass Group | Compass Food Safety Program | Brian Nolan | Eric Hightower | Relaunch | 24 | BH | 2016-09-01 | 2016-09-01 | 2016-09-01 | Y |  |  | 11
590 | Compass Group | Compass HD Program | Brian Nolan | Eric Hightower | Relaunch | 24 | BH | 2016-09-01 | 2016-09-01 | 2016-09-01 | Y |  |  | 11
591 | Compass Group | Compass Workplace Safety Program | Brian Nolan | Eric Hightower | Relaunch | 24 | BH | 2016-09-01 | 2016-09-01 | 2016-09-01 | Y |  |  | 11
592 | Hyatt Hotels | Hyatt Food Safety Program | John Bestler | Steve Steinberg | Relaunch | 0 | - | 2016-09-01 | 2016-09-01 | 2016-09-01 | Y |  | Removed during 2016 schedule valdation (MO 3/3) | 53
593 | Travel Centers of America | Travel Centers of America Food Safety Evaluation | John Bestler | Eric Hightower | Relaunch | 24 | JF | 2016-09-01 | 2016-09-01 | 2016-09-01 | Y |  | Scoring change requested by MK on 7/21; moving to 100 minus 5/3/1 | 65
594 | YUM! Brands | Pizza Hut - Co/FZ Program | Michelle Hudson | Emily Naufel | Relaunch | 24 | AD | 2016-09-01 | 2016-09-01 | 2016-09-01 | Y |  | They are moving to quarterly we may not be updating the form quarterly | 2
595 | YUM! Brands | Pizza Hut - Operator App | Michelle Hudson | Emily Naufel | Relaunch | 24 | AD | 2016-09-01 | 2016-09-01 | 2016-09-01 | Y |  | They are moving to quarterly we may not be updating the form quarterly | 2
596 | YUM! Brands | Pizza Hut - LIC Program | Michelle Hudson | Emily Naufel | Relaunch | 24 | AD | 2016-09-01 | 2016-09-01 | 2016-09-01 | Y |  | They are moving to quarterly we may not be updating the form quarterly | 2
597 | YUM! Brands | Pizza Hut - Target Program | Michelle Hudson | Emily Naufel | Relaunch | 24 | AD | 2016-09-01 | 2016-09-01 | 2016-09-01 | Y |  | They are moving to quarterly we may not be updating the form quarterly | 2
598 | Eureka! | Eureka Food Safety Program | Keith Woith | Emily Naufel | New Launch | 24 | BH | 2016-09-08 | 2016-08-01 | 2016-09-08 | Y |  | Requested Q3 launch from SH (6/10); scope supposed to have been provided by customer on 7/29 but then needed to be reviewed by Training Team, targetting 8/15 pending we get these soon and they're not too substantial (8/1); pushed back to 9/8 due to lack of scope and no hierarchy | 111
599 | Cattleman's | Cattlemens Food Safety Evaluation | Keith Woith | Amanda Coulombe | New Launch | 24 | JF | 2016-09-08 | 2016-09-01 | 2016-09-08 | Y |  | 100% standard FS; pushed back to 9/8 due to lack of scope | 129
600 | Chick-fil-A | Chick-fil-A Outside Payment Special Study | Rob Siler | Emily Naufel | Relaunch | 24 | AP | 2016-09-15 | 2016-09-15 | 2016-09-15 | Y |  | SH email on 7/7 states a good chance there will be an additional form; per TC on 7/26, no scoring, no web reports, no feedback reports, DO need an onsite | 44
601 | EcoSure | Ecosure Refused Entry Form | Division | All | Relaunch | 16 | RD | 2016-09-15 | 2016-09-15 | 2016-09-15 | Y |  | Removing Darden/Red Lobster text from client name question | 603
602 | Jamba Juice | Jamba Juice Traditional Food Safety Program - Steton Form | Keith Woith | Tim Cassidy | Relaunch | 40 | AD | 2016-09-15 | 2016-09-15 | 2016-09-15 | Y |  |  | 28
603 | Twin Peaks | Twin Peaks Food Safety Program | Michelle Hudson | Eric Hightower | New Launch | 16 | JF | 2016-09-30 | 2016-09-30 | 2016-09-30 | Y |  | Wrong reference number provided on recent relaunch; reversion form to correct ref num (9/27) | 52
604 | Compass Group | Compass J&W Program | Brian Nolan | Eric Hightower | Relaunch | 24 | JF | 2016-10-01 | 2016-09-01 | 2016-10-01 | Y |  |  | 11
605 | Jamba Juice | Jamba Juice Express Food Safety Program - iForm | Keith Woith | Tim Cassidy | New Launch | 0 | AD | 2016-10-01 | 2016-09-15 | 2016-10-01 | Y |  | Originally 7/1 but pushed back to 9/15 (MO 4/14); per VB email on 7/29 no launch due to internal changes on Jamba's end | 28
606 | Jamba Juice | Jamba Juice Express Food Safety Program - Steton Form | Keith Woith | Tim Cassidy | New Launch | 0 | AD | 2016-10-01 | 2016-09-15 | 2016-10-01 | Y |  | Originally 7/1 but pushed back to 9/15 (MO 4/14); per VB email on 7/29 no launch due to internal changes on Jamba's end | 28
607 | Jamba Juice | Jamba Juice Traditional Food Safety Program - iForm | Keith Woith | Tim Cassidy | Relaunch | 40 | AD | 2016-10-01 | 2016-09-15 | 2016-10-01 | Y |  |  | 28
608 | Compass Group | Compass Canada English Form | Brian Nolan | Eric Hightower | Relaunch | 24 | MG | 2016-10-01 | 2016-09-26 | 2016-10-01 | Y |  | Contact on vacation and unable to provide changes on time for 10/1 rollout; AT requesting 11/1 but told them we'll wait until we receive changes to determine if we can fit this in (8/30) | 11
609 | Compass Group | Compass Canada French Form | Brian Nolan | Eric Hightower | Relaunch | 24 | MG | 2016-10-01 | 2016-09-26 | 2016-10-01 | Y |  | Contact on vacation and unable to provide changes on time for 10/1 rollout; AT requesting 11/1 but told them we'll wait until we receive changes to determine if we can fit this in (8/30) | 11
610 | 4 Rivers Smokehouse | 4 Rivers Smokehouse Food Safety Evaluation | Rob Siler | Amanda Coulombe | New Launch | 24 | RD | 2016-10-01 | 2016-10-01 | 2016-10-01 | Y |  | Standard form, 100 minus 5/3/1 | 144
611 | Aramark | ARAMARK Food Safety Program | Brian Nolan | Amanda Coulombe | Relaunch | 0 | AP | 2016-10-01 | 2016-10-01 | 2016-10-01 | Y |  | No changes per SC during 8/22 mtg | 16
612 | Aramark | ARAMARK SAFE Food Safety Program | Brian Nolan | Amanda Coulombe | Relaunch | 40 | AP | 2016-10-01 | 2016-10-01 | 2016-10-01 | Y |  |  | 16
613 | Buffalo Wild Wings | Buffalo Wild Wings - CO & Franchise Food Safety Program | Justin Prestinario | Emily Naufel | Relaunch | 24 | MG | 2016-10-01 | 2016-10-01 | 2016-10-01 | Y |  |  | 15
614 | Chipotle | Chipotle Food Safety Program | Keith Woith | Amanda Coulombe | Relaunch | 32 | AD | 2016-10-01 | 2016-10-01 | 2016-10-01 | Y |  | 7/1 and 10/1 launches requested by AC on 4/22 (MO 4/22) | 6
615 | Jackson's | Jacksons Food Safety Program | Keith Woith | Amanda Coulombe | Relaunch | 24 | JF | 2016-10-01 | 2016-10-01 | 2016-10-01 | Y |  |  | 71
616 | King's Seafood | King's Seafood Food Safety Program | Keith Woith | Tim Cassidy | Relaunch | 16 | AD | 2016-10-01 | 2016-10-01 | 2016-10-01 | Y |  | Scoring change request from AM on 8/8; create autofail for 2+ criticals | 132
617 | Medieval Times | Medieval Times Food Safety Program | Michelle Hudson | Amanda Coulombe | New Launch | 0 | - | 2016-10-01 | 2016-10-01 | 2016-10-01 | Y |  | Added on 8/8 per AC email request on 8/3; will be launching on SafeGuard | 153
618 | Mimi's Café | Mimi's Café Food Safety Program | Michelle Hudson | Tim Cassidy | New Launch | 24 | BH | 2016-10-01 | 2016-10-01 | 2016-10-01 | Y |  |  | 75
619 | Olga's Kitchen | Olga's Kitchen Food Safety Program | John Bestler | Amanda Coulombe | New Launch | 24 | RD | 2016-10-01 | 2016-10-01 | 2016-10-01 | Y |  | Added on 8/8 per AC email request on 8/2 | 104
620 | Potbelly's | Potbelly's Food Safety Program | John Bestler | Amanda Coulombe | Relaunch | 0 | RD | 2016-10-01 | 2016-10-01 | 2016-10-01 | Y |  | No changes for LZ during mtg on 8/22 | 33
621 | Stripes | Stripes Food Safety Program | Michelle Hudson | Steve Steinberg | Relaunch | 24 | RD | 2016-10-01 | 2016-10-01 | 2016-10-01 | Y |  |  | 26
622 | Stripes | Sunoco Food Safety Program (Part of Stripes) | Michelle Hudson | Steve Steinberg | New Launch | 0 | - | 2016-10-01 | 2016-10-01 | 2016-10-01 | Y |  | Added during AT meeting (6/27); removed per MH on 8/29, will be launching 1/1/17 | 26
623 | The Procaccianti Group | TPG Food Safety Evaluations | Brian Nolan | Steve Steinberg | New Launch | 24 | JF | 2016-10-01 | 2016-10-01 | 2016-10-01 | Y |  |  | 109
624 | Starbucks | Starbucks Company Food Safety Program | Justin Prestinario | Tim Cassidy | Relaunch | 24 | BH | 2016-10-03 | 2016-10-03 | 2016-10-03 | Y |  |  | 1
625 | Starbucks | Starbucks Company Food Safety Program - French | Justin Prestinario | Tim Cassidy | Relaunch | 24 | BH | 2016-10-03 | 2016-10-03 | 2016-10-03 | Y |  |  | 1
626 | Chipotle | Chipotle Food Safety Program | Keith Woith | Amanda Coulombe | Relaunch | 16 | AD | 2016-10-06 | 2016-10-06 | 2016-10-06 | Y |  | Emergency PL change needed; AD to turnaround quickly (10/3) | 6
627 | Sodexo | Sodexo - Food Safety Canada (English Version) | Brian Nolan | Eric Hightower | New Launch | 32 | MG | 2016-10-07 | 2016-09-01 | 2016-10-07 | Y |  | This will be the full re-launch for all FS, HS, and Canada forms (8 forms) | 9
628 | Sodexo | Sodexo - Food Safety Canada (French Version) | Brian Nolan | Eric Hightower | New Launch | 32 | MG | 2016-10-07 | 2016-09-01 | 2016-10-07 | Y |  | This will be the full re-launch for all FS, HS, and Canada forms (8 forms) | 9
629 | Sodexo | Sodexo - Health & Safety Canada (English) | Brian Nolan | Eric Hightower | New Launch | 32 | MG | 2016-10-07 | 2016-09-01 | 2016-10-07 | Y |  | This will be the full re-launch for all FS, HS, and Canada forms (8 forms) | 9
630 | Sodexo | Sodexo - Health & Safety Canada (French) | Brian Nolan | Eric Hightower | New Launch | 32 | MG | 2016-10-07 | 2016-09-01 | 2016-10-07 | Y |  | This will be the full re-launch for all FS, HS, and Canada forms (8 forms) | 9
631 | Sodexo | Sodexo - Food Safety US | Brian Nolan | Eric Hightower | New Launch | 32 | BH | 2016-10-07 | 2016-09-01 | 2016-10-07 | Y |  | This will be the full re-launch for all FS, HS, and Canada forms (8 forms) | 9
632 | Sodexo | Sodexo - Health & Safety Food Service US | Brian Nolan | Eric Hightower | New Launch | 32 | BH | 2016-10-07 | 2016-09-01 | 2016-10-07 | Y |  | This will be the full re-launch for all FS, HS, and Canada forms (8 forms) | 9
633 | Sodexo | Sodexo - Health & Safety FM, Patient Transport, Environmental Services US | Brian Nolan | Eric Hightower | New Launch | 32 | BH | 2016-10-07 | 2016-09-01 | 2016-10-07 | Y |  | This will be the full re-launch for all FS, HS, and Canada forms (8 forms) | 9
634 | Sodexo | Sodexo - Health & Safety FM P&G US | Brian Nolan | Eric Hightower | New Launch | 32 | BH | 2016-10-07 | 2016-09-01 | 2016-10-07 | Y |  | This will be the full re-launch for all FS, HS, and Canada forms (8 forms) | 9
635 | EcoSure | Norovirus Add-On Form | Shawn Nelson | All | New Launch | 24 | BH | 2016-10-07 | 2016-10-03 | 2016-10-07 | Y |  | Form provided on 9/8 | 603
636 | Chick-fil-A | Chick-fil-A Dallas Special Study | Rob Siler | Emily Naufel | New Launch | 24 | AP | 2016-10-10 | 2016-10-10 | 2016-10-10 | Y |  |  | 44
637 | Chuck E. Cheese | Chuck E Cheese Food Safety Pilot Program | Michelle Hudson | Amanda Coulombe | New Launch | 24 | RD | 2016-10-15 | 2016-10-15 | 2016-10-15 | Y |  |  | 219
638 | Chick-fil-A | Chick-fil-A Catering Program | Rob Siler | Emily Naufel | Relaunch | 24 | AP | 2016-10-17 | 2016-08-15 | 2016-10-17 | Y |  | Pushed back to 10/17 per TC to help with Aug/Sep requests (MO 4/29) | 44
639 | Chick-fil-A | Chick-fil-A CPE Program | Rob Siler | Emily Naufel | Relaunch | 24 | AP | 2016-10-17 | 2016-08-15 | 2016-10-17 | Y |  | Pushed back to 10/17 per TC to help with Aug/Sep requests (MO 4/29) | 44
640 | Il Fornaio | Il Fornaio Food Safety Program | Michelle Hudson | Tim Cassidy | Relaunch | 24 | JF | 2016-11-01 | 2016-06-01 | 2016-11-01 | Y |  | VB requested this be added asap for new food code changes (MO 3/3); changes due on 5/1 from milestone email sent on 4/19; after multiple follow ups still no scope as of 5/25; per TC email on 5/25 pushing relaunch back to 11/1 and removing 1/1/17 rollout (MO 5/25) | 100
641 | TGI Friday's | TGIF Food Safety Program | Michelle Hudson | Eric Hightower | Relaunch | 24 | JF | 2016-11-01 | 2016-08-01 | 2016-11-01 | Y |  | New contact who wants to make changes but won't be finalized until end of June (6/13); earliest will now be 10/1, if not 1/1/17 (7/11) | 17
642 | HoneyBaked Ham | Honeybaked Ham Holiday Program - Food Safety Program | Rob Siler | Emily Naufel | Relaunch | 24 | AP | 2016-11-01 | 2016-11-01 | 2016-11-01 | Y |  |  | 37
643 | HoneyBaked Ham | Honeybaked Ham Holiday Program - PopUp Retail | Rob Siler | Emily Naufel | Relaunch | 24 | AP | 2016-11-01 | 2016-11-01 | 2016-11-01 | Y |  |  | 37
644 | Fresh Ideas | Fresh Ideas Food Safety Program | John Bestler | Steve Steinberg | New Launch | 24 | RD | 2016-11-03 | 2016-10-10 | 2016-11-03 | Y |  | Standard customer; requested on 9/6; launched pushed back to 11/1 due to no store/hierarchy/CAM info on 10/5; 11/1 predicated on receiving this info by Fri, 10/14; hierarchy received late and not built/flagged until Friday, 10/28. Emailed AT on Monday, 10/31 stating we'll launch on Thursday, 11/3 | 135
645 | The Kitchen | The Kitchen Food Safety Program | Keith Woith | Amanda Coulombe | New Launch | 24 | JF | 2016-11-11 | 2016-11-11 | 2016-11-11 | Y |  | Requested by SH on 10/12 | 143
646 | CKE | CKE Brand Standards | John Bestler | Amanda Coulombe | New Launch | 80 | MG | 2016-11-21 | 2016-10-01 | 2016-11-21 | Y |  | No info from customer as of 8/22 so no longer targeting 10/1; tentatively scheduling as 11/1 peding Training's capacity | 4
647 | Red Lobster | Red Lobster Food Safety Program | John Bestler | Amanda Coulombe | Relaunch | 24 | RD | 2016-11-25 | 2016-11-25 | 2016-11-25 | Y |  | Added 5/18 (MO) | 23
648 | Four Winds Casino | Four Winds Casino Food Safety Program | John Bestler | Steve Steinberg | Relaunch | 8 | BH | 2016-11-30 | 2016-11-30 | 2016-11-30 | Y |  | Request to turn on CAM, which requires versioning form and adding due dates. Requested on 11/18, BH said he can fit it in next week | 136
649 | John's Incredible Pizza | John's Incredible Pizza Food Safety Program | Keith Woith | Tim Cassidy | Relaunch | 0 | RD | 2016-12-01 | 2016-12-01 | 2016-12-01 | Y |  | Originally requested 1/1/17, pulled up to 12/1/16 per AM email on 5/136 (MO 5/13); no changes per AT since already have the 2015 supplemental updates (10/6) | 125
650 | Popeye's | Popeyes Food Safety Program | Rob Siler | Emily Naufel | Relaunch | 40 | JF | 2016-12-26 | 2017-01-01 | 2017-01-01 | Y | Dec | Maggie requested this be ready on 12/26 instead of 1/1 (9/20) | 12
651 | EcoSure | Norovirus Add-On Form | Shawn Nelson | All | Relaunch | 8 | AD | 2016-12-29 | 2016-12-29 | 2016-12-29 | Y |  | Additional changes requested by Shawn Nelson | 603
652 | Academia Barilla | Academia Barilla Food Safety | John Bestler | Steve Steinberg | Relaunch | 8 | RD | 2017-01-01 | 2017-01-01 | 2017-01-01 | Y |  | 12/13 - AT confirmed RefNum only updates; RD able to fit in for 1/1 | 157
653 | Adak Restaurants | Adak Restaurants Food Safety Program | John Bestler | Eric Hightower | Relaunch | 0 | - | 2017-01-01 | 2017-01-01 | 2017-01-01 | Y |  | Per EH response to Q4 schedule validation: Remove | 219
654 | Aramark | ARAMARK Food Safety Program | Brian Nolan | Amanda Coulombe | Relaunch | 40 | BH | 2017-01-01 | 2017-01-01 | 2017-01-01 | Y | Nov |  | 16
655 | Aramark | ARAMARK SAFE Food Safety Program | Brian Nolan | Amanda Coulombe | Relaunch | 0 | BH | 2017-01-01 | 2017-01-01 | 2017-01-01 | Y | Dec | 12/6 - AT notified us no longer using SAFE form because cuatomer is still not ready, despite changes being provided | 16
656 | Arby's | Arby's Food Safety Program | Rob Siler | Amanda Coulombe | Relaunch | 40 | BH | 2017-01-01 | 2017-01-01 | 2017-01-01 | Y | Oct | Form should be converted to 1:1 box groups to match how scoring is calculated (MO 6/2/16) | 19
657 | Areas USA | Areas USA Food Safety Program | John Bestler | Steve Steinberg | Relaunch | 8 | JF | 2017-01-01 | 2017-01-01 | 2017-01-01 | Y | Nov | Reference number updates only | 93
658 | Avendra Hospitality | Avendra Hospitality Food Safety Program | Brian Nolan | Amanda Coulombe | Relaunch | 8 | RD | 2017-01-01 | 2017-01-01 | 2017-01-01 | Y |  | Requested for 1/1 but not worked due to capacity; AT confirmed RefNum only changes, RD able to fit in before 1/1 | 74
659 | Bloomin' Brands | Bloomin Brands Food Safety Program | Rob Siler | Steve Steinberg | Relaunch | 24 | JF | 2017-01-01 | 2017-01-01 | 2017-01-01 | Y | Dec |  | 13
660 | Briad | Briad Food Safety Program | Keith Woith | Tim Cassidy | Relaunch | 0 | - | 2017-01-01 | 2017-01-01 | 2017-01-01 | Y |  | Per TC's email on 7/14, no relaunch needed for 1/1 | 115
661 | Burger King | Burger King Bun Sampling Program | John Bestler | Steve Steinberg | Relaunch | 8 | RD | 2017-01-01 | 2017-01-01 | 2017-01-01 | Y |  | Added on 11/14 per AF's request; RD said he can take this on; reference num only changes | 20
662 | Burger King | Burger King Playground Inspection Program | John Bestler | Steve Steinberg | Relaunch | 24 | JF | 2017-01-01 | 2017-01-01 | 2017-01-01 | Y | Dec |  | 20
663 | Burgerville | Burgerville Food Safety and Workplace Safety | Keith Woith | Emily Naufel | Relaunch | 0 | JF | 2017-01-01 | 2017-01-01 | 2017-01-01 | Y | Oct | TBD - may not have changes; per Joe Reeder email on 10/6 no changes for 1/1 | 219
664 | Café Zupa's | Café Zupas Food Safety Program | Keith Woith | Eric Hightower | Relaunch | 0 | JF | 2017-01-01 | 2017-01-01 | 2017-01-01 | Y | Oct | CC sent JF email on 9/27 confirming no changes | 81
665 | Caribou / Einstein | Caribou Coffee Assessment (Brand Standards) | Justin Prestinario | Tim Cassidy | Relaunch | 24 | MG | 2017-01-01 | 2017-01-01 | 2017-01-01 | Y | Dec |  | 18
666 | Centerplate | Centerplate Food Safety | Rob Siler | Emily Naufel | Relaunch | 8 | RD | 2017-01-01 | 2017-01-01 | 2017-01-01 | Y |  | Just reference number updates, this one only had 2016 ref num added, can do this anytime; Requested for 1/1 but not worked due to capacity; RD able to fit in RefNum only updates for 1/1 | 156
667 | Checkers | Checkers Food Safety Program | Rob Siler | Steve Steinberg | Relaunch | 24 | AD | 2017-01-01 | 2017-01-01 | 2017-01-01 | Y | Oct |  | 22
668 | Cheddar's | Cheddar's Casual Cafe Food Safety Evaluations | Michelle Hudson | Amanda Coulombe | Relaunch | 0 | AP | 2017-01-01 | 2017-01-01 | 2017-01-01 | Y | Nov | Reference Number updates only (10/19); confirmed reference numbers already in the form so no changes needed (11/10) | 39
669 | Chipotle | Chipotle Food Safety Program | Keith Woith | Amanda Coulombe | Relaunch | 32 | AP | 2017-01-01 | 2017-01-01 | 2017-01-01 | Y | Dec |  | 6
670 | Cinemark | Cinemark Food Safety Program | Michelle Hudson | Tim Cassidy | Relaunch | 24 | MG | 2017-01-01 | 2017-01-01 | 2017-01-01 | Y | Nov |  | 29
671 | Cinemark | Cinemark Brand Standards Program | Michelle Hudson | Tim Cassidy | Relaunch | 0 | MG | 2017-01-01 | 2017-01-01 | 2017-01-01 | Y | Nov | This was a form for a pilot and they have not signed on for a larger program, so not making any changes until they sign on (11/3); Meera also sent email on 11/10 to JC recapping conversation confirming no changes for this program | 29
672 | City BBQ | City BBQ Food Safety Program | John Bestler | Emily Naufel | Relaunch | 8 | RD | 2017-01-01 | 2017-01-01 | 2017-01-01 | Y |  | Placeholder, newer customer may not have changes; Requested for 1/1 but not worked due to capacity; AT confirmed RefNum only changes, RD able to fit in for 1/1 | 95
673 | Cornell University | Cornell Food Safety Program | Brian Nolan | Eric Hightower | Relaunch | 0 | - | 2017-01-01 | 2017-01-01 | 2017-01-01 | Y |  | Per EH response to Q4 schedule validation: Remove | 110
674 | Corner Bakery | Corner Bakery Food Safety Evaluations | Michelle Hudson | Steve Steinberg | Relaunch | 8 | JF | 2017-01-01 | 2017-01-01 | 2017-01-01 | Y | Nov | Reference number updates only | 40
675 | Corner Store | Corner Store Food Safety Program | Michelle Hudson | Steve Steinberg | Relaunch | 8 | JF | 2017-01-01 | 2017-01-01 | 2017-01-01 | Y | Nov | Reference number updates only | 27
676 | Creative Dining Services | Creative Dining Services Food Safety Program | John Bestler | Amanda Coulombe | Relaunch | 24 | AP | 2017-01-01 | 2017-01-01 | 2017-01-01 | Y | Oct | Swapped with Glory Days per KL request on 8/29 | 123
677 | Culinaire Hospitality | Culinaire Food Safety Program | Brian Nolan | Eric Hightower | Relaunch | 0 | - | 2017-01-01 | 2017-01-01 | 2017-01-01 | Y |  | Per EH response to Q4 schedule validation: Remove | 152
678 | Dairy Queen | Dairy Queen Pride Program | Justin Prestinario | Amanda Coulombe | Relaunch | 32 | AD | 2017-01-01 | 2017-01-01 | 2017-01-01 | Y | Nov |  | 8
679 | Delaware North | Delaware North Food Safety Program | Brian Nolan | Steve Steinberg | Relaunch | 8 | RD | 2017-01-01 | 2017-01-01 | 2017-01-01 | Y |  | 12/13 - AT confirmed RefNum updates needed; RD able to fit in for 1/1 | 94
680 | Desert Island Properties | Desert Island Food Safety Program | Keith Woith | Steve Steinberg | Relaunch | 24 | RD | 2017-01-01 | 2017-01-01 | 2017-01-01 | Y | Dec | MO assigned to team due to AT's removing some requests (8/8) | 120
681 | DineEquity | IHOP Egg Reaudit | Keith Woith | Steve Steinberg | New Launch | 24 | BH | 2017-01-01 | 2017-01-01 | 2017-01-01 | Y | Nov | QuestionIDs need to match IHOP form (11/28) | 5
682 | Entertainment Cruises | Entertainment Cruises Food Saftey | John Bestler | Eric Hightower | Relaunch | 24 | AD | 2017-01-01 | 2017-01-01 | 2017-01-01 | Y | Nov |  | 56
683 | Eureka! | Eureka Food Safety Program | Keith Woith | Emily Naufel | Relaunch | 24 | BH | 2017-01-01 | 2017-01-01 | 2017-01-01 | Y | Nov | Requested by DR on 11/4 due to Piada now not having changes; swapped with Piada | 111
684 | Fairmont Hotels | Fairmont Food Safety Program | Justin Prestinario | Eric Hightower | Relaunch | 24 | MG | 2017-01-01 | 2017-01-01 | 2017-01-01 | Y | Oct |  | 47
685 | Fairmont Hotels | Fairmont Guest Experience Program | Justin Prestinario | Eric Hightower | Relaunch | 24 | MG | 2017-01-01 | 2017-01-01 | 2017-01-01 | Y | Oct |  | 47
686 | Famous Dave's | Famous Dave's Food Safety Program | Justin Prestinario | Eric Hightower | Relaunch | 24 | AD | 2017-01-01 | 2017-01-01 | 2017-01-01 | Y | Nov |  | 43
687 | Fogo De Chao | Fogo de Chao Food Safety | Michelle Hudson | Eric Hightower | Relaunch | 24 | JF | 2017-01-01 | 2017-01-01 | 2017-01-01 | Y | Nov |  | 55
688 | Four Winds Casino | Four Winds Casino Food Safety Program | John Bestler | Steve Steinberg | Relaunch | 8 | RD | 2017-01-01 | 2017-01-01 | 2017-01-01 | Y |  | Requested for 1/1 but not worked due to capacity; AT confirmed RefNum only changes, RD able to fit in before 1/1 | 136
689 | Fox Restaurant Concepts | Fox Restaurant QSR Evaluation | Keith Woith | Tim Cassidy | Relaunch | 24 | JF | 2017-01-01 | 2017-01-01 | 2017-01-01 | Y | Oct | No changes per AM email on 10/10, fwd from JF on 10/10 | 68
690 | Fox Restaurant Concepts | Fox Restaurant Workplace Safety Program | Keith Woith | Tim Cassidy | Relaunch | 0 | - | 2017-01-01 | 2017-01-01 | 2017-01-01 | Y |  | Per TC's email on 7/14, no relaunch needed for 1/1 | 68
691 | Friendly's | Friendly's Food Safety Program | Brian Nolan | Emily Naufel | Relaunch | 40 | RD | 2017-01-01 | 2017-01-01 | 2017-01-01 | Y | Dec |  | 41
692 | Garbanzo | Garbanzo Food Safety Program | Keith Woith | Tim Cassidy | Relaunch | 0 | - | 2017-01-01 | 2017-01-01 | 2017-01-01 | Y |  | Per TC's email on 7/14, no relaunch needed for 1/1 | 205
693 | General Mills | General Mills Quarterly Retrieval | Division | Eric Hightower | Relaunch | 0 | - | 2017-01-01 | 2017-01-01 | 2017-01-01 | Y |  | Per EH response to Q4 schedule validation: Remove | 142
694 | Genji Inc. | Genji Food Safety Program | Brian Nolan | Amanda Coulombe | Relaunch | 8 | RD | 2017-01-01 | 2017-01-01 | 2017-01-01 | Y |  | Requested for 1/1 but not worked due to capacity; AT confirmed RefNum only changes, RD able to fit in before 1/1 | 186
695 | Glory Days | Glory Days Food Safety | Brian Nolan | Amanda Coulombe | Relaunch | 0 | - | 2017-01-01 | 2017-01-01 | 2017-01-01 | Y |  | Swapped with Creative Dining per KL request on 8/29; Requested for 1/1 but not worked due to capacity; 1/9 - no changes and 2017 ref nums already present | 99
696 | Golden Corral | Golden Corral Food Safety | Brian Nolan | Emily Naufel | Relaunch | 8 | MG | 2017-01-01 | 2017-01-01 | 2017-01-01 | Y | Oct | No changes per AT on 10/13; 12/1 - MG said reference numbers are changing per AT | 21
697 | Granite City | Granite City Food Safety Assessments | Justin Prestinario | Tim Cassidy | Relaunch | 24 | RD | 2017-01-01 | 2017-01-01 | 2017-01-01 | Y | Nov |  | 50
698 | Greenville School System | Greenville Food Safety Program | Rob Siler | Amanda Coulombe | Relaunch | 0 | RD | 2017-01-01 | 2017-01-01 | 2017-01-01 | Y |  | Per AC repsonse to Q4 schedule validation: Remove - no 1/1 rollout needed | 79
699 | Guckenheimer | Guckenheimer Food Safety & Workplace Safety Program | Keith Woith | Emily Naufel | Relaunch | 0 | BH | 2017-01-01 | 2017-01-01 | 2017-01-01 | Y | Nov | KP emailed BH on 9/23 stating no updates | 42
700 | Hard Rock Café | Hard Rock Café Food Safety Program | John Bestler | Amanda Coulombe | Relaunch | 24 | RD | 2017-01-01 | 2017-01-01 | 2017-01-01 | Y | Oct |  | 36
701 | Hilton | Hilton Food Safety Program | Brian Nolan | Eric Hightower | Relaunch | 24 | MG | 2017-01-01 | 2017-01-01 | 2017-01-01 | Y | Nov |  | 25
702 | Hooters of America | Hooters Food Safety Program | Rob Siler | Emily Naufel | Relaunch | 24 | AP | 2017-01-01 | 2017-01-01 | 2017-01-01 | Y | Dec | Only refNum changes per CC (10/31); CC emailed Hooters wants some changes on 11/2, added back to schedule | 30
703 | Ignite Restaurants | Ignite Food Safety Evaluation Program | Michelle Hudson | Amanda Coulombe | Relaunch | 16 | RD | 2017-01-01 | 2017-01-01 | 2017-01-01 | Y | Nov |  | 54
704 | iPic Theaters | iPic Food Safety Program | Rob Siler | Steve Steinberg | Relaunch | 24 | BH | 2017-01-01 | 2017-01-01 | 2017-01-01 | Y | Oct |  | 102
705 | Jackson's | Jacksons Food Safety Program | Keith Woith | Amanda Coulombe | Relaunch | 16 | RD | 2017-01-01 | 2017-01-01 | 2017-01-01 | Y | Nov | Reference Number updates only; completed and signed off on but still waiting on confirmation from customer on adding 2 photos (will use auditor notifications) so can close (10/31) | 71
706 | Jamba Juice | Jamba Juice International Food Safety Program - Steton Form | Keith Woith | Tim Cassidy | New Launch | 0 | AD | 2017-01-01 | 2017-01-01 | 2017-01-01 | Y | Dec | Removed per TC's file for 2017 schedule review | 28
707 | Jamba Juice | Jamba Juice International Food Safety Program - iForm | Keith Woith | Tim Cassidy | New Launch | 0 | AD | 2017-01-01 | 2017-01-01 | 2017-01-01 | Y | Dec | Removed per TC's file for 2017 schedule review | 28
708 | Kendall Senior Living | Kendal Senior Living Workplace Safety Program | Brian Nolan | Amanda Coulombe | Relaunch | 0 | BH | 2017-01-01 | 2017-01-01 | 2017-01-01 | Y | Oct | AT confirmed no changes (10/10) | 140
709 | Kendall Senior Living | Kendal Senior Living Food Safety Program | Brian Nolan | Amanda Coulombe | Relaunch | 0 | BH | 2017-01-01 | 2017-01-01 | 2017-01-01 | Y | Oct | AT confirmed no changes (10/10) | 140
710 | Kona Grill | Kona Grill Food Safety Program | Keith Woith | Tim Cassidy | Relaunch | 0 | RD | 2017-01-01 | 2017-01-01 | 2017-01-01 | Y | Oct | Per RD Lync message, AM confirmed no changes for 1/1 relaunch | 77
711 | Landry's | Landry's Food Safety Program | Keith Woith | Tim Cassidy | Relaunch | 0 | - | 2017-01-01 | 2017-01-01 | 2017-01-01 | Y |  | Requested for 1/1 but not worked due to capacity | 107
712 | Lazy Dog Café | Lazy Dog Cafe Food Safety Program | Division | Steve Steinberg | Relaunch | 24 | RD | 2017-01-01 | 2017-01-01 | 2017-01-01 | Y | Oct |  | 83
713 | Linchris Hotels | Linchris Hotel Corporate Food Safety Program | Brian Nolan | Eric Hightower | Relaunch | 0 | - | 2017-01-01 | 2017-01-01 | 2017-01-01 | Y |  | Per EH response to Q4 schedule validation: Remove | 138
714 | LTP Management Group | LTP Food Safety Program | Rob Siler | Eric Hightower | Relaunch | 0 | - | 2017-01-01 | 2017-01-01 | 2017-01-01 | Y |  | Per EH response to Q4 schedule validation: Remove | 176
715 | Macaroni Grill | MacGrill Food Safety Program | Michelle Hudson | Amanda Coulombe | Relaunch | 8 | RD | 2017-01-01 | 2017-01-01 | 2017-01-01 | Y | Nov | Just reference number updates; will be sent to RD today (11/28) | 62
716 | Mambo | Mambo Food Safety Program | Michelle Hudson | Amanda Coulombe | Relaunch | 0 | - | 2017-01-01 | 2017-01-01 | 2017-01-01 | Y |  | Per AC repsonse to Q4 schedule validation: remove program cancelled | 604
717 | Marcus Hotels | Marcus Hotels Food Safety Program | John Bestler | Tim Cassidy | Relaunch | 0 | - | 2017-01-01 | 2017-01-01 | 2017-01-01 | Y |  | Requested for 1/1 but not worked due to capacity | 131
718 | Margaritaville | Margaritaville Food Safety Program | Rob Siler | Amanda Coulombe | Relaunch | 8 | JF | 2017-01-01 | 2017-01-01 | 2017-01-01 | Y |  | Removed per AC email on 8/17 stating no changes; Requested for 1/1 but not worked due to capacity; AT pinged JF on 12/14 asking for RefNum only updates and JF said he can fit this in | 103
719 | Max Restaurant Group | Max Restaurant Group 2008 Food Safety Evaluation | Brian Nolan | Amanda Coulombe | Relaunch | 0 | RD | 2017-01-01 | 2017-01-01 | 2017-01-01 | Y |  | Requested for 1/1 but not worked due to capacity; 12/8 - pinged AT's for Ref Num only updates and deteremined already present through 2018 | 113
720 | McDonald's | McDonalds PlayPlace Program | Justin Prestinario | Eric Hightower | Relaunch | 40 | BH | 2017-01-01 | 2017-01-01 | 2017-01-01 | Y | Dec |  | 3
721 | My Fit Foods | My Fit Foods Food Safety Program | Michelle Hudson | Steve Steinberg | Relaunch | 24 | BH | 2017-01-01 | 2017-01-01 | 2017-01-01 | Y | Nov | Customer sent over more feedback/changes; Paul reviewing and should be finalized soon (11/28) | 213
722 | Ocean Properties | Ocean Properties Food Safety Program | John Bestler | Steve Steinberg | Relaunch | 8 | RD | 2017-01-01 | 2017-01-01 | 2017-01-01 | Y |  | 12/13 - AT confirmed RefNum updates needed; RD able to fit in for 1/1 | 86
723 | Ohio State University | Ohio State Food Safety Program | John Bestler | Eric Hightower | Relaunch | 0 | - | 2017-01-01 | 2017-01-01 | 2017-01-01 | Y |  | Per EH response to Q4 schedule validation: Remove | 162
724 | Old Spaghetti Factory | Old Spaghetti Factory Food Safety Program | Keith Woith | Tim Cassidy | Relaunch | 0 | - | 2017-01-01 | 2017-01-01 | 2017-01-01 | Y |  | Per TC's email on 7/14, no relaunch needed for 1/1; 1/10 - TC email states customer discontinued program | 219
725 | Omni Hotels | Omni Hotels Food Safety Program | Michelle Hudson | Tim Cassidy | Relaunch | 0 | RD | 2017-01-01 | 2017-01-01 | 2017-01-01 | Y | Oct | AT confirmed no changes (9/29) | 57
726 | On the Border | On the Border Food Safety Program | Michelle Hudson | Steve Steinberg | Relaunch | 24 | RD | 2017-01-01 | 2017-01-01 | 2017-01-01 | Y | Nov | Was more feedback, Paul finalized and changes should be sent today (11/28) | 46
727 | Panera Bread | Panera Bread Food Safety Program | John Bestler | Tim Cassidy | Relaunch | 8 | JF | 2017-01-01 | 2017-01-01 | 2017-01-01 | Y | Dec |  | 10
728 | Pantry (Auntie M's) | Pantry Audits Food Safety Program | Brian Nolan | Tim Cassidy | Relaunch | 24 | JF | 2017-01-01 | 2017-01-01 | 2017-01-01 | Y | Oct |  | 78
729 | Peet's Coffee & Tea | Peet's Coffee & Tea Food Safety Evaluations | Keith Woith | Amanda Coulombe | Relaunch | 8 | RD | 2017-01-01 | 2017-01-01 | 2017-01-01 | Y | Dec | No customer changes; maybe reference number only??? | 51
730 | Piada Group | Piada Group Food Safety Program | John Bestler | Emily Naufel | Relaunch | 0 | BH | 2017-01-01 | 2017-01-01 | 2017-01-01 | Y | Nov | Requested by AT on 10/11; added due to other 1/1 cancellations; per AT no changes now (11/4) | 96
731 | Pizza Ranch | Pizza Ranch Food Safety Program | Justin Prestinario | Eric Hightower | Relaunch | 8 | RD | 2017-01-01 | 2017-01-01 | 2017-01-01 | Y | Nov | Only RefNum changes per CC (10/19); CC requested additional small changes on 11/21 | 58
732 | Potbelly's | Potbelly's Food Safety Program | John Bestler | Amanda Coulombe | Relaunch | 24 | BH | 2017-01-01 | 2017-01-01 | 2017-01-01 | Y | Oct |  | 33
733 | Pret A Manger | Pret A Manger Food Safety Program | Brian Nolan | Steve Steinberg | Relaunch | 24 | RD | 2017-01-01 | 2017-01-01 | 2017-01-01 | Y | Dec |  | 64
734 | Quorum | Quorum Food Safety Program | Keith Woith | Eric Hightower | Relaunch | 0 | - | 2017-01-01 | 2017-01-01 | 2017-01-01 | Y |  | Per EH response to Q4 schedule validation: Remove | 187
735 | RaceTrac | RaceTrac Food Safety Evaluations | Brian Nolan | Emily Naufel | Relaunch | 24 | AP | 2017-01-01 | 2017-01-01 | 2017-01-01 | Y | Dec |  | 34
736 | Sauce | Sauce Pizza and Wine Food Safety Program | Keith Woith | Tim Cassidy | Relaunch | 0 | JF | 2017-01-01 | 2017-01-01 | 2017-01-01 | Y | Nov | MO assigned to team due to AT's removing some requests (8/8); no changes per AM (10/27) | 130
737 | Select Restaurants | Select Restaurants Food Safety Program | John Bestler | Eric Hightower | Relaunch | 0 | - | 2017-01-01 | 2017-01-01 | 2017-01-01 | Y |  | Per EH response to Q4 schedule validation: Remove | 141
738 | Shopper Events LLC | Shopper Events Food Safety Program | Keith Woith | Steve Steinberg | Relaunch | 24 | AP | 2017-01-01 | 2017-01-01 | 2017-01-01 | Y | Oct | MH still working with customer on what questions trigger high/med/low risk questions; targeting getting this over by EOW (11/28) | 45
739 | Silver Cloud | Silver Cloud Food Safety Program | Keith Woith | Eric Hightower | Relaunch | 0 | - | 2017-01-01 | 2017-01-01 | 2017-01-01 | Y |  | Per EH response to Q4 schedule validation: Remove | 178
740 | SilverBirch Hotels | Silver Birch Food Safety Program | Justin Prestinario | Eric Hightower | Relaunch | 0 | - | 2017-01-01 | 2017-01-01 | 2017-01-01 | Y |  | Per EH response to Q4 schedule validation: Remove | 167
741 | Snooze | Snooze Food Safety Program | Keith Woith | Amanda Coulombe | Relaunch | 40 | AD | 2017-01-01 | 2017-01-01 | 2017-01-01 | Y | Nov | Per AC repsonse to Q4 schedule validation: snooze is a maybe, swap with white lodging, WL will not need to be relaunched | 112
742 | Sodexo | Sodexo Food Safety & HS Program | Brian Nolan | Eric Hightower | Relaunch | 0 | AD | 2017-01-01 | 2017-01-01 | 2017-01-01 | Y | Nov | Removed per AT email on 10/31 | 9
743 | Stanford University | Stanford Food Safety Program | Keith Woith | Eric Hightower | Relaunch | 0 | - | 2017-01-01 | 2017-01-01 | 2017-01-01 | Y |  | Per EH response to Q4 schedule validation: Remove | 118
744 | Stanford University | Stanford Workplace Safety Program | Keith Woith | Eric Hightower | Relaunch | 0 | - | 2017-01-01 | 2017-01-01 | 2017-01-01 | Y |  | Per EH response to Q4 schedule validation: Remove | 118
745 | Starbucks | Starbucks LIC Food Safety Program | Justin Prestinario | Tim Cassidy | Relaunch | 24 | AP | 2017-01-01 | 2017-01-01 | 2017-01-01 | Y | Dec |  | 1
746 | Steak 'n Shake | Steak 'n Shake Food Safety Program | John Bestler | Tim Cassidy | Relaunch | 24 | RD | 2017-01-01 | 2017-01-01 | 2017-01-01 | Y |  | 12/8 - added to schedule for KM email; scoring change request to move from 0/golf > 100 minus | 24
747 | Stripes | Stripes Food Safety Program | Michelle Hudson | Steve Steinberg | Relaunch | 24 | AP | 2017-01-01 | 2017-01-01 | 2017-01-01 | Y | Nov |  | 26
748 | Tavistock | Tavistock Food Safety Program | Keith Woith | Steve Steinberg | Relaunch | 24 | AP | 2017-01-01 | 2017-01-01 | 2017-01-01 | Y | Oct |  | 106
749 | TGI Friday's | TGIF Food Safety Program | Michelle Hudson | Eric Hightower | Relaunch | 40 | JF | 2017-01-01 | 2017-01-01 | 2017-01-01 | Y | Dec |  | 17
750 | The Resort at Pelican Hill | The Resort at Pelican Hill Food Safety Program | Keith Woith | Eric Hightower | Relaunch | 0 | - | 2017-01-01 | 2017-01-01 | 2017-01-01 | Y |  | Per EH response to Q4 schedule validation: Remove | 150
751 | Travel Centers of America | Travel Centers of America Food Safety Evaluation | John Bestler | Eric Hightower | Relaunch | 24 | JF | 2017-01-01 | 2017-01-01 | 2017-01-01 | Y | Oct |  | 65
752 | Tropical Smoothie Café | Tropical Smoothie Café Food Safety Program | Brian Nolan | Tim Cassidy | Relaunch | 8 | AP | 2017-01-01 | 2017-01-01 | 2017-01-01 | Y | Oct | No changes per AT on 10/6; meeting with customer in November '16 to review entire form, change may come out of meeting but will determine a new launch date for those; 12/3 - reference number changes needed, AP to convert question type to text with default value; 12/9 - AT now requesting form and scoring changes but no info received as of 12/14 | 31
753 | Unidine | Unidine Food Safety Program | Brian Nolan | Steve Steinberg | Relaunch | 8 | RD | 2017-01-01 | 2017-01-01 | 2017-01-01 | Y |  | Requested for 1/1 but not worked due to capacity; AT confirmed RefNum only changes, RD able to fit in before 1/1 | 171
754 | Verve Senior Living | Verve Senior Living Food Safety Program | Justin Prestinario | Steve Steinberg | Relaunch | 24 | RD | 2017-01-01 | 2017-01-01 | 2017-01-01 | Y | Dec |  | 92
755 | Veteran's Canteen Services | VCS Food Safety & Barbershop Program | Rob Siler | Tim Cassidy | Relaunch | 24 | AP | 2017-01-01 | 2017-01-01 | 2017-01-01 | Y | Nov |  | 70
756 | Weber Grill | Weber Grill Food Safety | John Bestler | Tim Cassidy | Relaunch | 0 | - | 2017-01-01 | 2017-01-01 | 2017-01-01 | Y |  | Per TC's email on 7/14, no relaunch needed for 1/1 | 117
757 | White Lodging | White Lodging Food Safety Program | John Bestler | Amanda Coulombe | Relaunch | 0 | - | 2017-01-01 | 2017-01-01 | 2017-01-01 | Y |  | Per AC repsonse to Q4 schedule validation: snooze is a maybe, swap with white lodging, WL will not need to be relaunched | 108
758 | Wyndham Hotels | Wyndham Food Safety Program | Brian Nolan | Tim Cassidy | Relaunch | 24 | AP | 2017-01-01 | 2017-01-01 | 2017-01-01 | Y | Nov |  | 80
759 | YUM! Brands | Pizza Hut - Co/FZ Program | Michelle Hudson | Emily Naufel | Relaunch | 80 | AD | 2017-01-01 | 2017-01-01 | 2017-01-01 | Y | Oct |  | 2
760 | YUM! Brands | Pizza Hut - Co/Fr Operator App | Michelle Hudson | Emily Naufel | Relaunch | 24 | AD | 2017-01-01 | 2017-01-01 | 2017-01-01 | Y | Oct |  | 2
761 | YUM! Brands | Pizza Hut - M Operator App | Michelle Hudson | Emily Naufel | Relaunch | 24 | AD | 2017-01-01 | 2017-01-01 | 2017-01-01 | Y | Oct |  | 2
762 | YUM! Brands | Pizza Hut - LIC Program | Michelle Hudson | Emily Naufel | Relaunch | 40 | AD | 2017-01-01 | 2017-01-01 | 2017-01-01 | Y | Oct |  | 2
763 | YUM! Brands | Pizza Hut - Maintenance Program | Michelle Hudson | Emily Naufel | Relaunch | 40 | AD | 2017-01-01 | 2017-01-01 | 2017-01-01 | Y | Oct |  | 2
764 | YUM! Brands | Pizza Hut - Target Program | Michelle Hudson | Emily Naufel | Relaunch | 24 | AD | 2017-01-01 | 2017-01-01 | 2017-01-01 | Y | Oct |  | 2
765 | Z Foods | Z Foods Food Safety Program | Brian Nolan | Amanda Coulombe | Relaunch | 0 | RD | 2017-01-01 | 2017-01-01 | 2017-01-01 | Y |  | Requested for 1/1 but not worked due to capacity; 12/8 - pinged AT's for Ref Num only updates and deteremined already present through 2018 | 602
766 | Seaport Boston | Seaport Boston Food Safety Program | Brian Nolan | Steve Steinberg | Relaunch | 8 | RD | 2017-01-01 | 2017-01-20 | 2017-01-20 | Y |  | Requested for 1/1 but not worked due to capacity; AT confirmed RefNum only changes, RD able to fit in before 1/1 | 160
767 | Donovan's Steak & Chop House | Donovan's Food Safety Program | Keith Woith | Steve Steinberg | Relaunch | 8 | RD | 2017-01-01 | 2017-02-01 | 2017-02-01 | Y |  | AT confirmed RefNum only updates; RD able to fit in for 1/1 | 161
768 | Willow Valley Resort | Willow Valley Food Safety Program | Brian Nolan | Steve Steinberg | Relaunch | 8 | RD | 2017-01-01 | 2017-02-01 | 2017-02-01 | Y |  | 12/13 - AT confirmed RefNum only updates; RD able to fit in for 1/1 | 146
769 | Aramark | ARAMARK SAFE Food Safety Program | Brian Nolan | Amanda Coulombe | Relaunch | 40 | JF | 2017-01-04 | 2017-01-09 | 2017-01-09 | Y |  | 12/16 - urgent request to update form to work with their data feed consumption process | 16
770 | Taco Mac | Taco Mac Food Safety Program | Rob Siler | Emily Naufel | Relaunch | 24 | JF | 2017-01-09 | 2017-01-01 | 2017-01-09 | Y |  | Requested for 1/1 but not worked due to capacity; 11/30 - customer requested form be changed from Cr/Ma/Mi > Cr/Mi and point values change to 3/1 respectively. Assigned to Joel. | 85
771 | Tommy Bahama | Tommy Bahama Food Safety Program | Rob Siler | Tim Cassidy | Relaunch | 8 | MG | 2017-01-09 | 2017-01-01 | 2017-01-09 | Y | Oct | MO assigned to team due to AT's removing some requests (8/8); contact non-responsive so removing from schedule for 1/1 (10/6); determined there was no update button so updating form but pushing back to 1/9, AT approved | 134
772 | Entertainment Cruises | Entertainment Cruises Food Saftey | John Bestler | Eric Hightower | Relaunch | 24 | AD | 2017-01-11 | 2017-01-09 | 2017-01-11 | Y |  | 12/19 - Urgent request from EH | 56
773 | DineEquity | Applebee's eCaPS Program | Keith Woith | Steve Steinberg | Relaunch | 24 | MG | 2017-01-12 | 2017-01-12 | 2017-01-12 | Y | Nov |  | 5
774 | DineEquity | IHOP OAR Program | Keith Woith | Steve Steinberg | Relaunch | 40 | MG | 2017-01-12 | 2017-01-12 | 2017-01-12 | Y | Nov |  | 5
775 | Popeye's | Popeyes Franchisee Food Safety Program | Rob Siler | Emily Naufel | New Launch | 16 | JF | 2017-01-13 | 2017-01-06 | 2017-01-13 | Y |  | 1/3 - new Popeye's franchise/client; was not specifically requested to be setup; doing what we can to setup what's needed | 12
776 | Honeybaked Ham | Honeybaked Ham Food Safety Program | Rob Siler | Emily Naufel | Relaunch | 24 | AP | 2017-01-15 | 2017-01-15 | 2017-01-15 | Y | Nov |  | 37
777 | Tropical Smoothie Café | Tropical Smoothie Café Food Safety Program | Brian Nolan | Tim Cassidy | Relaunch | 0 | AP | 2017-01-16 | 2017-01-16 | 2017-01-16 | Y |  | No changes per AT on 10/6; meeting with customer in November '16 to review entire form, change may come out of meeting but will determine a new launch date for those; 12/3 - reference number changes needed, AP to convert question type to text with default value; 12/9 - AT now requesting form and scoring changes but no info received as of 12/14; 1/2 - customer decided against scoring chagnes and AP already completed all other changes, so this can be closed out | 31
778 | Caribou / Einstein | Caribou Co-Branded Program | Justin Prestinario | Tim Cassidy | Relaunch | 24 | MG | 2017-01-23 | 2017-01-01 | 2017-01-23 | Y | Dec | 12/22 - last minute custom scoring change request | 18
779 | Caribou / Einstein | Einstein Bagels Food Safety Program | Justin Prestinario | Tim Cassidy | New Launch | 80 | MG | 2017-01-23 | 2017-01-01 | 2017-01-23 | Y | Dec | Announced on 9/15; still no hierarchy as of 12/21; hierarchy just created and flagged on 12/22; setup/testing to resume in early-January | 18
780 | CKE | CKE Food Safety | John Bestler | Amanda Coulombe | Relaunch | 80 | AD | 2017-01-31 | 2017-01-15 | 2017-01-31 | Y | Dec |  | 4
781 | CKE | CKE Playground Program | John Bestler | Amanda Coulombe | Relaunch | 8 | AD | 2017-01-31 | 2017-01-15 | 2017-01-31 | Y | Dec | No customer changes; maybe reference number only??? | 4
782 | CKE | CKE Workplace Safety | John Bestler | Amanda Coulombe | Relaunch | 40 | JF | 2017-01-31 | 2017-01-15 | 2017-01-31 | Y | Dec |  | 4
783 | CKE | CKE Mexico | John Bestler | Amanda Coulombe | Relaunch | 40 | JF | 2017-01-31 | 2017-01-15 | 2017-01-31 | Y | Dec |  | 4
784 | LaRosa's | LaRosa's Food Safety Program | John Bestler | Steve Steinberg | Relaunch | 0 | JF | 2017-02-01 | 2017-01-01 | 2017-02-01 | Y |  | Requested for 1/1 but not worked due to capacity; per SH email who followed up with SS, there are no changes and no refeference nubmer updates needed (12/21) | 87
785 | Mohonk | Mohonk Resort Brand Standards Program | Brian Nolan | Emily Naufel | Relaunch | 8 | AP | 2017-02-01 | 2017-01-01 | 2017-02-01 | Y |  | Requested for 1/1 but not worked due to capacity | 89
786 | Mohonk | Mohonk Resort Food Safety Program | Brian Nolan | Emily Naufel | Relaunch | 8 | AP | 2017-02-01 | 2017-01-01 | 2017-02-01 | Y |  | Requested for 1/1 but not worked due to capacity | 89
787 | Twin Peaks | Twin Peaks Food Safety Program | Michelle Hudson | Eric Hightower | Relaunch | 24 | AP | 2017-02-01 | 2017-01-01 | 2017-02-01 | Y |  | Looking to change scoring; going from 10/5/1 to 5/3/1 (or something similar) | 52
788 | Stripes | Sunoco Food Safety Program (Part of Stripes) | Michelle Hudson | Steve Steinberg | New Launch | 24 | AP | 2017-02-01 | 2017-01-15 | 2017-02-01 | Y |  | Per SS response to Q4 schedule validation: New program launch - quarterly; swapping out with LaRosa's; not launching 1/1 per AT, pushed back to 4/1 (10/17); per 2017 schedule confirmation launch date moving from 4/1/17 to 1/15/17 | 26
789 | Benihana | Benihana Food Safety Program | Rob Siler | Steve Steinberg | New Launch | 32 | JF | 2017-02-01 | 2017-02-01 | 2017-02-01 | Y |  | 12/20 - SH email request on how we can fit this in | 49
790 | Buffalo Wild Wings | Buffalo Wild Wings - CO & Franchise Food Safety Program | Justin Prestinario | Emily Naufel | Relaunch | 32 | JF | 2017-02-01 | 2017-02-01 | 2017-02-01 | Y |  | Actually launching 2/1 but customer needs materials a month in advance; set target launch a month earlier (8/31/16); 1/3 - due to BH departure, reassigned to JF to wrap up with new target deadline of 1/11 | 15
791 | Cotton Patch Café | Cotton Patch Café Food Safety Program | Michelle Hudson | Emily Naufel | Relaunch | 0 | AD | 2017-02-01 | 2017-02-01 | 2017-02-01 | Y |  | 12/20 - AT confirmed no changes and no reference number updates needed | 97
792 | McDonald's | McDonalds Food Safety/ECS Program | Justin Prestinario | Eric Hightower | Relaunch | 40 | MG | 2017-02-01 | 2017-02-01 | 2017-02-01 | Y |  |  | 3
793 | McDonald's | McDonald's Security Assessment Program | Justin Prestinario | Eric Hightower | New Launch | 24 | MG | 2017-02-01 | 2017-02-01 | 2017-02-01 | Y |  |  | 3
794 | Pinnacle Entertainment Group | Pinnacle Casino Food Safety Program | Keith Woith | Emily Naufel | Relaunch | 24 | JF | 2017-02-01 | 2017-02-01 | 2017-02-01 | Y |  |  | 73
795 | Sunkist | Sunkist Retrieval | Keith Woith | Eric Hightower | Relaunch | 0 | - | 2017-02-01 | 2017-02-01 | 2017-02-01 | Y |  | Per EH response to Q4 schedule validation: Remove | 82
796 | Tilted Kilt | Tilted Kilt Food Safety Evaluations | Keith Woith | Steve Steinberg | Relaunch | 0 | RD | 2017-02-01 | 2017-02-01 | 2017-02-01 | Y |  | 12/6 - SS email stated contract being cancelled at end of 2016 | 196
797 | Bass Pro Shop | Bass Pro 2009 Food Safety Evaluations | John Bestler | Amanda Coulombe | Relaunch | 8 | JF | 2017-02-01 | 2017-02-15 | 2017-02-15 | Y |  | Per AC repsonse to Q4 schedule validation: move to 3/1/2017 launch - give their spot to Kendal FS form; per 2017 confirmation file launch date moved from 3/1/17 to 2/15/17; 12/21 - reference number only updates | 76
798 | DineEquity | Transportation Audit | Keith Woith | Steve Steinberg | Relaunch | 40 | JF | 2017-02-08 | 2017-01-12 | 2017-02-08 | Y |  | Pushed back to 2/1 per SS on 11/2 weekly meeting | 5
799 | Checkers | Checkers Food Safety Program | Rob Siler | Steve Steinberg | Relaunch | 24 | NJ | 2017-02-10 | 2017-01-09 | 2017-02-10 | Y |  | Urgent request from SC (12/16) | 22
800 | Cerca Trova | BBI Thunderbirds Franchise Program | Keith Woith | Steve Steinberg | New Launch | 40 | NJ | 2017-02-10 | 2017-02-01 | 2017-02-10 | Y |  | 11/28 - waiting for AT to provide form content to determine launch date; 12/22 - AF email stating February launch will work | 84
801 | Noodle's | Noodles Food Safety Program | Keith Woith | Steve Steinberg | Relaunch | 40 | MG | 2017-02-15 | 2017-01-01 | 2017-02-15 | Y |  | Requested for 1/1, pushed back to 2/1; 12/21 - per SH email can wait until 2/15 | 32
802 | Noodle's | Noodles Self-Assessment Program | Keith Woith | Steve Steinberg | Relaunch | 40 | MG | 2017-02-15 | 2017-01-01 | 2017-02-15 | Y |  | Requested for 1/1, pushed back to 2/1; 12/21 - per SH email can wait until 2/15 | 32
803 | Chipotle | Chipotle ATP Program | Keith Woith | Amanda Coulombe | New Launch | 40 | AP | 2017-02-15 | 2017-02-15 | 2017-02-15 | Y |  | Added on 12/14 for 2/15 launch; waiting to hear from Tammy if her team is comfortable with this | 6
804 | CKE | CKE Brand Standards | John Bestler | Amanda Coulombe | Relaunch | 80 | AP | 2017-02-15 | 2017-02-15 | 2017-02-15 | Y |  | Anticipating remaing 2/3 of form to launch (10*1) | 4
805 | Corner Store | Corner Store Food Safety Program | Michelle Hudson | Steve Steinberg | Relaunch | 24 | NJ | 2017-02-20 | 2017-02-01 | 2017-02-20 | Y |  | 12/30 - MH email requesting updates for 2/1 | 27
806 | Compass Group | Compass FLIK RizePoint Form | Brian Nolan | Eric Hightower | New Launch | 24 | AK | 2017-02-20 | 2017-02-20 | 2017-02-20 | Y |  | 1/31 - this is a 'data capture' form used for the field to enter data on as these audits will be conducted on a Compass software platform called 'Acuity'; 2/22 - Per JO email, no info from customer so program on hold indefinitely; will determine a new launch date if/when changes are finalized | 11
807 | Boudin Bakery | Boudin Bakery Food Safety Program | Keith Woith | Eric Hightower | New Launch | 40 | MG | 2017-02-27 | 2017-02-27 | 2017-02-27 | Y |  | 1/12 - SH email req late-Feb rollout | 66
808 | 85 ᵒC Café | 85 Degrees Celsius Café Food Safety Program | Keith Woith | Steve Steinberg | Relaunch | 0 | - | 2017-03-01 | 2017-01-01 | 2017-03-01 | Y |  | Requested for 1/1 but not worked due to capacity; 12/21 - RefNum only updates per SH, however 2017 RefNum already present so removed from schedule | 98
809 | Jamba Juice | Jamba Juice Traditional Food Safety Program - iForm | Keith Woith | Tim Cassidy | Relaunch | 24 | AD | 2017-03-01 | 2017-01-01 | 2017-03-01 | Y |  |  | 28
810 | Jamba Juice | Jamba Juice Traditional Food Safety Program - Steton Form | Keith Woith | Tim Cassidy | Relaunch | 24 | AD | 2017-03-01 | 2017-01-01 | 2017-03-01 | Y |  |  | 28
811 | Jamba Juice | Jamba Juice Express Food Safety Program - iForm | Keith Woith | Tim Cassidy | New Launch | 0 | AD | 2017-03-01 | 2017-01-01 | 2017-03-01 | Y |  | 2/1 - not launching until 5/1 per TC email (already on schdule for 5/1) | 28
812 | Jamba Juice | Jamba Juice Express Food Safety Program - Steton Form | Keith Woith | Tim Cassidy | New Launch | 0 | AD | 2017-03-01 | 2017-01-01 | 2017-03-01 | Y |  | 2/1 - not launching until 5/1 per TC email (already on schdule for 5/1) | 28
813 | Pepperidge Farm | Pepperidge Farm Depot Food Safety Inspection | Brian Nolan | Tim Cassidy | Relaunch | 8 | JF | 2017-03-01 | 2017-01-01 | 2017-03-01 | Y |  | Requested for 1/1 but not worked due to capacity; ref num only updates | 133
814 | Trusthouse (Aladdin) | TrustHouse Food Safety Program | Brian Nolan | Eric Hightower | Relaunch | 24 | AD | 2017-03-01 | 2017-01-01 | 2017-03-01 | Y |  | Requested for 1/1 but not worked due to capacity; 1/9 - ref num only changes | 137
815 | Mimi's Café | Mimi's Café Food Safety Program | Michelle Hudson | Tim Cassidy | Relaunch | 24 | AK | 2017-03-01 | 2017-01-09 | 2017-03-01 | Y |  | 12/22 - email request from AM for form updates | 75
816 | Interstate Hotels and Resorts | Interstate Food Safety Program | Brian Nolan | Eric Hightower | Relaunch | 24 | NJ | 2017-03-01 | 2017-02-01 | 2017-03-01 | Y |  | 12/23 - RH needs ref num updates for unexpected training in February | 48
817 | Metz & Associates | Metz Culinary Management | Brian Nolan | Amanda Coulombe | Relaunch | 8 | AK | 2017-03-01 | 2017-02-01 | 2017-03-01 | Y |  |  | 59
818 | Sage Hospitality | Sage Hospitality Food Safety Program | Keith Woith | Emily Naufel | Relaunch | 8 | JF | 2017-03-01 | 2017-02-01 | 2017-03-01 | Y |  |  | 88
819 | Vi | Vi Food Safety Program | John Bestler | Amanda Coulombe | Relaunch | 0 | AK | 2017-03-01 | 2017-02-01 | 2017-03-01 | Y |  | 1/30 - per AC customer wants changes but will not have them ready on time; customer states it's imperative we continue auditing for now; AC requests we readd for 5/1 | 101
820 | Vi | Vi Beverage Program | John Bestler | Amanda Coulombe | Relaunch | 0 | AK | 2017-03-01 | 2017-02-01 | 2017-03-01 | Y |  | 1/30 - per AC customer wants changes but will not have them ready on time; customer states it's imperative we continue auditing for now; AC requests we readd for 5/1 | 101
821 | Academia Barilla | Academia Barilla Food Safety | John Bestler | Steve Steinberg | Relaunch | 0 | - | 2017-03-01 | 2017-03-01 | 2017-03-01 | Y |  | 1/9 - Only ref nums needed but already present | 157
822 | Checkers | Checkers Food Safety Evaluation - Training Form | Rob Siler | Steve Steinberg | Relaunch | 24 | JF | 2017-03-01 | 2017-03-01 | 2017-03-01 | Y |  | 12/21 - Moved back to 3/1 per SH email | 22
823 | Cinemark | Cinemark Food Safety Program | Michelle Hudson | Tim Cassidy | Relaunch | 8 | AD | 2017-03-01 | 2017-03-01 | 2017-03-01 | Y |  | 2/2 - JC identified question numbering issue ("Yes,"); replacing Pepperidge with this instead | 29
824 | Compass Group | Compass HD Program | Brian Nolan | Eric Hightower | Relaunch | 24 | AP | 2017-03-01 | 2017-03-01 | 2017-03-01 | Y |  | 2/21 - EH high priority email stating contact is extremely upset 6 questions were left as informational (despite EN having documentation showing he instructed us to keep them this way). | 11
825 | Hilton | Hilton Beverage Program | Brian Nolan | Eric Hightower | Relaunch | 40 | NJ | 2017-03-01 | 2017-03-01 | 2017-03-01 | Y |  | Per EH response to Q4 schedule validation: This can be moved to 3/1/17 | 25
826 | Hilton | Hilton Additional Program | Brian Nolan | Eric Hightower | Relaunch | 24 | NJ | 2017-03-01 | 2017-03-01 | 2017-03-01 | Y |  | Per EH response to Q4 schedule validation: This can be moved to 3/1/17; removed 'Core Menu' program and replaced with new Add-On form for ice machine questions called Additional (10/31) | 25
827 | Hilton | Hilton Cookie Program | Brian Nolan | Eric Hightower | New Launch | 0 | NJ | 2017-03-01 | 2017-03-01 | 2017-03-01 | Y |  | Per EH response to Q4 schedule validation: This can be moved to 3/1/17; 1/9 - per EH this can be removed, not launching | 25
828 | HoneyBaked Ham | HoneyBaked Ham California Form | Rob Siler | Emily Naufel | New Launch | 0 | AP | 2017-03-01 | 2017-03-01 | 2017-03-01 | Y |  | Per EN on 7/26 will launch on current HBH form; leave this on pipeline as expecation is they'll want their own form; 1/26 - still no info from customer so removed from schedule, once scope received will work with AT on new launch timing | 37
829 | Peter Piper Pizza | Peter Piper Pizza Mexico Food Safety Audits | Keith Woith | Amanda Coulombe | Relaunch | 0 | JF | 2017-03-01 | 2017-03-01 | 2017-03-01 | Y |  | 2/3 - AC confirmed no changes; 2017/18 ref nums already in form | 67
830 | Starwood | Starwood Beverage Program | Brian Nolan | Eric Hightower | Relaunch | 0 | MG | 2017-03-01 | 2017-03-01 | 2017-03-01 | Y |  | 1/13 - RH email stating program cancelled for 2017 | 166
831 | Starwood | Starwood Food Safety Program | Brian Nolan | Eric Hightower | Relaunch | 0 | MG | 2017-03-01 | 2017-03-01 | 2017-03-01 | Y |  | 1/30 - Program cancelled | 166
832 | Starwood | Starwood Storage & Receiving Program | Brian Nolan | Eric Hightower | Relaunch | 0 | MG | 2017-03-01 | 2017-03-01 | 2017-03-01 | Y |  | 1/30 - Program cancelled | 166
833 | The Peninsula Hotel | The Peninsula Food Safety Program | John Bestler | Amanda Coulombe | Relaunch | 8 | AD | 2017-03-01 | 2017-03-01 | 2017-03-01 | Y |  | Added per 2017 schedule confirmation response; needs 2017 ref numbers added, but since only 1 per year will convert to free text w/ default ref num | 168
834 | Au Bon Pain | Au Bon Pain Food Safety Program | Brian Nolan | Eric Hightower | New Launch | 40 | AP | 2017-03-11 | 2017-03-01 | 2017-03-11 | Y |  | 1/26 - Semi-custom standard form; 2/27 - AT provided wrong CAM due date (7 days; 5 is correct), worked with AT to push launch back to 3/11 to accommodate this change (Newk's 4/1 had no changes and was just removed today) | 38
835 | Compass Group | Compass Canada English Form | Brian Nolan | Eric Hightower | Relaunch | 32 | NJ | 2017-03-20 | 2017-01-01 | 2017-03-20 | Y |  | Added per 2017 schedule confirmation response; 1/30 - still waiting on customer to clarify some items; 3/10 - launch pushed back to 4/1 | 11
836 | EcoSure | EcoSure Food Safety Review Form | All | All | Relaunch | 24 | JF | 2017-03-20 | 2017-03-20 | 2017-03-20 | Y |  | 3/9 - change walkthrough form scoring from pts / pts possible to 100 minus 5/3/1 | 603
837 | Brookdale | Brookdale Senior Living Program | John Bestler | Steve Steinberg | Relaunch | 100 | AD | 2017-03-23 | 2017-02-01 | 2017-03-23 | Y |  | Moved from 1/1 to 2/1 per MH (7/25); 2/17 - final changes finally provided; got back to AT on 2/22 with target launch date of 3/23 | 7
838 | Checkers | Checkers Marketing Audit | Rob Siler | Steve Steinberg | Relaunch | 0 | AD | 2017-04-01 | 2017-02-01 | 2017-04-01 | Y |  | Added per 2017 schedule confirmation response; 1/30 - AT requested pushed back to 4/1 due to other higher priorities regarding vetting form | 22
839 | TGI Friday's | TGIF Brand Standards Program | Michelle Hudson | Eric Hightower | New Launch | 80 | MG | 2017-04-01 | 2017-03-01 | 2017-04-01 | Y |  | Added per 2017 schedule confirmation response; Monthly updates will be required due to the nature of a Brand Standards program; 1/30 - per EH moved back from 3/1 to 4/1; 2/22 - onsite visit took place yesterday, TP to follow up with team to see how it went/when changes can be finalized; 2/27 - FD provided AT changed on 2/27 | 17
840 | 4 Rivers Smokehouse | 4 Rivers Smokehouse Food Safety Evaluation | Rob Siler | Amanda Coulombe | Relaunch | 0 | - | 2017-04-01 | 2017-04-01 | 2017-04-01 | Y |  | Added per 2017 schedule confirmation response; 3/20 - removed; will remove all relaunches except 10/1 | 144
841 | Aramark | ARAMARK Food Safety Program | Brian Nolan | Amanda Coulombe | Relaunch | 0 | JF | 2017-04-01 | 2017-04-01 | 2017-04-01 | Y |  | 2/20 - AT meeting; form is being retired | 16
842 | Aramark | ARAMARK SAFE Food Safety Program | Brian Nolan | Amanda Coulombe | Relaunch | 0 | JF | 2017-04-01 | 2017-04-01 | 2017-04-01 | Y |  | 2/20 - AT meeting; no changes for this form for 4/1 | 16
843 | Arby's | Arby's Food Safety Program | Rob Siler | Amanda Coulombe | Relaunch | 24 | JF | 2017-04-01 | 2017-04-01 | 2017-04-01 | Y |  | 1/11 - AC request to add Arby's 4/1 relaunch due to form changes | 19
844 | Benihana | Benihana Food Safety Program | Rob Siler | Steve Steinberg | Relaunch | 24 | JF | 2017-04-01 | 2017-04-01 | 2017-04-01 | Y |  | 3/1 - orignally told no 4/1 changes so pushed back to 7/1 (which is still on schedule), AF requested it be readded due to a missed question; JF able to fit this in | 49
845 | Bento Sushi | Bento Sushi Factory Program | Justin Prestinario | Amanda Coulombe | New Launch | 40 | AD | 2017-04-01 | 2017-04-01 | 2017-04-01 | Y |  | 1/12 - AC provided initial form content, emailed asking when can be launched | 61
846 | Bento Sushi | Bento Sushi Kiosk Program | Justin Prestinario | Amanda Coulombe | New Launch | 0 | AD | 2017-04-01 | 2017-04-01 | 2017-04-01 | Y |  | 1/12 - AC provided initial form content, emailed asking when can be launched; 2/27 - AT email stating will only launch Factory program, Kiosk will not launch until July 17 | 61
847 | Cattleman's | Cattlemens Food Safety Evaluation | Keith Woith | Amanda Coulombe | Relaunch | 0 | - | 2017-04-01 | 2017-04-01 | 2017-04-01 | Y |  | Added per 2017 schedule confirmation response; 2/20 - AT meeting, may be moving to SafeGuard, removed from 4/1 for now but left 7/1 request on schedule | 129
848 | Chipotle | Chipotle Food Safety Program | Keith Woith | Amanda Coulombe | Relaunch | 32 | BH | 2017-04-01 | 2017-04-01 | 2017-04-01 | Y |  |  | 6
849 | ClubCorp | Club Corp Food Safety | Michelle Hudson | Emily Naufel | Relaunch | 8 | NJ | 2017-04-01 | 2017-04-01 | 2017-04-01 | Y |  | 2/16 - per MS ref num updates only | 63
850 | Dairy Queen | Dairy Queen Pride Program | Justin Prestinario | Amanda Coulombe | Relaunch | 40 | AD | 2017-04-01 | 2017-04-01 | 2017-04-01 | Y |  | 12/5 - added per FL's email request | 8
851 | Delaware North | Delaware North Food Safety Program | Brian Nolan | Steve Steinberg | Relaunch | 0 | AK | 2017-04-01 | 2017-04-01 | 2017-04-01 | Y |  | 2/20 - ref num only changes (if not in form already); 2/21 - MH emailed stating they have a new contact who now may want changes, call not scheduled yet to may need to push back launch, will determine once changes are received; 3/6 - still no word from contact; MH following up again today and will circle back by EOW; 3/10 - MN email stating no changes except reference number (which were already added by RD for the 1/1 relaunch), this was not set live however, so JF is setting form live on Monday, 3/13 | 94
852 | Entertainment Cruises | Entertainment Cruises Food Saftey | John Bestler | Eric Hightower | Relaunch | 0 | NJ | 2017-04-01 | 2017-04-01 | 2017-04-01 | Y |  | 2/6 - per NJ email from AT no changes | 56
853 | Eureka! | Eureka Food Safety Program | Keith Woith | Emily Naufel | Relaunch | 0 | - | 2017-04-01 | 2017-04-01 | 2017-04-01 | Y |  | 12/13 - DR email requested they be added for 4/1; 3/2 - no changes per DR, removed from schedule | 111
854 | Famous Dave's | Famous Dave's Food Safety Program | Justin Prestinario | Eric Hightower | Relaunch | 24 | NJ | 2017-04-01 | 2017-04-01 | 2017-04-01 | Y |  |  | 43
855 | Golden Corral | Golden Corral Food Safety | Brian Nolan | Emily Naufel | Relaunch | 24 | BH | 2017-04-01 | 2017-04-01 | 2017-04-01 | Y |  | 12/22 - DR requested they be added to 4/1 | 21
856 | Hard Rock Café | Hard Rock Café Food Safety Program | John Bestler | Amanda Coulombe | Relaunch | 24 | AK | 2017-04-01 | 2017-04-01 | 2017-04-01 | Y |  | Per 2017 schedule validation, launch date changed from 9/1/17 to 4/1/17 | 36
857 | Jackson's | Jacksons Food Safety Program | Keith Woith | Amanda Coulombe | Relaunch | 40 | JF | 2017-04-01 | 2017-04-01 | 2017-04-01 | Y |  |  | 71
858 | Margaritaville | Margaritaville Food Safety Program | Rob Siler | Amanda Coulombe | Relaunch | 0 | - | 2017-04-01 | 2017-04-01 | 2017-04-01 | Y |  | Added per 2017 schedule confirmation response; 2/20 - AT meeting, removed from 4/1 for now but left 7/1 request on schedule | 103
859 | McDonald's | McDonalds PlayPlace Program | Justin Prestinario | Eric Hightower | Relaunch | 0 | MG | 2017-04-01 | 2017-04-01 | 2017-04-01 | Y |  | 2/22 - TP confirmed with EH there are no PlayPlace changes for 4/1 | 3
860 | Mimi's Café | Mimi's Café Food Safety Program | Michelle Hudson | Tim Cassidy | Relaunch | 0 | - | 2017-04-01 | 2017-04-01 | 2017-04-01 | Y |  | Added per 2017 schedule confirmation response; 1/5 - not launching due to relaunching on 3/1 | 75
861 | Newk's | Newks Food Safety Program | Michelle Hudson | Steve Steinberg | Relaunch | 0 | AP | 2017-04-01 | 2017-04-01 | 2017-04-01 | Y |  | 2/20 - customer non-responsive; AT workign with CAM to try and get changes; may remove 4/1 and instead relaunch next cycle (10/1); 2/27 - no changes per AF | 69
862 | Pret A Manger | Pret A Manger Food Safety Program | Brian Nolan | Steve Steinberg | Relaunch | 24 | MG | 2017-04-01 | 2017-04-01 | 2017-04-01 | Y |  | 2/22 - SH/TP weekly meeting, changes received however were not entered in form update template and AT doesn't have bandwidth to enter them soon; 3/13 - form changes going back-and-forth between Training and customer, uncertain of when Training will review and/or form content will be finalized | 64
863 | Real Mex | Real Mex Food Safety Program | Keith Woith | Amanda Coulombe | New Launch | 24 | BH | 2017-04-01 | 2017-04-01 | 2017-04-01 | Y |  | Added per 2017 schedule confirmation response; ask Amanda if this is the launch or if a launch line item still needs to be added?; 2/27 - moving forward with Standard form | 60
864 | Snooze | Snooze Food Safety Program | Keith Woith | Amanda Coulombe | Relaunch | 0 | - | 2017-04-01 | 2017-04-01 | 2017-04-01 | Y |  | 3/20 - removed; will remove all relaunches except 10/1 | 112
865 | Starbucks | Starbucks Facilities Program | Justin Prestinario | Tim Cassidy | Relaunch | 0 | - | 2017-04-01 | 2017-04-01 | 2017-04-01 | Y |  | Removed per TC's file for 2017 schedule review | 1
866 | Starbucks | Starbucks Facilities Program - French | Justin Prestinario | Tim Cassidy | Relaunch | 0 | - | 2017-04-01 | 2017-04-01 | 2017-04-01 | Y |  | Removed per TC's file for 2017 schedule review | 1
867 | Steak 'n Shake | Steak 'n Shake Food Safety Program | John Bestler | Tim Cassidy | Relaunch | 0 | AK | 2017-04-01 | 2017-04-01 | 2017-04-01 | Y |  | Added per 2017 schedule confirmation response; 2/22 - SH/TP weekly meeting, no changes received, no timing of when will be received; 3/2 - weekly meeting, per KM no changes for 4/1 instead will wait to relaunch 7/1 | 24
868 | Stripes | Stripes Food Safety Program | Michelle Hudson | Steve Steinberg | Relaunch | 24 | AD | 2017-04-01 | 2017-04-01 | 2017-04-01 | Y |  | 2/20 - changes received from customer but MH needs to convert to form change template and she's out Tu-Fr of this week and Flory is in onboarding next week… Can Training work with format changes provided in or is someone else availble besides Flory??; 3/1 - MH provided AT form change template | 26
869 | TGI Friday's | TGIF Food Safety Program | Michelle Hudson | Eric Hightower | Relaunch | 24 | AK | 2017-04-01 | 2017-04-01 | 2017-04-01 | Y |  | 2/28 - removed per EH 2017 expected work file; 2/28 - there's actually 1 question text which needs to be updated so leaving it on the schedule | 17
870 | Tropical Smoothie Café | Tropical Smoothie Café Food Safety Program | Brian Nolan | Tim Cassidy | Relaunch | 0 | JF | 2017-04-01 | 2017-04-01 | 2017-04-01 | Y |  | Added per 2017 schedule confirmation response; 2/16 - AT meeting, removed due to no customer changes; will target 7/1 | 31
871 | Veteran's Canteen Services | VCS Food Safety & Barbershop Program | Rob Siler | Tim Cassidy | Relaunch | 24 | MG | 2017-04-01 | 2017-04-01 | 2017-04-01 | Y |  | 1/10 - AM email stating customer requesting point changes to criticality | 70
872 | Luna Grill | Luna Grill Food Safety Program | Keith Woith | Emily Naufel | New Launch | 32 | JF | 2017-04-05 | 2017-04-05 | 2017-04-05 | Y |  | 2/27 - added per SH email notification of new sale; 3/9 - weekly A&A meeting, learned AT is not meeting with the customer to review edits until 3/22, launch will need to be adjusted | 90
873 | Starbucks | Starbucks LIC Food Safety Program - French | Justin Prestinario | Tim Cassidy | Relaunch | 80 | AP | 2017-04-07 | 2017-04-01 | 2017-04-07 | Y |  | Per AT meeting on 12/1, customer not asking for French yet so pushing back to 4/1; 3/28 - per AP, launch needs to be pushed back to 4/7 to allow for additional testing time (Stage down most of week of 3/19 for ELB Testing, Production down 3/28 due to ELB integration issues with duplicate audits and mising images | 1
874 | Starbucks | Starbucks Company Food Safety Program - French | Justin Prestinario | Tim Cassidy | Relaunch | 24 | AP | 2017-04-07 | 2017-04-01 | 2017-04-07 | Y |  | 3/28 - per AP, launch needs to be pushed back to 4/7 to allow for additional testing time (Stage down most of week of 3/19 for ELB Testing, Production down 3/28 due to ELB integration issues with duplicate audits and mising images | 1
875 | Starbucks | Starbucks Company Food Safety Program | Justin Prestinario | Tim Cassidy | Relaunch | 24 | AP | 2017-04-07 | 2017-04-01 | 2017-04-07 | Y |  | 3/28 - per AP, launch needs to be pushed back to 4/7 to allow for additional testing time (Stage down most of week of 3/19 for ELB Testing, Production down 3/28 due to ELB integration issues with duplicate audits and mising images | 1
876 | Compass Group | Compass Canada French Form | Brian Nolan | Eric Hightower | Relaunch | 32 | NJ | 2017-04-08 | 2017-01-01 | 2017-04-08 | Y |  | Added per 2017 schedule confirmation response; 1/30 - still waiting on customer to clarify some items; 2/21 - email thread between JH, NJ agreed on 3/13 as new launch date; 2/27 - in weekly meeting…if no changes provided by EOW, will remove from schedule on Monday 3/6 | 11
877 | Fairmont Hotels | Fairmont Food Safety Program | Justin Prestinario | Eric Hightower | Relaunch | 0 | NJ | 2017-04-08 | 2017-04-01 | 2017-04-08 | Y |  | 2/7 - no changes per RH Lync conversation | 47
878 | Fairmont Hotels | Fairmont Guest Experience Program | Justin Prestinario | Eric Hightower | Relaunch | 24 | NJ | 2017-04-08 | 2017-04-01 | 2017-04-08 | Y |  | 3/10 - launch pushed back a week to 3/8 to accommodate last minute Compass CAN Eng question addition | 47
879 | Starbucks | Starbucks Company Food Safety Program - French | Justin Prestinario | Tim Cassidy | Relaunch | 24 | AP | 2017-04-09 | 2017-04-01 | 2017-04-09 | Y |  | 4/7 - relaunch needed due to missing reference numbers | 1
880 | Starbucks | Starbucks Company Food Safety Program | Justin Prestinario | Tim Cassidy | Relaunch | 24 | AP | 2017-04-09 | 2017-04-01 | 2017-04-09 | Y |  | 4/7 - relaunch needed due to missing reference numbers | 1
881 | YUM! Brands | Pizza Hut - Co/Fr Operator App | Michelle Hudson | Emily Naufel | Relaunch | 24 | BH | 2017-04-10 | 2017-04-10 | 2017-04-10 | Y |  | 4/5 - BH relaunching these programs to take advantage of new ELB feedback platform (and deprecate old ELB tool) | 2
882 | YUM! Brands | Pizza Hut - M Operator App | Michelle Hudson | Emily Naufel | Relaunch | 24 | BH | 2017-04-10 | 2017-04-10 | 2017-04-10 | Y |  | 4/5 - BH relaunching these programs to take advantage of new ELB feedback platform (and deprecate old ELB tool) | 2
883 | Main Event | MainEvent Food Safety Program | Michelle Hudson | Emily Naufel | New Launch | 0 | JF | 2017-04-24 | 2017-04-24 | 2017-04-24 | Y |  | 3/15 - added per weekly SH meeting; semi-standard FS form; 3/17 - both Vi programs pushed from 5/1 to 6/1. Emailed SH, AT and TP if form can be finalized by 4/10, can launch 5/8; 3/23 - launching on "new platform" SafeGuard program…???; 3/29 - stakeholder call with team, determined launching on new RP instance too difficult given timing of April launch, committed to launching on current instance on 4/24; 4/10 - KP informed me as of late Friday, 4/7 program moving back to CORE on new instance | 91
884 | Cerca Trova | Cerca Trova Food Safety Program | Keith Woith | Steve Steinberg | Relaunch | 32 | BH | 2017-04-28 | 2017-04-15 | 2017-04-28 | Y |  | 3/15 - added as placeholder per SS email on 3/14 | 84
885 | Cerca Trova | Cerca Trova Self Assessment Program | Keith Woith | Steve Steinberg | Relaunch | 0 | JF | 2017-04-28 | 2017-04-15 | 2017-04-28 | Y |  | 4/10 - with rebranding, FS program now needs to relaunch at same time as self assessment form; 5/15 - Cerca Trova meeting, per SS and AF only launching FS form on 7/1 and no need to relaunch on 6/1 | 84
886 | Checkers | Checkers Brand Standards Audit | Rob Siler | Steve Steinberg | New Launch | 0 | AD | 2017-05-01 | 2017-02-01 | 2017-05-01 | Y |  | Added per 2017 schedule confirmation response; 1/30 - AT is still working Training on form changes, call with customer to review not scheduled until 2/8 so window tight, may need to push launch back; 2/20 - AT meeting; still working on finalizing changes, ok with pushing back to 5/1; 3/22 - weekly SH/TP meeting, changes provided by customer but Flory is focused on TGIF BS program which launch was pushed back for, so now owns 2 very complex Training rollouts which overlap; 4/11 - Flory has been focused on other priorities, still no changes received | 22
887 | Compass Group | Compass Food Safety Program | Brian Nolan | Eric Hightower | Relaunch | 0 | AP | 2017-05-01 | 2017-03-01 | 2017-05-01 | Y |  | 2/1 - only scoring change per CC email; 2/15 - AT meeting, moved back to 5/1 due to no info from customer | 11
888 | Compass Group | Compass HD Program | Brian Nolan | Eric Hightower | Relaunch | 0 | AP | 2017-05-01 | 2017-03-01 | 2017-05-01 | Y |  | 2/15 - AT meeting, moved back to 5/1 due to no info from customer; 3/29 - weekly A&A meeting, removed from schedule due to no changes from customer | 11
889 | Compass Group | Compass J&W Program | Brian Nolan | Eric Hightower | Relaunch | 0 | AP | 2017-05-01 | 2017-03-01 | 2017-05-01 | Y |  | 2/15 - AT meeting, moved back to 5/1 due to no info from customer; 3/29 - weekly A&A meeting, removed from schedule due to no changes from customer | 11
890 | Compass Group | Compass Workplace Safety Program | Brian Nolan | Eric Hightower | Relaunch | 32 | AP | 2017-05-01 | 2017-03-01 | 2017-05-01 | Y |  | 2/15 - AT meeting, moved back to 5/1 due to no info from customer; 3/29 - weekly A&A meeting, removed from schedule due to no changes from customer; 4/11 - still no form changes received | 11
891 | Hyatt Hotels | Hyatt Food Safety Program | John Bestler | Steve Steinberg | Relaunch | 24 | AP | 2017-05-01 | 2017-03-01 | 2017-05-01 | Y |  | 12/21 - moved from 2/1 > 3/1 per SH email; 1/30 - AT has not engaged with customer yet, Exec Review not until early March so earliest launch will be 4/1 - 4/15; 3/13 - pushed back to 5/1 to allow for review, changes, rollout changes | 53
892 | Glory Days | Glory Days Food Safety | Brian Nolan | Amanda Coulombe | Relaunch | 24 | AD | 2017-05-01 | 2017-04-01 | 2017-05-01 | Y |  | Added per 2017 schedule confirmation response; 3/27 - weekly A&A meeting, no changes per FL; 3/27 - FL email now requesting a few form changes related to alergens, requested a 6/1 launch, informed him we'd like to keep 5/1 for workload balancing purposes and to work with Training to finalize form content ASAP | 99
893 | Bass Pro Shop | Bass Pro 2009 Food Safety Evaluations | John Bestler | Amanda Coulombe | Relaunch | 0 | AK | 2017-05-01 | 2017-05-01 | 2017-05-01 | Y |  | Per 2017 schedule validation file, launch moved from 7/1/17 to 5/1/17; 3/16 - Weekly A&A meeting, no changes per FL | 76
894 | Buffalo Wild Wings | Buffalo Wild Wings - CO & Franchise Food Safety Program | Justin Prestinario | Emily Naufel | Relaunch | 32 | NJ | 2017-05-01 | 2017-05-01 | 2017-05-01 | Y |  | Actually launching 6/1 but customer needs materials a month in advance; set target launch a month earlier (8/31/16) | 15
895 | Caribou / Einstein | Caribou Coffee Assessment (Brand Standards) | Justin Prestinario | Tim Cassidy | Relaunch | 24 | BH | 2017-05-01 | 2017-05-01 | 2017-05-01 | Y |  |  | 18
896 | Caribou / Einstein | Caribou Co-Branded Program | Justin Prestinario | Tim Cassidy | Relaunch | 24 | BH | 2017-05-01 | 2017-05-01 | 2017-05-01 | Y |  |  | 18
897 | Chick-fil-A | Chick-fil-A Dallas Special Study | Rob Siler | Emily Naufel | Relaunch | 24 | AK | 2017-05-01 | 2017-05-01 | 2017-05-01 | Y |  | 2/23 - per AT, only 1 question being added and all questions need to be assigned a priority (so MSBI works); internally driven so we can technically update whenever we're ready; | 44
898 | Compass Group | Compass FLIK RizePoint Form | Brian Nolan | Eric Hightower | New Launch | 24 | AP | 2017-05-01 | 2017-05-01 | 2017-05-01 | Y |  | 3/29 - added per SH email, just requested from Compass | 11
899 | Corner Store | Corner Store Food Safety Program | Michelle Hudson | Steve Steinberg | Relaunch | 24 | NJ | 2017-05-01 | 2017-05-01 | 2017-05-01 | Y |  | Added per 2017 schedule confirmation response; | 27
900 | DineEquity | Water Filtration Program | Keith Woith | Steve Steinberg | New Launch | 0 | BH | 2017-05-01 | 2017-05-01 | 2017-05-01 | Y |  | 4/11 - still no changes received; 4/24 - weekly A&A meeting, removed per EL due to waiting until cycle 3 (9/1) to launch on IHOP only | 5
901 | DineEquity | IHOP Egg Reaudit | Keith Woith | Steve Steinberg | Relaunch | 0 | BH | 2017-05-01 | 2017-05-01 | 2017-05-01 | Y |  | Added per 2017 schedule confirmation response; 3/13 - removed; replaced with Hyatt FS | 5
902 | Hooters of America | Hooters Food Safety Program | Rob Siler | Emily Naufel | Relaunch | 24 | AK | 2017-05-01 | 2017-05-01 | 2017-05-01 | Y |  | 3/8 - AK email fwd from DR that they want to launch 4/17 instead of 5/1; will determine if achievable once changes are received | 30
903 | Jamba Juice | Jamba Juice Express Food Safety Program - iForm | Keith Woith | Tim Cassidy | Relaunch | 32 | AD | 2017-05-01 | 2017-05-01 | 2017-05-01 | Y |  |  | 28
904 | Jamba Juice | Jamba Juice Express Food Safety Program - Steton Form | Keith Woith | Tim Cassidy | Relaunch | 32 | AD | 2017-05-01 | 2017-05-01 | 2017-05-01 | Y |  |  | 28
905 | Jamba Juice | Jamba Juice International Food Safety Program - iForm | Keith Woith | Tim Cassidy | Relaunch | 0 | AD | 2017-05-01 | 2017-05-01 | 2017-05-01 | Y |  | 2/15 - SH/TP weekly meeting…will not launch until after Express already has; can be removed | 28
906 | Jamba Juice | Jamba Juice International Food Safety Program - Steton Form | Keith Woith | Tim Cassidy | Relaunch | 0 | AD | 2017-05-01 | 2017-05-01 | 2017-05-01 | Y |  | 2/15 - SH/TP weekly meeting…will not launch until after Express already has; can be removed | 28
907 | Panera Bread | Panera Bread Food Safety Program | John Bestler | Tim Cassidy | Relaunch | 32 | JF | 2017-05-01 | 2017-05-01 | 2017-05-01 | Y |  | Added per 2017 schedule confirmation response; | 10
908 | TGI Friday's | TGIF Brand Standards Program | Michelle Hudson | Eric Hightower | Relaunch | 0 | NJ | 2017-05-01 | 2017-05-01 | 2017-05-01 | Y |  | Added per 2017 schedule confirmation response; Monthly updates will be required due to the nature of a Brand Standards program; 3/6 - removed per EH in weekly A&A meeting | 17
909 | YUM! Brands | Pizza Hut - Co/FZ Program | Michelle Hudson | Emily Naufel | Relaunch | 80 | MG | 2017-05-01 | 2017-05-01 | 2017-05-01 | Y |  |  | 2
910 | YUM! Brands | Pizza Hut - Co/Fr Operator App | Michelle Hudson | Emily Naufel | Relaunch | 24 | MG | 2017-05-01 | 2017-05-01 | 2017-05-01 | Y |  |  | 2
911 | YUM! Brands | Pizza Hut - M Operator App | Michelle Hudson | Emily Naufel | Relaunch | 24 | MG | 2017-05-01 | 2017-05-01 | 2017-05-01 | Y |  |  | 2
912 | YUM! Brands | Pizza Hut - LIC Program | Michelle Hudson | Emily Naufel | Relaunch | 40 | MG | 2017-05-01 | 2017-05-01 | 2017-05-01 | Y |  |  | 2
913 | YUM! Brands | Pizza Hut - Maintenance Program | Michelle Hudson | Emily Naufel | Relaunch | 40 | MG | 2017-05-01 | 2017-05-01 | 2017-05-01 | Y |  |  | 2
914 | YUM! Brands | Pizza Hut - Target Program | Michelle Hudson | Emily Naufel | Relaunch | 0 | MG | 2017-05-01 | 2017-05-01 | 2017-05-01 | Y |  | 3/14 - No changes per KP email | 2
915 | YUM! Brands | Pizza Hut - Shed Program | Michelle Hudson | Emily Naufel | Relaunch | 24 | MG | 2017-05-01 | 2017-05-01 | 2017-05-01 | Y |  | 4/17 - added per AT request | 2
916 | HoneyBaked Ham | HoneyBaked Ham California Form | Rob Siler | Emily Naufel | New Launch | 24 | JF | 2017-05-08 | 2017-05-08 | 2017-05-08 | Y |  | 4/13 - email from KP requesting this to be added | 37
917 | Medieval Times | Medieval Times Food Safety Program | Michelle Hudson | Emily Naufel | New Launch | 32 | NJ | 2017-05-08 | 2017-05-08 | 2017-05-08 | Y |  | 3/15 - added per weekly SH meeting; semi-standard FS form; 3/17 - both Vi programs pushed from 5/1 to 6/1. Emailed SH, AT and TP if form can be finalized by 4/10, can launch 5/8 | 153
918 | Compass Group | Compass FLIK RizePoint Form | Brian Nolan | Eric Hightower | Relaunch | 24 | AP | 2017-05-15 | 2017-05-01 | 2017-05-15 | Y |  | 5/7 - AT requested another form change, new version required | 11
919 | Compass Group | Compass Food Safety Program | Brian Nolan | Eric Hightower | Relaunch | 32 | BH | 2017-05-15 | 2017-05-15 | 2017-05-15 | Y |  | 4/7 - JO email needing to change Compass FS scoring so relaunch requried; TASK0619678 | 11
920 | Honeybaked Ham | Honeybaked Ham Food Safety Program | Rob Siler | Emily Naufel | Relaunch | 0 | - | 2017-05-15 | 2017-05-15 | 2017-05-15 | Y |  | 2/27 - removed per EN's 2017 expected work updates | 37
921 | Popeye's | Popeyes Food Safety Excellence Program | Rob Siler | Emily Naufel | Relaunch | 40 | AK | 2017-05-15 | 2017-05-15 | 2017-05-15 | Y |  | Per 2017 schedule validation, launch date changed from 4/1/17 to 5/15/17 | 12
922 | Shake Shack | Shake Shack FS Program | Brian Nolan | Emily Naufel | New Launch | 40 | AD | 2017-05-15 | 2017-05-15 | 2017-05-15 | Y |  | 4/24 - added per MS email request; timing is dependent on final form content in Excel being provided (if provided today, 4/24, launch will be on 5/15 and so on…) | 105
923 | CKE | CKE Mexico | John Bestler | Amanda Coulombe | Relaunch | 0 | - | 2017-05-23 | 2017-05-23 | 2017-05-23 | Y |  | Per 2017 confirmation file, removed from schedule for May 2017 | 4
924 | CKE | CKE Playground Program | John Bestler | Amanda Coulombe | Relaunch | 0 | JF | 2017-05-23 | 2017-05-23 | 2017-05-23 | Y |  | Per 2017 confirmation file, launch date moved from 5/15/17 to 5/23/17; 3/27 - weekly A&A meeting, no changes per FL | 4
925 | CKE | CKE Workplace Safety | John Bestler | Amanda Coulombe | Relaunch | 40 | JF | 2017-05-23 | 2017-05-23 | 2017-05-23 | Y |  | Per 2017 confirmation file, launch date moved from 5/15/17 to 5/23/17 | 4
926 | CKE | CKE Food Safety | John Bestler | Amanda Coulombe | Relaunch | 24 | JF | 2017-05-23 | 2017-05-23 | 2017-05-23 | Y |  | Per 2017 confirmation file, launch date moved from 5/15/17 to 5/23/17 | 4
927 | Red Lobster | Red Lobster Food Safety Program | John Bestler | Amanda Coulombe | Relaunch | 24 | AK | 2017-05-29 | 2017-05-29 | 2017-05-29 | Y |  | Per 2017 schedule validation file, launch moved from 5/31/17 to 5/29/17 | 23
928 | Areas USA | Areas USA Brand Standards Program | John Bestler | Steve Steinberg | New Launch | 0 | BH | 2017-06-01 | 2017-03-01 | 2017-06-01 | Y |  | Added per 2017 schedule confirmation response; 2/22 - SH weekly meeting, AT had call on 2/17 to vet form, uncertain of status; 3/6 - in weekly A&A meeting decided to push back to to 6/1 due to lack of customer changes/direction; 5/15 - still no info from customer so removing from schedule | 93
929 | McDonald's | McDonalds Food Safety/ECS Program | Justin Prestinario | Eric Hightower | Relaunch | 60 | MG | 2017-06-01 | 2017-04-01 | 2017-06-01 | Y |  | 3/8 - EH email stating launch needs to be pushed back from 4/15 to 5/15 | 3
930 | Ocean Properties | Ocean Properties Food Safety Program | John Bestler | Steve Steinberg | Relaunch | 24 | NJ | 2017-06-01 | 2017-05-01 | 2017-06-01 | Y |  | Added per 2017 schedule confirmation response; | 86
931 | Vi | Vi Food Safety Program | John Bestler | Amanda Coulombe | Relaunch | 0 | JF | 2017-06-01 | 2017-05-01 | 2017-06-01 | Y |  | 1/30 - per AC customer wants changes but will not have them ready on time; customer states it's imperative we continue auditing for now; AC requests we readd for 5/1; 3/16 - in weekly A&A meeting AT stated changes have not been communicated to customer; 3/17 - spoke to AC, pushing back to 6/1 to make room for Main Event and Medeival Times; 4/17 - A&A weekly meeting, no changes per SC | 101
932 | Vi | Vi Beverage Program | John Bestler | Amanda Coulombe | Relaunch | 0 | JF | 2017-06-01 | 2017-05-01 | 2017-06-01 | Y |  | 1/30 - per AC customer wants changes but will not have them ready on time; customer states it's imperative we continue auditing for now; AC requests we readd for 5/1; 3/16 - in weekly A&A meeting AT stated changes have not been communicated to customer; 3/17 - spoke to AC, pushing back to 6/1 to make room for Main Event and Medeival Times; 4/17 - A&A weekly meeting, no changes per SC | 101
933 | DineEquity | IHOP OAR Program | Keith Woith | Steve Steinberg | Relaunch | 24 | AP | 2017-06-01 | 2017-05-15 | 2017-06-01 | Y |  | 4/17 - SS email requesting 5/15 launch be added | 5
934 | DineEquity | IHOP OAR Program - Spanish | Keith Woith | Steve Steinberg | Relaunch | 60 | AP | 2017-06-01 | 2017-05-15 | 2017-06-01 | Y |  | 4/17 - SS email requesting 5/15 launch be added | 5
935 | DineEquity | Applebee's eCaPS Program | Keith Woith | Steve Steinberg | Relaunch | 24 | AP | 2017-06-01 | 2017-05-15 | 2017-06-01 | Y |  | 4/17 - SS email requesting 5/15 launch be added | 5
936 | DineEquity | Applebee's eCaPS Program - Spanish | Keith Woith | Steve Steinberg | Relaunch | 60 | AP | 2017-06-01 | 2017-05-15 | 2017-06-01 | Y |  | 4/17 - SS email requesting 5/15 launch be added | 5
937 | Atrium Hospitality | Atrium Hospitality Food Safety Program | Justin Prestinario | Tim Cassidy | New Launch | 0 | AP | 2017-06-01 | 2017-06-01 | 2017-06-01 | Y |  | 3/3 - MM email asking when can be fit in; 4/18 - launching on new RizePoint instance | 174
938 | Atrium Hospitality | Atrium Hospitality Guest Experience Program | Justin Prestinario | Tim Cassidy | New Launch | 0 | AP | 2017-06-01 | 2017-06-01 | 2017-06-01 | Y |  | 3/3 - MM email asking when can be fit in; 4/18 - launching on new RizePoint instance | 174
939 | Cerca Trova | Cerca Trova Food Safety Program | Keith Woith | Steve Steinberg | Relaunch | 0 | BH | 2017-06-01 | 2017-06-01 | 2017-06-01 | Y |  | Added per 2017 schedule confirmation response; 5/15 - Cerca Trova meeting, per SS and AF only launching FS form on 7/1 and no need to relaunch on 6/1 | 84
940 | Cerca Trova | Cerca Trova Self Assessment Program | Keith Woith | Steve Steinberg | Relaunch | 0 | BH | 2017-06-01 | 2017-06-01 | 2017-06-01 | Y |  | 3/15 - added as placeholder per SS email on 3/14; 5/15 - Cerca Trova meeting, per SS and AF only launching FS form on 7/1 and no need to relaunch on 6/1 | 84
941 | City BBQ | City BBQ Food Safety Program | John Bestler | Emily Naufel | Relaunch | 24 | AD | 2017-06-01 | 2017-06-01 | 2017-06-01 | Y |  | 5/4 - MS request from customer to add 1 question to form | 95
942 | Darden Franchise Group | Darden Franchise Group Food Safety Program | Rob Siler | Amanda Coulombe | New Launch | 32 | AK | 2017-06-01 | 2017-06-01 | 2017-06-01 | Y |  | 3/21 - added per AC email request | 185
943 | Peet's Coffee & Tea | Peet's Coffee & Tea Food Safety Evaluations | Keith Woith | Amanda Coulombe | Relaunch | 0 | - | 2017-06-01 | 2017-06-01 | 2017-06-01 | Y |  | 3/20 - weekly A&A meeting, removed per AC | 51
944 | Shake Shack | Shake Shack FS Program | Brian Nolan | Emily Naufel | Relaunch | 24 | AD | 2017-06-01 | 2017-06-01 | 2017-06-01 | Y |  | 5/23 - AD email stating Training identified 2 picklists missing the word "No", audits already conducted against form so requires a reversion | 105
945 | Texas Roadhouse | Texas Roadhouse FS & WPS Program | Brian Nolan | Amanda Coulombe | New Launch | 40 | AK | 2017-06-01 | 2017-06-01 | 2017-06-01 | Y |  | 3/21 - added per JC email request; 5/1 - aligned to FL, does not sound like any work has started | 219
946 | TGI Friday's | TGIF Brand Standards Program | Michelle Hudson | Eric Hightower | Relaunch | 24 | BH | 2017-06-01 | 2017-06-01 | 2017-06-01 | Y |  | Added per 2017 schedule confirmation response; Monthly updates will be required due to the nature of a Brand Standards program | 17
947 | Twin Peaks | Twin Peaks Food Safety Program | Michelle Hudson | Eric Hightower | Relaunch | 0 | NJ | 2017-06-01 | 2017-06-01 | 2017-06-01 | Y |  | 4/24 - weekly A&A meeting, no changes per CC (just new feedback rule for reaudits) | 52
948 | 85 ᵒC Café | 85 Degrees Celsius Café Food Safety Program | Keith Woith | Steve Steinberg | Relaunch | 24 | NJ | 2017-06-01 | 2017-07-01 | 2017-07-01 | Y |  |  | 98
949 | Au Bon Pain | Au Bon Pain Food Safety Program | Brian Nolan | Eric Hightower | Relaunch | 0 | AK | 2017-06-01 | 2017-07-01 | 2017-07-01 | Y |  | 2/28 - added per EH 2017 expected work file; 4/24 - weekly A&A meeting, no changes per CC | 38
950 | Boudin Bakery | Boudin Bakery Food Safety Program | Keith Woith | Eric Hightower | Relaunch | 0 | AD | 2017-06-01 | 2017-07-01 | 2017-07-01 | Y |  | 2/28 - added per EH 2017 expected work file; 4/20 - no changes per AD email, forwarded from CC | 66
951 | Corner Bakery | Corner Bakery Food Safety Evaluations | Michelle Hudson | Steve Steinberg | Relaunch | 24 | AD | 2017-06-01 | 2017-07-01 | 2017-07-01 | Y |  | Added per 2017 schedule confirmation response; | 40
952 | Guckenheimer | Guckenheimer Food Safety & Workplace Safety Program | Keith Woith | Emily Naufel | Relaunch | 24 | MG | 2017-06-01 | 2017-07-01 | 2017-07-01 | Y |  |  | 42
953 | Ignite Restaurants | Ignite Food Safety Evaluation Program | Michelle Hudson | Amanda Coulombe | Relaunch | 0 | MG | 2017-06-01 | 2017-07-01 | 2017-07-01 | Y |  | 4/24 - weekly A&A meeting, removed per SC due to non-resposive customer | 54
954 | Margaritaville | Margaritaville Food Safety Program | Rob Siler | Amanda Coulombe | Relaunch | 0 | MG | 2017-06-01 | 2017-07-01 | 2017-07-01 | Y |  | Added per 2017 schedule confirmation response; 4/17 - A&A weekly meeting, no changes per SC | 103
955 | Mimi's Café | Mimi's Café Food Safety Program | Michelle Hudson | Tim Cassidy | Relaunch | 0 | AP | 2017-06-01 | 2017-07-01 | 2017-07-01 | Y |  | Added per 2017 schedule confirmation response; 4/14 - AM email stating customer has no changes, removed from schedule | 75
956 | Olga's Kitchen | Olga's Kitchen Food Safety Program | John Bestler | Amanda Coulombe | Relaunch | 24 | JF | 2017-06-01 | 2017-07-01 | 2017-07-01 | Y |  | Added per 2017 schedule confirmation response; | 104
957 | Omni Hotels | Omni Hotels Food Safety Program | Michelle Hudson | Tim Cassidy | Relaunch | 0 | NJ | 2017-06-01 | 2017-07-01 | 2017-07-01 | Y |  | 2/27 - added per TC's 2017 expected work file; 4/10 - NJ email from JC stating no 6/1 changes due to contact change with customer | 57
958 | Piada Group | Piada Group Food Safety Program | John Bestler | Emily Naufel | Relaunch | 0 | AD | 2017-06-01 | 2017-07-01 | 2017-07-01 | Y |  | Added per 2017 schedule confirmation response; 4/3 - email from DR stating no form changes | 96
959 | Pret A Manger | Pret A Manger Food Safety Program | Brian Nolan | Steve Steinberg | Relaunch | 0 | MG | 2017-06-01 | 2017-07-01 | 2017-07-01 | Y |  | 4/24 - weekly A&A meeting, removed per EL due to just launching on 4/1 | 64
960 | The Procaccianti Group | TPG Food Safety Evaluations | Brian Nolan | Steve Steinberg | Relaunch | 0 | AK | 2017-06-01 | 2017-07-01 | 2017-07-01 | Y |  | Added per 2017 schedule confirmation response; 4/3 - weekly A&A meeting, removed per MN | 109
961 | Trusthouse (Aladdin) | TrustHouse Food Safety Program | Brian Nolan | Eric Hightower | Relaunch | 0 | AK | 2017-06-01 | 2017-07-01 | 2017-07-01 | Y |  | 4/24 - weekly A&A meeting, no changes per CC | 137
962 | Verve Senior Living | Verve Senior Living Food Safety Program | Justin Prestinario | Steve Steinberg | Relaunch | 24 | AD | 2017-06-01 | 2017-07-01 | 2017-07-01 | Y |  |  | 92
963 | Freddy's Frozen Custard | Freddy's Frozen Custard FS Program | John Bestler | Eric Hightower | New Launch | 32 | BH | 2017-06-19 | 2017-06-19 | 2017-06-19 | Y |  | 5/24 - SH email asking for June timing, committed to delivering 6/19 if scope provided quickly | 207
964 | YUM! Brands | Pizza Hut - Co/FZ Program | Michelle Hudson | Emily Naufel | Relaunch | 40 | MG | 2017-06-19 | 2017-06-19 | 2017-06-19 | Y |  |  | 2
965 | YUM! Brands | Pizza Hut - Co/Fr Operator App | Michelle Hudson | Emily Naufel | Relaunch | 24 | MG | 2017-06-19 | 2017-06-19 | 2017-06-19 | Y |  |  | 2
966 | State of North Carolina | NC Department of Health FS Program | Brian Nolan | Tim Cassidy | New Launch | 32 | AK | 2017-06-21 | 2017-06-21 | 2017-06-21 | Y |  | 5/31 - SH email stating we can launch in "June" after we discussed in our weekly SH/TP meeting; 6/22 Signed off | 35
967 | 4 Rivers Smokehouse | 4 Rivers Smokehouse Food Safety Evaluation | Rob Siler | Amanda Coulombe | Relaunch | 0 | - | 2017-07-01 | 2017-07-01 | 2017-07-01 | Y |  | Added per 2017 schedule confirmation response; 3/20 - removed; will remove all relaunches except 10/1 | 144
968 | Aramark | ARAMARK Food Safety Program | Brian Nolan | Amanda Coulombe | Relaunch | 0 | - | 2017-07-01 | 2017-07-01 | 2017-07-01 | y |  | 3/20 - removed; this form will be decommed | 16
969 | Aramark | ARAMARK SAFE Food Safety Program | Brian Nolan | Amanda Coulombe | Relaunch | 0 | NJ | 2017-07-01 | 2017-07-01 | 2017-07-01 | Y |  | 4/24 - weekly A&A meeting, removed per SC because Aramark wants us to focus on field training | 16
970 | Avendra Hospitality | Avendra Hospitality Food Safety Program | Brian Nolan | Amanda Coulombe | Relaunch | 0 | - | 2017-07-01 | 2017-07-01 | 2017-07-01 | Y |  | 3/20 - weekly A&A meeting, removed per AC | 74
971 | Benihana | Benihana Food Safety Program | Rob Siler | Steve Steinberg | Relaunch | 0 | MG | 2017-07-01 | 2017-07-01 | 2017-07-01 | Y |  | 2/13 - per AT pushed back from 4/1 to 7/1 (just launched, no changes yet); 5/31 - MG email (sick) stating AF notified her on 5/24 stating no changes | 49
972 | Bloomin' Brands | Bloomin Brands Food Safety Program | Rob Siler | Steve Steinberg | Relaunch | 0 | AK | 2017-07-01 | 2017-07-01 | 2017-07-01 | Y |  | 6/6 - MH email stating no changes | 13
973 | Brookdale | Brookdale Senior Living Program | John Bestler | Steve Steinberg | Relaunch | 0 | MG | 2017-07-01 | 2017-07-01 | 2017-07-01 | Y |  |  | 7
974 | Burger King | Burger King Playground Inspection Program | John Bestler | Steve Steinberg | Relaunch | 24 | MG | 2017-07-01 | 2017-07-01 | 2017-07-01 | Y |  | 5/15 - Per MH email, swapping Brookdale for BK PG RefNum update | 20
975 | Cattleman's | Cattlemens Food Safety Evaluation | Keith Woith | Amanda Coulombe | Relaunch | 0 | - | 2017-07-01 | 2017-07-01 | 2017-07-01 | Y |  | Added per 2017 schedule confirmation response; 3/20 - weekly A&A meeting, removed per AC | 129
976 | Checkers | Checkers Food Safety Program | Rob Siler | Steve Steinberg | Relaunch | 40 | AP | 2017-07-01 | 2017-07-01 | 2017-07-01 | Y |  |  | 22
977 | Checkers | Checkers Brand Standards Audit | Rob Siler | Steve Steinberg | New Launch | 24 | AP | 2017-07-01 | 2017-07-01 | 2017-07-01 | Y |  | Added per 2017 schedule confirmation response; | 22
978 | Checkers | Checkers Food Safety Evaluation - Training Form | Rob Siler | Steve Steinberg | Relaunch | 24 | AP | 2017-07-01 | 2017-07-01 | 2017-07-01 | Y |  | 4/17 - SS email requesting 7/1 launch; 4/17 - A&A weekly meeting, moved to 7/1 in place of Checkers Marketing | 22
979 | Cheddar's | Cheddar's Casual Cafe Food Safety Evaluations | Michelle Hudson | Amanda Coulombe | Relaunch | 0 | NJ | 2017-07-01 | 2017-07-01 | 2017-07-01 | Y |  | 4/25 - DR email stating no 7/1 changes | 39
980 | Chipotle | Chipotle Food Safety Program | Keith Woith | Amanda Coulombe | Relaunch | 32 | NJ | 2017-07-01 | 2017-07-01 | 2017-07-01 | Y |  |  | 6
981 | Cinemark | Cinemark Brand Standards Program | Michelle Hudson | Tim Cassidy | Relaunch | 0 | NJ | 2017-07-01 | 2017-07-01 | 2017-07-01 | Y |  | Added per 2017 schedule confirmation response; This was a form for a pilot and they have not signed on for a larger program, so not making any changes until they sign on (11/3); Meera also sent email on 11/10 to JC recapping conversation confirming no changes for this program; 4/20 - removed in A&A weekly meeting due to Jennifer being out, once we're ready to reengage Jennifer, Tammy and I will connect | 29
982 | Cooper's Hawk | Coopers Hawk Food Safety & Workplace Safety Program | John Bestler | Eric Hightower | New Launch | 32 | AK | 2017-07-01 | 2017-07-01 | 2017-07-01 | Y |  | 4/10 - added per SH email | 119
983 | Dairy Queen | Dairy Queen Pride Program | Justin Prestinario | Amanda Coulombe | Relaunch | 0 | NJ | 2017-07-01 | 2017-07-01 | 2017-07-01 | Y |  | 5/19 - FL email stating no changes for 7/1, removed from schedule | 8
984 | DineEquity | Applebee's eCaPS Program | Keith Woith | Steve Steinberg | Relaunch | 0 | AD | 2017-07-01 | 2017-07-01 | 2017-07-01 | Y |  | 5/22 - MN email stating only feedback report change, no actual form changes so removed from schedule | 5
985 | DineEquity | Applebee's eCaPS Program - Spanish | Keith Woith | Steve Steinberg | Relaunch | 0 | AD | 2017-07-01 | 2017-07-01 | 2017-07-01 | Y |  | 4/17 - SS email requesting 5/15 launch be added, so now Spanish launches need to be added to each launch; 5/22 - MN email stating only feedback report change, no actual form changes so removed from schedule | 5
986 | Famous Dave's | Famous Dave's Food Safety Program | Justin Prestinario | Eric Hightower | Relaunch | 0 | NJ | 2017-07-01 | 2017-07-01 | 2017-07-01 | Y |  | 4/24 - RH email stating no changes for Famous Daves form | 43
987 | Friendly's | Friendly's Food Safety Program | Brian Nolan | Emily Naufel | Relaunch | 40 | AK | 2017-07-01 | 2017-07-01 | 2017-07-01 | Y |  |  | 41
988 | Glory Days | Glory Days Food Safety | Brian Nolan | Amanda Coulombe | Relaunch | 0 | - | 2017-07-01 | 2017-07-01 | 2017-07-01 | Y |  | Added per 2017 schedule confirmation response; 3/20 - weekly A&A meeting, removed per AC | 99
989 | Golden Corral | Golden Corral Food Safety | Brian Nolan | Emily Naufel | Relaunch | 32 | BH | 2017-07-01 | 2017-07-01 | 2017-07-01 | Y |  |  | 21
990 | Hard Rock Café | Hard Rock Café Food Safety Program | John Bestler | Amanda Coulombe | Relaunch | 0 | - | 2017-07-01 | 2017-07-01 | 2017-07-01 | Y |  | Added per 2017 schedule confirmation response; 3/20 - weekly A&A meeting, removed per AC | 36
991 | Hilton | Hilton Core Menu Program | Brian Nolan | Eric Hightower | Relaunch | 0 | - | 2017-07-01 | 2017-07-01 | 2017-07-01 | Y |  | 3/20 - weekly A&A meeting, removed per EH | 25
992 | Hilton | Hilton Food Safety Program | Brian Nolan | Eric Hightower | Relaunch | 0 | AP | 2017-07-01 | 2017-07-01 | 2017-07-01 | Y |  | 4/24 - RH email stating no changes for any Hilton programs | 25
993 | Hilton | Hilton Beverage Program | Brian Nolan | Eric Hightower | Relaunch | 0 | AP | 2017-07-01 | 2017-07-01 | 2017-07-01 | Y |  | 4/24 - RH email stating no changes for any Hilton programs | 25
994 | Jackson's | Jacksons Food Safety Program | Keith Woith | Amanda Coulombe | Relaunch | 0 | - | 2017-07-01 | 2017-07-01 | 2017-07-01 | Y |  | 3/20 - weekly A&A meeting, removed per AC | 71
995 | Kendall Senior Living | Kendal Senior Living Workplace Safety Program | Brian Nolan | Amanda Coulombe | Relaunch | 0 | - | 2017-07-01 | 2017-07-01 | 2017-07-01 | Y |  | Added per 2017 schedule confirmation response; 3/20 - weekly A&A meeting, removed per AC | 140
996 | Kendall Senior Living | Kendal Senior Living Food Safety Program | Brian Nolan | Amanda Coulombe | Relaunch | 0 | - | 2017-07-01 | 2017-07-01 | 2017-07-01 | Y |  | Added per 2017 schedule confirmation response; 3/20 - weekly A&A meeting, removed per AC | 140
997 | Max Restaurant Group | Max Restaurant Group 2008 Food Safety Evaluation | Brian Nolan | Amanda Coulombe | Relaunch | 0 | - | 2017-07-01 | 2017-07-01 | 2017-07-01 | Y |  | Added per 2017 schedule confirmation response; 3/20 - weekly A&A meeting, removed per AC | 113
998 | McDonald's | McDonalds Food Safety/ECS Program | Justin Prestinario | Eric Hightower | Relaunch | 40 | AD | 2017-07-01 | 2017-07-01 | 2017-07-01 | Y |  | 2/28 - added per EH 2017 expected work file | 3
999 | Noodle's | Noodles Food Safety Program | Keith Woith | Steve Steinberg | Relaunch | 40 | BH | 2017-07-01 | 2017-07-01 | 2017-07-01 | Y |  |  | 32
1000 | Noodle's | Noodles Self-Assessment Program | Keith Woith | Steve Steinberg | Relaunch | 40 | BH | 2017-07-01 | 2017-07-01 | 2017-07-01 | Y |  |  | 32
1001 | On the Border | On the Border Food Safety Program | Michelle Hudson | Steve Steinberg | Relaunch | 0 | AK | 2017-07-01 | 2017-07-01 | 2017-07-01 | Y |  |  | 46
1002 | Panera Bread | Panera Bread Brand Standards Program | John Bestler | Tim Cassidy | New Launch | 0 | AK | 2017-07-01 | 2017-07-01 | 2017-07-01 | Y |  | Added per 2017 schedule confirmation response; 2/15 - SH/TP meeting, 5/1 will not happen if questions are being ADDED (5/1 achievable with removals only); 2/27 - launch changed from 5/1 to 7/1 per TC's 2017 expected work file; 4/13 - weekly A&A meeting, customer will not be ready by 7/1 so removed from schedule | 10
1003 | Pizzeria Locale | Pizzeria Locale FS Program (Chipotle Subsidiary) | Keith Woith | Amanda Coulombe | New Launch | 32 | NJ | 2017-07-01 | 2017-07-01 | 2017-07-01 | Y |  | 4/5 - AC email stating possible request for custom form needed for Q3 (may instead add triggers to Chipotle form if possible) | #N/A
1004 | Potbelly's | Potbelly's Food Safety Program | John Bestler | Amanda Coulombe | Relaunch | 0 | AK | 2017-07-01 | 2017-07-01 | 2017-07-01 | Y |  | 5/31 - AC email confirming no 7/1 changes | 33
1005 | RaceTrac | RaceTrac Food Safety Evaluations | Brian Nolan | Emily Naufel | Relaunch | 24 | AP | 2017-07-01 | 2017-07-01 | 2017-07-01 | Y |  | 3/30 - weekly A&A meeting, 1st cycle start date delayed due to customer not provididng changes, customer never meets deadline, 2nd cycle starts 8/1 so pushing back to 8/1 | 34
1006 | Real Mex | Real Mex Food Safety Program | Keith Woith | Amanda Coulombe | Relaunch | 24 | AD | 2017-07-01 | 2017-07-01 | 2017-07-01 | Y |  | Added per 2017 schedule confirmation response; 3/20 - removed; will remove all relaunches except 10/1 | 60
1007 | Red Robin | Red Robin Food Safety Program | Keith Woith | Amanda Coulombe | New Launch | 32 | MG | 2017-07-01 | 2017-07-01 | 2017-07-01 | N |  | As of 6/30, hierarchy with test location is the only hierarchy on foodauditwebsite; waiting on customer for hierarchy information and email recipient information. 4/10 - added per SH email | 219
1008 | Snooze | Snooze Food Safety Program | Keith Woith | Amanda Coulombe | Relaunch | 0 | - | 2017-07-01 | 2017-07-01 | 2017-07-01 | Y |  | 3/20 - removed; will remove all relaunches except 10/1 | 112
1009 | Starbucks | Starbucks LIC Food Safety Program | Justin Prestinario | Tim Cassidy | Relaunch | 0 | BH | 2017-07-01 | 2017-07-01 | 2017-07-01 | Y |  | 5/23 - KM email stating no LS changes, removed from schedule | 1
1010 | Starbucks | Starbucks LIC Food Safety Program - French | Justin Prestinario | Tim Cassidy | Relaunch | 0 | BH | 2017-07-01 | 2017-07-01 | 2017-07-01 | Y |  | Added per 2017 schedule confirmation response; 5/23 - KM email stating no LS changes, removed from schedule | 1
1011 | Steak 'n Shake | Steak 'n Shake Food Safety Program | John Bestler | Tim Cassidy | Relaunch | 0 | NJ | 2017-07-01 | 2017-07-01 | 2017-07-01 | Y |  | Added per 2017 schedule confirmation response; 5/9 - KM email stating no changes | 24
1012 | Stripes | Stripes Food Safety Program | Michelle Hudson | Steve Steinberg | Relaunch | 24 | NJ | 2017-07-01 | 2017-07-01 | 2017-07-01 | Y |  |  | 26
1013 | Stripes | Sunoco Food Safety Program (Part of Stripes) | Michelle Hudson | Steve Steinberg | Relaunch | 24 | NJ | 2017-07-01 | 2017-07-01 | 2017-07-01 | Y |  | Added per 2017 schedule confirmation response; | 26
1014 | TGI Friday's | TGIF Food Safety Program | Michelle Hudson | Eric Hightower | Relaunch | 0 | MG | 2017-07-01 | 2017-07-01 | 2017-07-01 | Y |  | 5/31 - MG email (sick) stating RH notified her stating no changes | 17
1015 | TGI Friday's | TGIF Brand Standards Program | Michelle Hudson | Eric Hightower | Relaunch | 0 | MG | 2017-07-01 | 2017-07-01 | 2017-07-01 | Y |  | Added per 2017 schedule confirmation response; Monthly updates will be required due to the nature of a Brand Standards program; 4/12 - weekly SH/TP meeting, after discussing with Steve we removed from schedule due to relaunching on 6/1 | 17
1016 | Tropical Smoothie Café | Tropical Smoothie Café Food Safety Program | Brian Nolan | Tim Cassidy | Relaunch | 0 | NJ | 2017-07-01 | 2017-07-01 | 2017-07-01 | Y |  | Added per 2017 schedule confirmation response; No changes per AT on 10/6; meeting with customer in November '16 to review entire form, change may come out of meeting but will determine a new launch date for those; 5/8 - KM email stating no changes | 31
1017 | Starbucks | Starbucks Company Food Safety Program - French | Justin Prestinario | Tim Cassidy | Relaunch | 0 | AP | 2017-07-04 | 2017-07-04 | 2017-07-04 | Y |  | 4/17 - JC email requesting 7/4 launch be added; 5/8 - JC email stating cautioned SBUX on mid-cycle scoring change, customer agreed to no changes until FY18 | 1
1018 | Starbucks | Starbucks Company Food Safety Program | Justin Prestinario | Tim Cassidy | Relaunch | 0 | AP | 2017-07-04 | 2017-07-04 | 2017-07-04 | Y |  | 4/17 - JC email requesting 7/4 launch be added; 5/8 - JC email stating cautioned SBUX on mid-cycle scoring change, customer agreed to no changes until FY18 | 1
1019 | CKE | CKE Brand Standards | John Bestler | Amanda Coulombe | New Launch | 80 | AD | 2017-07-06 | 2017-05-01 | 2017-07-06 | Y |  | Added per 2017 schedule confirmation response; | 4
1020 | McDonald's | McDonalds Food Safety/ECS Program | Justin Prestinario | Eric Hightower | Relaunch | 40 | AD | 2017-07-07 | 2017-07-01 | 2017-07-07 | Y |  | 7/3 - relaunch to "fix" MSBI reports to break out findings by criticality | 3
1021 | Caribou / Einstein | Einstein Bagels Food Safety Program | Justin Prestinario | Tim Cassidy | Relaunch | 24 | MG | 2017-07-14 | 2017-07-01 | 2017-07-14 | Y |  | 6/23 - Per Victoria, launch date is 7/14. (Meeting with Victoria & Meera) 3/8 - per TC email, Einstein relaunches were aligned to Caribou (3 cycles) but since it's a 2 cycle program they only need to relaunch on 7/1. Removed 5/1 and 9/1 relaunches and replaced with 7/1. | 18
1022 | Trusthouse (Aladdin) | TrustHouse Food Safety Program | Brian Nolan | Eric Hightower | Relaunch | 8 | BH | 2017-07-14 | 2017-07-14 | 2017-07-14 | Y |  | 7/10 - CC email requesting N/A's be added | 137
1023 | Interstate Hotels and Resorts | Interstate Food Safety Program | Brian Nolan | Eric Hightower | Relaunch | 24 | BH | 2017-07-20 | 2017-07-20 | 2017-07-20 | N |  | 7/14 - BH email stating RH stopped by requesting CAM be setup | 48
1024 | Travel Centers of America | Travel Centers of America Food Safety Evaluation | John Bestler | Eric Hightower | Relaunch | 24 | BH | 2017-07-20 | 2017-07-20 | 2017-07-20 | N |  | 7/14 - BH email stating RH stopped by requesting CAM be setup | 65
1025 | Macaroni Grill | MacGrill Food Safety Program | Michelle Hudson | Amanda Coulombe | Relaunch | 24 | NJ | 2017-08-01 | 2017-07-01 | 2017-08-01 | N |  |  | 62
1026 | Checkers | Checkers Marketing Audit | Rob Siler | Steve Steinberg | Relaunch | 0 | AD | 2017-08-01 | 2017-08-01 | 2017-08-01 | Y |  | Added per 2017 schedule confirmation response; 4/17 - A&A weekly meeting, pushed back to 8/1 to make room for Checkers Training; 6/5 removed per EL due to customer being satisfied with current form | 22
1027 | Compass Group | Compass Workplace Safety Program #1 | Brian Nolan | Eric Hightower | New Launch | 40 | MG | 2017-08-01 | 2017-08-01 | 2017-08-01 | N |  | 3/1 - added per EH email | 11
1028 | Compass Group | Compass Workplace Safety Program #2 | Brian Nolan | Eric Hightower | New Launch | 40 | MG | 2017-08-01 | 2017-08-01 | 2017-08-01 | N |  |  | 11
1029 | Compass Group | Compass Workplace Safety Program #3 | Brian Nolan | Eric Hightower | New Launch | 40 | MG | 2017-08-01 | 2017-08-01 | 2017-08-01 | N |  |  | 11
1030 | Compass Group | Compass Workplace Safety Program #4 | Brian Nolan | Eric Hightower | New Launch | 40 | BH | 2017-08-01 | 2017-08-01 | 2017-08-01 | N |  |  | 11
1031 | Compass Group | Compass Workplace Safety Program #5 | Brian Nolan | Eric Hightower | New Launch | 40 | BH | 2017-08-01 | 2017-08-01 | 2017-08-01 | N |  |  | 11
1032 | Compass Group | Compass Workplace Safety Program #6 | Brian Nolan | Eric Hightower | New Launch | 0 | BH | 2017-08-01 | 2017-08-01 | 2017-08-01 | Y |  | 7/17 - weekly A&A meeting, removed; launching 1/1/18 | 11
1033 | Compass Group | Compass Workplace Safety Program #7 | Brian Nolan | Eric Hightower | New Launch | 0 | BH | 2017-08-01 | 2017-08-01 | 2017-08-01 | Y |  | 7/17 - weekly A&A meeting, removed; launching 1/1/18 | 11
1034 | Compass Group | Compass Workplace Safety Program #8 | Brian Nolan | Eric Hightower | New Launch | 0 | BH | 2017-08-01 | 2017-08-01 | 2017-08-01 | Y |  | 7/17 - weekly A&A meeting, removed; launching 1/1/18 | 11
1035 | Eatsa | Eatsa Food Safety Program | Keith Woith | Steve Steinberg | New Launch | 32 | AK | 2017-08-01 | 2017-08-01 | 2017-08-01 | N |  | 7/12 - added during relaunch | #N/A
1036 | Interstate Hotels and Resorts | Interstate Beverage Program | Brian Nolan | Eric Hightower | Relaunch | 24 | AP | 2017-08-01 | 2017-08-01 | 2017-08-01 | N |  | 2/28 - per EH 2017 expected work file, launch changed from 6/1 to 8/1 | 48
1037 | Interstate Hotels and Resorts | Interstate Food Safety Program | Brian Nolan | Eric Hightower | Relaunch | 0 | AP | 2017-08-01 | 2017-08-01 | 2017-08-01 | Y |  | 2/28 - per EH 2017 expected work file, launch changed from 6/1 to 8/1 | 48
1038 | Jamba Juice | Jamba Juice Traditional Food Safety Program - iForm | Keith Woith | Tim Cassidy | Relaunch | 32 | AD | 2017-08-01 | 2017-08-01 | 2017-08-01 | N |  | 2/27 - launch changed from 5/1 to 8/1 per TC's 2017 expected work file | 28
1039 | Jamba Juice | Jamba Juice Traditional Food Safety Program - Steton Form | Keith Woith | Tim Cassidy | Relaunch | 32 | AD | 2017-08-01 | 2017-08-01 | 2017-08-01 | N |  | 2/27 - launch changed from 5/1 to 8/1 per TC's 2017 expected work file | 28
1040 | Jamba Juice | Jamba Juice Express Food Safety Program - iForm | Keith Woith | Tim Cassidy | Relaunch | 0 | AD | 2017-08-01 | 2017-08-01 | 2017-08-01 | Y |  | 2/27 - launch changed to 8/1 per TC's 2017 expected work file; 7/20 - VB email confirming no changes, not launching | 28
1041 | Jamba Juice | Jamba Juice Express Food Safety Program - Steton Form | Keith Woith | Tim Cassidy | Relaunch | 0 | AK | 2017-08-01 | 2017-08-01 | 2017-08-01 | Y |  | 2/27 - launch changed to 8/1 per TC's 2017 expected work file; 7/20 - VB email confirming no changes, not launching | 28
1042 | Jamba Juice | Jamba Juice International Food Safety Program - iForm | Keith Woith | Tim Cassidy | New Launch | 40 | AK | 2017-08-01 | 2017-08-01 | 2017-08-01 | N |  | 2/27 - launch changed from 9/1 to 8/1 per TC's 2017 expected work file | 28
1043 | Jamba Juice | Jamba Juice International Food Safety Program - Steton Form | Keith Woith | Tim Cassidy | New Launch | 40 | AK | 2017-08-01 | 2017-08-01 | 2017-08-01 | N |  | 2/27 - launch changed from 9/1 to 8/1 per TC's 2017 expected work file | 28
1044 | McDonald's | McDonalds Food Safety Franchise Program | Justin Prestinario | Eric Hightower | New Launch | 40 | AP | 2017-08-01 | 2017-08-01 | 2017-08-01 | N |  | 6/9 - EH email requesting it be added; data to be separate from Corporate data and not accessible by Corp users | 3
1045 | McDonald's | McDonalds Food Safety/ECS Program | Justin Prestinario | Eric Hightower | Relaunch | 24 | MG | 2017-08-01 | 2017-08-01 | 2017-08-01 | N |  | 7/10 - AT requesting 2 questions be moved from 1 score group to another; will be delayed until after reprocessing of historical forms takes place | 3
1046 | Peter Piper Pizza | Peter Piper Pizza Mexico Food Safety Audits | Keith Woith | Amanda Coulombe | Relaunch | 0 | AP | 2017-08-01 | 2017-08-01 | 2017-08-01 | Y |  |  | 67
1047 | Pizza Ranch | Pizza Ranch Food Safety Program | Justin Prestinario | Eric Hightower | Relaunch | 16 | NJ | 2017-08-01 | 2017-08-01 | 2017-08-01 | N |  |  | 58
1048 | Stanford University | Stanford Food Safety Program | Keith Woith | Eric Hightower | Relaunch | 0 | NJ | 2017-08-01 | 2017-08-01 | 2017-08-01 | Y |  | 6/14 - AT weekly meeting, RH no changes | 118
1049 | Stanford University | Stanford Workplace Safety Program | Keith Woith | Eric Hightower | Relaunch | 0 | AP | 2017-08-01 | 2017-08-01 | 2017-08-01 | Y |  | 6/14 - AT weekly meeting, RH no changes | 118
1050 | TGI Friday's | TGIF Brand Standards Program | Michelle Hudson | Eric Hightower | Relaunch | 24 | NJ | 2017-08-01 | 2017-08-01 | 2017-08-01 | N |  | Added per 2017 schedule confirmation response; Monthly updates will be required due to the nature of a Brand Standards program | 17
1051 | Chick-fil-A | Chick-fil-A Catering Program | Rob Siler | Emily Naufel | Relaunch | 24 | AK | 2017-08-01 | 2017-09-01 | 2017-09-01 | N |  | 3/27 - AM request to pull up from 9/1 to 8/1 | 44
1052 | Chick-fil-A | Chick-fil-A CPE Program | Rob Siler | Emily Naufel | Relaunch | 24 | AK | 2017-08-01 | 2017-09-01 | 2017-09-01 | N |  | 3/27 - AM request to pull up from 9/1 to 8/1 | 44
1053 | CKE | CKE Mexico | John Bestler | Amanda Coulombe | Relaunch | 0 | AK | 2017-08-15 | 2017-08-15 | 2017-08-15 | Y |  | Per 2017 confirmation file, launch date moved from 9/10/17 to 8/15/17; 4/10 - removed per A&A weekly meeting, Mexico will now sync with January program year launches and only update once per year | 4
1054 | Buffalo Wild Wings | Buffalo Wild Wings - CO & Franchise Food Safety Program | Justin Prestinario | Emily Naufel | Relaunch | 32 | BH | 2017-09-01 | 2017-09-01 | 2017-09-01 | N |  | Actually launching 10/1 but customer needs materials a month in advance; set target launch a month earlier (8/31/16) | 15
1055 | Caribou / Einstein | Caribou Coffee Assessment (Brand Standards) | Justin Prestinario | Tim Cassidy | Relaunch | 24 | BH | 2017-09-01 | 2017-09-01 | 2017-09-01 | N |  |  | 18
1056 | Caribou / Einstein | Caribou Co-Branded Program | Justin Prestinario | Tim Cassidy | Relaunch | 24 | BH | 2017-09-01 | 2017-09-01 | 2017-09-01 | N |  |  | 18
1057 | Caribou / Einstein | Einstein Bagels Food Safety Program | Justin Prestinario | Tim Cassidy | Relaunch | 0 | - | 2017-09-01 | 2017-09-01 | 2017-09-01 | Y |  | 3/8 - removed per TC, originally a 5/1 and 9/1 relaunch (aligned with Caribou, but Einstein is only 2 cycles), so replaced with a 7/1 | 18
1058 | Cattleman's | Cattlemens Food Safety Evaluation | Keith Woith | Amanda Coulombe | Relaunch | 0 | - | 2017-09-01 | 2017-09-01 | 2017-09-01 | Y |  | Added per 2017 schedule confirmation response; 3/20 - weekly A&A meeting, launch date changed from 10/1 to 9/1; 7/10 - weekly A&A meeting, customer is dropping contract | 129
1059 | Compass Group | Compass Workplace Safety Program | Brian Nolan | Eric Hightower | Relaunch | 0 | AP | 2017-09-01 | 2017-09-01 | 2017-09-01 | Y |  | 7/10 - removed per weekly A&A meeting | 11
1060 | Creative Dining Services | Creative Dining Services Food Safety Program | John Bestler | Amanda Coulombe | Relaunch | 24 | - | 2017-09-01 | 2017-09-01 | 2017-09-01 | Y |  | 7/10 - weekly A&A meeting, unable to fit into schedule so removing | 123
1061 | DineEquity | IHOP OAR Program | Keith Woith | Steve Steinberg | Relaunch | 40 | BH | 2017-09-01 | 2017-09-01 | 2017-09-01 | N |  |  | 5
1062 | DineEquity | IHOP OAR Program - Spanish | Keith Woith | Steve Steinberg | Relaunch | 60 | BH | 2017-09-01 | 2017-09-01 | 2017-09-01 | N |  | 4/17 - SS email requesting 5/15 launch be added, so now Spanish launches need to be added to each launch | 5
1063 | DineEquity | IHOP Egg Reaudit | Keith Woith | Steve Steinberg | Relaunch | 0 | NJ | 2017-09-01 | 2017-09-01 | 2017-09-01 | Y |  | Added per 2017 schedule confirmation response; | 5
1064 | Greenville School System | Greenville Food Safety Program | Rob Siler | Amanda Coulombe | Relaunch | 24 | - | 2017-09-01 | 2017-09-01 | 2017-09-01 | Y |  | 7/10 - weekly A&A meeting, unable to fit into schedule so removing | 79
1065 | Hooters of America | Hooters Food Safety Program | Rob Siler | Emily Naufel | Relaunch | 0 | - | 2017-09-01 | 2017-09-01 | 2017-09-01 | Y |  | 7/17 - DR email confirming no changes until 1/1/18 | 30
1066 | Jamba Juice | Jamba Juice Traditional Food Safety Program - iForm | Keith Woith | Tim Cassidy | Relaunch | 0 | - | 2017-09-01 | 2017-09-01 | 2017-09-01 | Y |  | 2/27 - removed per TC's 2017 expected work file | 28
1067 | Jamba Juice | Jamba Juice Traditional Food Safety Program - Steton Form | Keith Woith | Tim Cassidy | Relaunch | 0 | - | 2017-09-01 | 2017-09-01 | 2017-09-01 | Y |  | 2/27 - removed per TC's 2017 expected work file | 28
1068 | King's Seafood | King's Seafood Food Safety Program | Keith Woith | Tim Cassidy | Relaunch | 0 | - | 2017-09-01 | 2017-09-01 | 2017-09-01 | Y |  | 6/1 - MM email stating no 9/1 changes | 132
1069 | Panera Bread | Panera Bread Food Safety Program | John Bestler | Tim Cassidy | Relaunch | 0 | NJ | 2017-09-01 | 2017-09-01 | 2017-09-01 | Y |  | Added per 2017 schedule confirmation response; 7/20 - weekly A&A meeting, no changes per VB | 10
1070 | Sodexo | Sodexo - Food Safety Canada (English Version) | Brian Nolan | Eric Hightower | New Launch | 32 | AD | 2017-09-01 | 2017-09-01 | 2017-09-01 | N |  | Added per 2017 schedule confirmation response; FY2018 Re-launch | 9
1071 | Sodexo | Sodexo - Food Safety Canada (French Version) | Brian Nolan | Eric Hightower | New Launch | 32 | AD | 2017-09-01 | 2017-09-01 | 2017-09-01 | N |  | Added per 2017 schedule confirmation response; FY2018 Re-launch | 9
1072 | Sodexo | Sodexo - Health & Safety Canada (English) | Brian Nolan | Eric Hightower | New Launch | 32 | AD | 2017-09-01 | 2017-09-01 | 2017-09-01 | N |  | Added per 2017 schedule confirmation response; FY2018 Re-launch | 9
1073 | Sodexo | Sodexo - Health & Safety Canada (French) | Brian Nolan | Eric Hightower | New Launch | 32 | AD | 2017-09-01 | 2017-09-01 | 2017-09-01 | N |  | Added per 2017 schedule confirmation response; FY2018 Re-launch | 9
1074 | Sodexo | Sodexo - Food Safety US | Brian Nolan | Eric Hightower | New Launch | 32 | AD | 2017-09-01 | 2017-09-01 | 2017-09-01 | N |  | Added per 2017 schedule confirmation response; FY2018 Re-launch | 9
1075 | Sodexo | Sodexo - Health & Safety Food Service US | Brian Nolan | Eric Hightower | New Launch | 32 | NJ | 2017-09-01 | 2017-09-01 | 2017-09-01 | N |  | Added per 2017 schedule confirmation response; FY2018 Re-launch | 9
1076 | Sodexo | Sodexo - Health & Safety FM, Patient Transport, Environmental Services US | Brian Nolan | Eric Hightower | New Launch | 0 | NJ | 2017-09-01 | 2017-09-01 | 2017-09-01 | Y |  | Added per 2017 schedule confirmation response; FY2018 Re-launch; 7/10 - removed per weekly A&A meeting | 9
1077 | Sodexo | Sodexo - Health & Safety FM P&G US | Brian Nolan | Eric Hightower | New Launch | 0 | NJ | 2017-09-01 | 2017-09-01 | 2017-09-01 | Y |  | Added per 2017 schedule confirmation response; FY2018 Re-launch; 7/10 - removed per weekly A&A meeting | 9
1078 | TGI Friday's | TGIF Brand Standards Program | Michelle Hudson | Eric Hightower | Relaunch | 0 | AP | 2017-09-01 | 2017-09-01 | 2017-09-01 | Y |  | Added per 2017 schedule confirmation response; Monthly updates will be required due to the nature of a Brand Standards program | 17
1079 | YUM! Brands | Pizza Hut - Co/FZ Program | Michelle Hudson | Emily Naufel | Relaunch | 80 | MG | 2017-09-01 | 2017-09-01 | 2017-09-01 | N |  |  | 2
1080 | YUM! Brands | Pizza Hut - Co/Fr Operator App | Michelle Hudson | Emily Naufel | Relaunch | 24 | MG | 2017-09-01 | 2017-09-01 | 2017-09-01 | N |  |  | 2
1081 | YUM! Brands | Pizza Hut - M Operator App | Michelle Hudson | Emily Naufel | Relaunch | 24 | MG | 2017-09-01 | 2017-09-01 | 2017-09-01 | N |  |  | 2
1082 | YUM! Brands | Pizza Hut - LIC Program | Michelle Hudson | Emily Naufel | Relaunch | 40 | MG | 2017-09-01 | 2017-09-01 | 2017-09-01 | N |  |  | 2
1083 | YUM! Brands | Pizza Hut - Maintenance Program | Michelle Hudson | Emily Naufel | Relaunch | 40 | MG | 2017-09-01 | 2017-09-01 | 2017-09-01 | N |  |  | 2
1084 | YUM! Brands | Pizza Hut - Target Program | Michelle Hudson | Emily Naufel | Relaunch | 24 | MG | 2017-09-01 | 2017-09-01 | 2017-09-01 | N |  |  | 2
1085 | Popeye's | Popeyes Food Safety Program | Rob Siler | Emily Naufel | Relaunch | 16 | AK | 2017-09-04 | 2017-09-04 | 2017-09-04 | N |  | 7/15 - MS confirmed RefNum only changes | 12
1086 | Popeye's | Popeyes Food Safety Excellence Program | Rob Siler | Emily Naufel | Relaunch | 0 | - | 2017-09-04 | 2017-09-04 | 2017-09-04 | Y |  | Per 2017 schedule validation, launch date changed from 8/1/17 to 9/4/17; 2/27 - removed per EN's 2017 expected work file | 12
1087 | CKE | CKE Food Safety | John Bestler | Amanda Coulombe | Relaunch | 80 | AK | 2017-09-10 | 2017-09-10 | 2017-09-10 | N |  | Per 2017 confirmation file, launch date moved from 9/10/17 to 9/12/17 | 4
1088 | CKE | CKE Playground Program | John Bestler | Amanda Coulombe | Relaunch | 24 | AK | 2017-09-10 | 2017-09-10 | 2017-09-10 | N |  | Per 2017 confirmation file, launch date moved from 9/10/17 to 9/12/17 | 4
1089 | CKE | CKE Workplace Safety | John Bestler | Amanda Coulombe | Relaunch | 40 | AK | 2017-09-10 | 2017-09-10 | 2017-09-10 | N |  | Per 2017 confirmation file, launch date moved from 9/10/17 to 9/12/17 | 4
1090 | CKE | CKE Brand Standards | John Bestler | Amanda Coulombe | Relaunch | 40 | AK | 2017-09-10 | 2017-09-12 | 2017-09-12 | N |  | Added per 2017 schedule confirmation response; | 4
1091 | Compass Group | Compass FLIK RizePoint Form | Brian Nolan | Eric Hightower | Relaunch | 16 |  |  | 2017-08-04 | 2017-08-04 | N |  | 7/17 - CC email requesting 1 question's point change and new autofail functionality | 11
1092 | Compass Group | Compass Workplace Safety Program | Brian Nolan | Eric Hightower | Relaunch | 16 |  |  | 2017-08-04 | 2017-08-04 | N |  | 7/17 - CC email requesting 2018 reference numbers be added | 11
1093 | Santiagos | Santiagos Food Safety Program | Keith Woith | Eric Hightower | New Launch | 32 | AD | 2017-08-11 | 2017-08-11 | 2017-08-11 | N |  | 7/17 - RH provided high-level scope to start build | #N/A
1094 | Bass Pro Shop | Bass Pro 2009 Food Safety Evaluations | John Bestler | Amanda Coulombe | Relaunch | 24 |  |  | 2017-09-01 | 2017-09-01 | N |  | Added per 2017 schedule confirmation response; | 76
1095 | Burger King | Burger King Playground Inspection Program | John Bestler | Steve Steinberg | Relaunch | 24 |  |  | 2017-09-01 | 2017-09-01 | N |  | Per 2017 schedule validation, launch date moved from 8/1/17 to 9/1/17 | 20
1096 | Compass Group | Compass Food Safety Program | Brian Nolan | Eric Hightower | Relaunch | 32 |  |  | 2017-09-01 | 2017-09-01 | N |  |  | 11
1097 | Compass Group | Compass HD Program | Brian Nolan | Eric Hightower | Relaunch | 32 |  |  | 2017-09-01 | 2017-09-01 | N |  |  | 11
1098 | Compass Group | Compass J&W Program | Brian Nolan | Eric Hightower | Relaunch | 32 |  |  | 2017-09-01 | 2017-09-01 | N |  |  | 11
1099 | Hard Rock Café | Hard Rock Café Food Safety Program | John Bestler | Amanda Coulombe | Relaunch | 24 |  |  | 2017-09-01 | 2017-09-01 | N |  | Added per 2017 schedule confirmation response; 3/20 - weekly A&A meeting, launch date changed from 10/1 to 9/1 | 36
1100 | Hyatt Hotels | Hyatt Food Safety Program | John Bestler | Steve Steinberg | Relaunch | 0 | - | 2017-09-01 | 2017-09-01 | 2017-09-01 | Y |  | 7/20 - EL response confirming this can be removed (from my 9/1-10/1 request validation email) | 53
1101 | Metz & Associates | Metz Culinary Management | Brian Nolan | Amanda Coulombe | Relaunch | 24 |  |  | 2017-09-01 | 2017-09-01 | N |  | Added per 2017 schedule confirmation response; | 59
1102 | Texas Roadhouse | Texas Roadhouse FS & WPS Program | Brian Nolan | Amanda Coulombe | Relaunch | 40 |  |  | 2017-09-01 | 2017-09-01 | N |  | 4/27 - weekly A&A meeting, JC informed moving to AC's Team and will also need a 9/1 relaunch | 219
1103 | EcoSure | Canada Standard Food Safety Form | All | All | New Launch | 40 |  |  | 2017-09-15 | 2017-09-15 | N |  |  | 603
1104 | 4 Rivers Smokehouse | 4 Rivers Smokehouse Food Safety Evaluation | Rob Siler | Amanda Coulombe | Relaunch | 24 |  |  | 2017-10-01 | 2017-10-01 | N |  | Added per 2017 schedule confirmation response; | 144
1105 | Aramark | ARAMARK Food Safety Program | Brian Nolan | Amanda Coulombe | Relaunch | 24 |  |  | 2017-10-01 | 2017-10-01 | N |  |  | 16
1106 | Aramark | ARAMARK SAFE Food Safety Program | Brian Nolan | Amanda Coulombe | Relaunch | 40 |  |  | 2017-10-01 | 2017-10-01 | N |  |  | 16
1107 | Bento Sushi | Bento Sushi Factory Program | Justin Prestinario | Amanda Coulombe | Relaunch | 32 |  |  | 2017-10-01 | 2017-10-01 | N |  | 2/27 - added per AC 2017 expected work file; 7/1 Nothing from AT team pushed back to soft 10/01 | 61
1108 | Bento Sushi | Bento Sushi Kiosk Program | Justin Prestinario | Amanda Coulombe | New Launch | 40 |  |  | 2017-10-01 | 2017-10-01 | N |  | 2/27 - added per AC 2017 expected work file; 7/1 Nothing from AT team pushed back to soft 10/01 | 61
1109 | Chipotle | Chipotle Food Safety Program | Keith Woith | Amanda Coulombe | Relaunch | 32 |  |  | 2017-10-01 | 2017-10-01 | N |  |  | 6
1110 | Compass Group | Compass Canada English Form | Brian Nolan | Eric Hightower | Relaunch | 32 |  |  | 2017-10-01 | 2017-10-01 | N |  |  | 11
1111 | Compass Group | Compass Canada French Form | Brian Nolan | Eric Hightower | Relaunch | 32 |  |  | 2017-10-01 | 2017-10-01 | N |  |  | 11
1112 | Eureka! | Eureka Food Safety Program | Keith Woith | Emily Naufel | Relaunch | 24 |  |  | 2017-10-01 | 2017-10-01 | N |  | 4/14 - DR email requesting this be added | 111
1113 | Glory Days | Glory Days Food Safety | Brian Nolan | Amanda Coulombe | Relaunch | 0 |  |  | 2017-10-01 | 2017-10-01 | Y |  | Added per 2017 schedule confirmation response; 4/10 - weekly A&A meeting, removed per FL due to relaunching on 5/1 | 99
1114 | Jackson's | Jacksons Food Safety Program | Keith Woith | Amanda Coulombe | Relaunch | 24 |  |  | 2017-10-01 | 2017-10-01 | N |  |  | 71
1115 | Margaritaville | Margaritaville Food Safety Program | Rob Siler | Amanda Coulombe | Relaunch | 24 |  |  | 2017-10-01 | 2017-10-01 | N |  | Added per 2017 schedule confirmation response; | 103
1116 | Max Restaurant Group | Max Restaurant Group 2008 Food Safety Evaluation | Brian Nolan | Amanda Coulombe | Relaunch | 24 |  |  | 2017-10-01 | 2017-10-01 | N |  | Added per 2017 schedule confirmation response; | 113
1117 | Mimi's Café | Mimi's Café Food Safety Program | Michelle Hudson | Tim Cassidy | Relaunch | 0 | - | 2017-10-01 | 2017-10-01 | 2017-10-01 | Y |  | Added per 2017 schedule confirmation response; 7/19 - MO emailed AT asking if all backlog-9/1's and 10/1's still needed, MM confirmed this could be removed | 75
1118 | Newk's | Newks Food Safety Program | Michelle Hudson | Steve Steinberg | Relaunch | 24 |  |  | 2017-10-01 | 2017-10-01 | N |  | 4/17 - SS email requesting 10/1 launch be added | 69
1119 | Panera Bread | Panera Bread Brand Standards Program | John Bestler | Tim Cassidy | New Launch | 24 |  |  | 2017-10-01 | 2017-10-01 | N |  | Added per 2017 schedule confirmation response; 2/27 - launch changed from 9/1 to 10/1 per TC's 2017 expected work file | 10
1120 | Pret A Manger | Pret A Manger Food Safety Program | Brian Nolan | Steve Steinberg | Relaunch | 24 |  |  | 2017-10-01 | 2017-10-01 | N |  |  | 64
1121 | Real Mex | Real Mex Food Safety Program | Keith Woith | Amanda Coulombe | Relaunch | 24 |  |  | 2017-10-01 | 2017-10-01 | N |  | Added per 2017 schedule confirmation response; | 60
1122 | Snooze | Snooze Food Safety Program | Keith Woith | Amanda Coulombe | Relaunch | 40 |  |  | 2017-10-01 | 2017-10-01 | N |  |  | 112
1123 | Starbucks | Starbucks Company Food Safety Program - French | Justin Prestinario | Tim Cassidy | Relaunch | 24 |  |  | 2017-10-01 | 2017-10-01 | N |  | Added per 2017 schedule confirmation response; | 1
1124 | Starbucks | Starbucks Company Food Safety Program | Justin Prestinario | Tim Cassidy | Relaunch | 24 |  |  | 2017-10-01 | 2017-10-01 | N |  | Added per 2017 schedule confirmation response; | 1
1125 | Starbucks | Starbucks Facilities Program | Justin Prestinario | Tim Cassidy | Relaunch | 24 |  |  | 2017-10-01 | 2017-10-01 | N |  | Added per 2017 schedule confirmation response; | 1
1126 | Starbucks | Starbucks Facilities Program - French | Justin Prestinario | Tim Cassidy | Relaunch | 24 |  |  | 2017-10-01 | 2017-10-01 | N |  | Added per 2017 schedule confirmation response; | 1
1127 | Steak 'n Shake | Steak 'n Shake Food Safety Program | John Bestler | Tim Cassidy | Relaunch | 24 |  |  | 2017-10-01 | 2017-10-01 | N |  | Added per 2017 schedule confirmation response; | 24
1128 | Stripes | Stripes Food Safety Program | Michelle Hudson | Steve Steinberg | Relaunch | 24 |  |  | 2017-10-01 | 2017-10-01 | N |  |  | 26
1129 | TGI Friday's | TGIF Brand Standards Program | Michelle Hudson | Eric Hightower | Relaunch | 24 |  |  | 2017-10-01 | 2017-10-01 | N |  | 2/28 - Added per 2017 schedule confirmation response; Monthly updates will be required due to the nature of a Brand Standards program | 17
1130 | TGI Friday's | TGIF Food Safety Program | Michelle Hudson | Eric Hightower | Relaunch | 24 |  |  | 2017-10-01 | 2017-10-01 | N |  |  | 17
1131 | Tropical Smoothie Café | Tropical Smoothie Café Food Safety Program | Brian Nolan | Tim Cassidy | Relaunch | 24 |  |  | 2017-10-01 | 2017-10-01 | N |  | Added per 2017 schedule confirmation response; No changes per AT on 10/6; meeting with customer in November '16 to review entire form, change may come out of meeting but will determine a new launch date for those | 31
1132 | Twin Peaks | Twin Peaks Food Safety Program | Michelle Hudson | Eric Hightower | Relaunch | 24 |  |  | 2017-10-01 | 2017-10-01 | N |  |  | 52
1133 | Shake Shack | Shake Shack FS Program | Brian Nolan | Emily Naufel | Relaunch | 0 |  |  | 2017-10-10 | 2017-10-10 | Y |  | 6/22 - MS request to add realunch; 7/17 - MS emails stating changes no longer needed | 105
1134 | Honeybaked Ham | Honeybaked Ham Holiday Program - Food Safety Program | Rob Siler | Emily Naufel | Relaunch | 24 |  |  | 2017-11-01 | 2017-11-01 | N |  |  | 37
1135 | Honeybaked Ham | Honeybaked Ham Holiday Program - PopUp Retail | Rob Siler | Emily Naufel | Relaunch | 24 |  |  | 2017-11-01 | 2017-11-01 | N |  |  | 37
1136 | Darden Franchise Group | Darden Franchise Food Safety Program | Rob Siler | Amanda Coulombe | Relaunch | 32 |  |  | 2017-11-27 | 2017-11-27 | N |  |  | 185
1137 | Red Lobster | Red Lobster Food Safety Program | John Bestler | Amanda Coulombe | Relaunch | 24 |  |  | 2017-11-27 | 2017-11-27 | N |  | Per 2017 schedule validation file, launch moved from 11/30/17 to 11/27/17 | 23
1138 | 4 Rivers Smokehouse | 4 Rivers Smokehouse Food Safety Evaluation | Rob Siler | Amanda Coulombe | Relaunch | 24 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | 144
1139 | 85 ᵒC Café | 85 Degrees Celsius Café Food Safety Program | Keith Woith | Steve Steinberg | Relaunch | 24 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | 98
1140 | Academia Barilla | Academia Barilla Food Safety | John Bestler | Steve Steinberg | Relaunch | 24 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | 157
1141 | Aramark | ARAMARK SAFE Food Safety Program | Brian Nolan | Amanda Coulombe | Relaunch | 80 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | 16
1142 | Arby's | Arby's Food Safety Program | Rob Siler | Amanda Coulombe | Relaunch | 40 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | 19
1143 | Areas USA | Areas USA Food Safety Program | John Bestler | Steve Steinberg | Relaunch | 80 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | 93
1144 | Au Bon Pain | Au Bon Pain Food Safety Program | Brian Nolan | Eric Hightower | Relaunch | 40 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | 38
1145 | Avendra Hospitality | Avendra Hospitality Food Safety Program | Brian Nolan | Amanda Coulombe | Relaunch | 24 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | 74
1146 | Babalu | Babalu Food Safety Program | Rob Siler | Amanda Coulombe | Relaunch | 24 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | #N/A
1147 | Benihana | Benihana Food Safety Program | Rob Siler | Steve Steinberg | Relaunch | 32 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | 49
1148 | Bento Sushi | Bento Sushi Factory Program | Justin Prestinario | Amanda Coulombe | Relaunch | 40 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | 61
1149 | Bento Sushi | Bento Sushi Kiosk Program | Justin Prestinario | Amanda Coulombe | Relaunch | 40 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | 61
1150 | Bloomin' Brands | Bloomin Brands Food Safety Program | Rob Siler | Steve Steinberg | Relaunch | 24 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | 13
1151 | Boudin Bakery | Boudin Bakery Food Safety Program | Keith Woith | Eric Hightower | Relaunch | 40 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | 66
1152 | Buffalo Wild Wings | Buffalo Wild Wings - CO & Franchise Food Safety Program | Justin Prestinario | Emily Naufel | Relaunch | 24 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | 15
1153 | Burger King | Burger King Bun Sampling Program | John Bestler | Steve Steinberg | Relaunch | 80 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | 20
1154 | Café Zupa's | Café Zupas Food Safety Program | Keith Woith | Eric Hightower | Relaunch | 24 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | 81
1155 | Caribou / Einstein | Caribou Coffee Assessment (Brand Standards) | Rob Siler | Amanda Coulombe | Relaunch | 24 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | 18
1156 | Caribou / Einstein | Caribou Co-Branded Program | Rob Siler | Amanda Coulombe | Relaunch | 24 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | 18
1157 | Caribou / Einstein | Einstein Bagels Food Safety Program | Rob Siler | Amanda Coulombe | Relaunch | 24 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | 18
1158 | CERCA TROVA | CERCA TROVA Food Safety Program | Keith Woith | Steve Steinberg | Relaunch | 32 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | 84
1159 | Checkers | Checkers Food Safety Program | Rob Siler | Steve Steinberg | Relaunch | 24 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | 22
1160 | Checkers | Checkers Food Safety Evaluation - Training Form | Rob Siler | Steve Steinberg | Relaunch | 24 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | 22
1161 | Checkers | Checkers Marketing Audit | Rob Siler | Steve Steinberg | Relaunch | 24 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | 22
1162 | Checkers | Checkers Brand Standards Audit | Rob Siler | Steve Steinberg | Relaunch | 24 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | 22
1163 | Cheddar's | Cheddar's Casual Cafe Food Safety Evaluations | Michelle Hudson | Amanda Coulombe | Relaunch | 24 |  |  | 2018-01-01 | 2018-01-01 | N |  | 7/18 - AT note from 2018 file, this customer is now on Amanda's team; | 39
1164 | Chipotle | Chipotle Food Safety Program | Keith Woith | Amanda Coulombe | Relaunch | 32 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | 6
1165 | Cinemark | Cinemark Food Safety Program | Michelle Hudson | Tim Cassidy | Relaunch | 24 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | 29
1166 | Cinemark | Cinemark Brand Standards Program | Michelle Hudson | Tim Cassidy | Relaunch | 24 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | 29
1167 | City BBQ | City BBQ Food Safety Program | John Bestler | Emily Naufel | Relaunch | 40 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | 95
1168 | Compass Group | Compass FLIK RizePoint Form | Brian Nolan | Eric Hightower | Relaunch | 80 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | 11
1169 | Compass Group | Compass Canada English Form | Brian Nolan | Eric Hightower | Relaunch | 80 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | 11
1170 | Compass Group | Compass Canada French Form | Brian Nolan | Eric Hightower | Relaunch | 80 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | 11
1171 | Compass Group | Compass Food Safety Program | Brian Nolan | Eric Hightower | Relaunch | 80 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | 11
1172 | Compass Group | Compass HD Program | Brian Nolan | Eric Hightower | Relaunch | 80 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | 11
1173 | Compass Group | Compass J&W Program | Brian Nolan | Eric Hightower | Relaunch | 80 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | 11
1174 | Compass Group | Compass Workplace Safety Program #1 | Brian Nolan | Eric Hightower | Relaunch | 80 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | 11
1175 | Compass Group | Compass Workplace Safety Program #2 | Brian Nolan | Eric Hightower | Relaunch | 80 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | 11
1176 | Compass Group | Compass Workplace Safety Program #3 | Brian Nolan | Eric Hightower | Relaunch | 80 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | 11
1177 | Compass Group | Compass Workplace Safety Program #4 | Brian Nolan | Eric Hightower | Relaunch | 80 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | 11
1178 | Compass Group | Compass Workplace Safety Program #5 | Brian Nolan | Eric Hightower | New Launch | 80 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | 11
1179 | Compass Group | Compass Workplace Safety Program #6 | Brian Nolan | Eric Hightower | New Launch | 80 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | 11
1180 | Compass Group | Compass Workplace Safety Program #7 | Brian Nolan | Eric Hightower | New Launch | 80 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | 11
1181 | Compass Group | Compass Workplace Safety Program #8 | Brian Nolan | Eric Hightower | New Launch | 80 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | 11
1182 | Compass Group | Compass Workplace Safety Program | Brian Nolan | Eric Hightower | New Launch | 80 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | 11
1183 | Cooper's Hawk | Coopers Hawk Food Safety & Workplace Safety Program | Rob Siler | Amanda Coulombe | Relaunch | 24 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | 119
1184 | Cornell University | Cornell Food Safety Program | Brian Nolan | Eric Hightower | Relaunch | 24 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | 110
1185 | Corner Bakery | Corner Bakery Food Safery Program | Rob Siler | Amanda Coulombe | Relaunch | 24 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | 40
1186 | Corner Store | Corner Store Food Safety Program | Michelle Hudson | Steve Steinberg | Relaunch | 24 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | 27
1187 | Culinaire Hospitality | Culinaire Food Safety Program | Brian Nolan | Eric Hightower | Relaunch | 24 |  |  | 2018-01-01 | 2018-01-01 | N |  | 7/18 - AT note from 2018 file, ref #s only; | 152
1188 | Dairy Queen | Dairy Queen Pride Program | Justin Prestinario | Amanda Coulombe | Relaunch | 24 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | 8
1189 | Delaware North | Delaware North Food Safety Program | Brian Nolan | Steve Steinberg | Relaunch | 24 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | 94
1190 | Desert Island Properties | Desert Island Food Safety Program | Keith Woith | Steve Steinberg | Relaunch | 24 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | 120
1191 | Donovan's Steak & Chop House | Donovan's Food Safety Program | Keith Woith | Steve Steinberg | Relaunch | 24 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | 161
1192 | Eatsa | Eatsa Food Safety Program | Keith Woith | Steve Steinberg | Relaunch | 32 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | #N/A
1193 | Entertainment Cruises | Entertainment Cruises Food Safety | John Bestler | Eric Hightower | Relaunch | 24 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | 56
1194 | Eureka! | Eureka Food Safety Program | Keith Woith | Emily Naufel | Relaunch | 24 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | 111
1195 | Fairmont Hotels | Fairmont Food Safety Program | Justin Prestinario | Eric Hightower | Relaunch | 40 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | 47
1196 | Fairmont Hotels | Fairmont Guest Experience Program | Justin Prestinario | Eric Hightower | Relaunch | 40 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | 47
1197 | Famous Dave's | Famous Dave's Food Safety Program | Justin Prestinario | Eric Hightower | Relaunch | 24 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | 43
1198 | Fogo De Chao | Fogo de Chao Food Safety | Michelle Hudson | Eric Hightower | Relaunch | 24 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | 55
1199 | Four Winds Casino | Four Winds Casino Food Safety Program | John Bestler | Steve Steinberg | Relaunch | 24 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | 136
1200 | Fox Restaurant Concepts | Fox Restaurant QSR Evaluation | Keith Woith | Tim Cassidy | Relaunch | 24 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | 68
1201 | Fox Restaurant Concepts | Fox Restaurant Employee and Guest Safety | Keith Woith | Tim Cassidy | Relaunch | 24 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | 68
1202 | Freddy's Frozen Custard | Freddy's Frozen Custard FS Program | John Bestler | Eric Hightower | Relaunch | 32 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | 207
1203 | Friendly's | Friendly's Food Safety Program | Brian Nolan | Emily Naufel | Relaunch | 40 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | 41
1204 | Glory Days | Glory Days Food Safety | Brian Nolan | Amanda Coulombe | Relaunch | 24 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | 99
1205 | Golden Corral | Golden Corral Food Safety | Brian Nolan | Emily Naufel | Relaunch | 24 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | 21
1206 | Greenville School System | Greenville Food Safety Program | Rob Siler | Amanda Coulombe | Relaunch | 24 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | 79
1207 | Hard Rock Café | Hard Rock Café Food Safety Program | John Bestler | Amanda Coulombe | Relaunch | 24 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | 36
1208 | Hilton | Hilton Food Safety Program | Brian Nolan | Eric Hightower | Relaunch | 24 |  |  | 2018-01-01 | 2018-01-01 | N |  | 7/18 - AT note from 2018 file, likely only ref #s but will confirm; | 25
1209 | Hilton | Hilton Beverage Program | Brian Nolan | Eric Hightower | Relaunch | 24 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | 25
1210 | Hilton | Hilton Additional Program | Brian Nolan | Eric Hightower | Relaunch | 24 |  |  | 2018-01-01 | 2018-01-01 | N |  | 7/18 - AT note from 2018 file, likely only ref #s but will confirm; | 25
1211 | Hooters of America | Hooters Food Safety Program | Rob Siler | Emily Naufel | Relaunch | 24 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | 30
1212 | Ignite Restaurants | Ignite Food Safety Evaluation Program | Michelle Hudson | Amanda Coulombe | Relaunch | 40 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | 54
1213 | iPic Theaters | iPic Food Safety Program | Rob Siler | Steve Steinberg | Relaunch | 40 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | 102
1214 | Jackson's | Jacksons Food Safety Program | Keith Woith | Amanda Coulombe | Relaunch | 40 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | 71
1215 | Jamba Juice | Jamba Juice Traditional Food Safety Program - iForm | Keith Woith | Tim Cassidy | Relaunch | 24 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | 28
1216 | Jamba Juice | Jamba Juice Traditional Food Safety Program - Steton Form | Keith Woith | Tim Cassidy | Relaunch | 24 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | 28
1217 | Jamba Juice | Jamba Juice Express Food Safety Program - iForm | Keith Woith | Tim Cassidy | Relaunch | 24 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | 28
1218 | Jamba Juice | Jamba Juice Express Food Safety Program - Steton Form | Keith Woith | Tim Cassidy | Relaunch | 24 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | 28
1219 | Jamba Juice | Jamba Juice International Food Safety Program - iForm | Keith Woith | Tim Cassidy | Relaunch | 24 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | 28
1220 | Jamba Juice | Jamba Juice International Food Safety Program - Steton Form | Keith Woith | Tim Cassidy | Relaunch | 24 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | 28
1221 | Kendall Senior Living | Kendal Senior Living Workplace Safety Program | Brian Nolan | Amanda Coulombe | Relaunch | 40 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | 140
1222 | Kendall Senior Living | Kendal Senior Living Food Safety Program | Brian Nolan | Amanda Coulombe | Relaunch | 40 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | 140
1223 | King's Seafood | King's Seafood Food Safety Program | Rob Siler | Amanda Coulombe | Relaunch | 24 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | 132
1224 | Kona Grill | Kona Grill Food Safety | Keith Woith | Tim Cassidy | Relaunch | 24 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | 77
1225 | Lazy Dog Café | Lazy Dog Cafe Food Safety Program | Division | Steve Steinberg | Relaunch | 24 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | 83
1226 | Linchris Hotels | Linchris Hotel Corporate Food Safety Program | Brian Nolan | Eric Hightower | Relaunch | 24 |  |  | 2018-01-01 | 2018-01-01 | N |  | 7/18 - AT note from 2018 file, ref #s only; | 138
1227 | LTP Management Group | LTP Food Safety Program | Rob Siler | Eric Hightower | Relaunch | 24 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | 176
1228 | Luna Grill | Luna Grill Food Safety Program | Keith Woith | Emily Naufel | Relaunch | 32 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | 90
1229 | Macaroni Grill | MacGrill Food Safety Program | Michelle Hudson | Amanda Coulombe | Relaunch | 40 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | 62
1230 | Marcus Hotels | Marcus Hotels Food Safety | John Bestler | Tim Cassidy | Relaunch | 24 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | 131
1231 | Margaritaville | Margaritaville Food Safety Program | Rob Siler | Amanda Coulombe | Relaunch | 24 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | 103
1232 | Max Restaurant Group | Max Restaurant Group 2008 Food Safety Evaluation | Brian Nolan | Amanda Coulombe | Relaunch | 24 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | 113
1233 | McDonald's | McDonalds PlayPlace Program | Justin Prestinario | Eric Hightower | Relaunch | 24 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | 3
1234 | McDonald's | McDonalds Food Safety Program | Justin Prestinario | Eric Hightower | New Launch | 24 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | 3
1235 | McDonald's | McDonalds ECS Program | Justin Prestinario | Eric Hightower | New Launch | 24 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | 3
1236 | McDonald's | McDonald's Security Assessment Program | Justin Prestinario | Eric Hightower | Relaunch | 24 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | 3
1237 | McDonald's | McDonalds Food Safety Franchise Program | Justin Prestinario | Eric Hightower | Relaunch | 24 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | 3
1238 | Noodles | Noodles Food Safety Program | Rob Siler | Amanda Coulombe | Relaunch | 24 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | #N/A
1239 | Noodles | Noodles Self-Assessment Program | Rob Siler | Amanda Coulombe | Relaunch | 24 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | #N/A
1240 | Ohio State University | Ohio State Food Safety Program | John Bestler | Eric Hightower | Relaunch | 24 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | 162
1241 | Olga's Kitchen | Olga's Kitchen Food Safety Program | John Bestler | Amanda Coulombe | Relaunch | 24 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | 104
1242 | Omni Hotels | Omni Hotels Food Safety Program | Michelle Hudson | Tim Cassidy | Relaunch | 24 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | 57
1243 | On the Border | On the Border Food Safety Program | Rob Siler | Amanda Coulombe | Relaunch | 24 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | #N/A
1244 | Panera | Panera Bread Food Safety Program | Rob Siler | Amanda Coulombe | Relaunch | 24 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | #N/A
1245 | Peet's Coffee & Tea | Peet's Coffee & Tea Food Safety Evaluations | Keith Woith | Amanda Coulombe | Relaunch | 24 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | 51
1246 | Philz Coffee | Phil Coffee Food Safety Program | Rob Siler | Amanda Coulombe | Relaunch | 24 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | 191
1247 | Piada Group | Piada Group Food Safety Program | John Bestler | Emily Naufel | Relaunch | 40 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | 96
1248 | Pizza Ranch | Pizza Ranch Food Safety Program | Justin Prestinario | Eric Hightower | Relaunch | 24 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | 58
1249 | Pizzeria Locale | Pizzeria Locale FS Program (Chipotle Subsidiary) | Keith Woith | Amanda Coulombe | Relaunch | 32 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | #N/A
1250 | Potbelly's | Potbelly's Food Safety Program | John Bestler | Amanda Coulombe | Relaunch | 24 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | 33
1251 | Pret A Manger | Pret A Manger Food Safety Program | Brian Nolan | Steve Steinberg | Relaunch | 80 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | 64
1252 | Quorum | Quorum Food Safety Program | Keith Woith | Eric Hightower | Relaunch | 24 |  |  | 2018-01-01 | 2018-01-01 | N |  | 7/18 - AT note from 2018 file, ref #s only; | 187
1253 | RaceTrac | RaceTrac Food Safety Evaluations | Brian Nolan | Emily Naufel | Relaunch | 24 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | 34
1254 | Real Mex | Real Mex Food Safety Program | Keith Woith | Amanda Coulombe | Relaunch | 24 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | 60
1255 | Red Robin | Red Robin Food Safety Program | Keith Woith | Amanda Coulombe | Relaunch | 32 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | 219
1256 | Santiago's | Santiago's Food Safety Program | Rob Siler | Amanda Coulombe | Relaunch | 24 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | #N/A
1257 | Seaport Boston | Seaport Boston Food Safety Program | Brian Nolan | Steve Steinberg | Relaunch | 24 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | 160
1258 | Shake Shack | Shake Shack FS Program | Brian Nolan | Emily Naufel | Relaunch | 0 | - | 2018-01-01 | 2018-01-01 | 2018-01-01 | Y |  | 7/20 - weekly A&A meeting, did not win contract | 105
1259 | Shopper Events LLC | Shopper Events Food Safety Program | Keith Woith | Steve Steinberg | Relaunch | 24 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | 45
1260 | SilverBirch Hotels | Silver Birch Food Safety Program | Justin Prestinario | Eric Hightower | Relaunch | 24 |  |  | 2018-01-01 | 2018-01-01 | N |  | 7/18 - AT note from 2018 file, ref #s only; | 167
1261 | Smokey Bones | Smokey Bones Food Safety Program | Rob Siler | Amanda Coulombe | Relaunch | 24 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | 219
1262 | Snooze | Snooze Food Safety Program | Keith Woith | Amanda Coulombe | Relaunch | 40 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | 112
1263 | Stanford University | Stanford Food Safety Program | Keith Woith | Eric Hightower | Relaunch | 24 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | 118
1264 | Stanford University | Stanford Workplace Safety Program | Keith Woith | Eric Hightower | Relaunch | 24 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | 118
1265 | Starbucks | Starbucks LIC Food Safety Program | Justin Prestinario | Tim Cassidy | Relaunch | 24 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | 1
1266 | Starbucks | Starbucks LIC Food Safety Program - French | Justin Prestinario | Tim Cassidy | Relaunch | 24 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | 1
1267 | Steak 'n Shake | Steak 'n Shake Food Safety Program | John Bestler | Tim Cassidy | Relaunch | 40 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | 24
1268 | Stripes | Stripes Food Safety Program | Michelle Hudson | Steve Steinberg | Relaunch | 24 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | 26
1269 | Stripes | Sunoco Food Safety Program (Part of Stripes) | Michelle Hudson | Steve Steinberg | Relaunch | 24 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | 26
1270 | Sunkist | Sunkist Retrieval | Keith Woith | Eric Hightower | Relaunch | 24 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | 82
1271 | Tavistock | Tavistock Food Safety Program | Rob Siler | Amanda Coulombe | Relaunch | 24 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | #N/A
1272 | Texas Roadhouse | Texas Roadhouse FS & WPS Program | Brian Nolan | Amanda Coulombe | Relaunch | 40 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | 219
1273 | TGI Friday's | TGIF Food Safety Program | Michelle Hudson | Eric Hightower | Relaunch | 40 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | 17
1274 | TGI Friday's | TGIF Brand Standards Program | Michelle Hudson | Eric Hightower | Relaunch | 40 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | 17
1275 | The Pantry (Aunt M's) | The Pantry Food Safety | Rob Siler | Amanda Coulombe | Relaunch | 24 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | #N/A
1276 | The Procaccianti Group | TPG Food Safety Evaluations | Brian Nolan | Steve Steinberg | Relaunch | 24 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | 109
1277 | Travel Centers of America | Travel Centers of America Food Safety Evaluation | John Bestler | Eric Hightower | Relaunch | 24 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | 65
1278 | Tropical Smoothie Café | Tropical Smoothie Café Food Safety Program | Brian Nolan | Tim Cassidy | Relaunch | 40 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | 31
1279 | Trusthouse (Aladdin) | TrustHouse Food Safety Program | Brian Nolan | Eric Hightower | Relaunch | 24 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | 137
1280 | Twin Peaks | Twin Peaks Food Safety Program | Michelle Hudson | Eric Hightower | Relaunch | 80 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | 52
1281 | Unidine | Unidine Food Safety Program | Brian Nolan | Steve Steinberg | Relaunch | 24 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | 171
1282 | Verve Senior Living | Verve Senior Living Food Safety Program | Justin Prestinario | Steve Steinberg | Relaunch | 40 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | 92
1283 | White Lodging | White Lodging Food Safety Program | John Bestler | Amanda Coulombe | Relaunch | 24 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | 108
1284 | Wyndham Hotels | Wyndham Food Safety Program | Brian Nolan | Tim Cassidy | Relaunch | 24 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | 80
1285 | YUM! Brands | Pizza Hut - Co/FZ Program | Michelle Hudson | Emily Naufel | Relaunch | 120 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | 2
1286 | YUM! Brands | Pizza Hut - Co/Fr Operator App | Michelle Hudson | Emily Naufel | Relaunch | 24 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | 2
1287 | YUM! Brands | Pizza Hut - M Operator App | Michelle Hudson | Emily Naufel | Relaunch | 24 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | 2
1288 | YUM! Brands | Pizza Hut - LIC Program | Michelle Hudson | Emily Naufel | Relaunch | 40 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | 2
1289 | YUM! Brands | Pizza Hut - Maintenance Program | Michelle Hudson | Emily Naufel | Relaunch | 60 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | 2
1290 | YUM! Brands | Pizza Hut - Target Program | Michelle Hudson | Emily Naufel | Relaunch | 24 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | 2
1291 | YUM! Brands | Pizza Hut - Shed Program | Michelle Hudson | Emily Naufel | Relaunch | 24 |  |  | 2018-01-01 | 2018-01-01 | N |  | 7/18 - AT note from 2018 file, this is tentitive--may be removing this form in 2018; | 2
1292 | Z Foods | Z Foods Food Safety Program | Brian Nolan | Amanda Coulombe | Relaunch | 24 |  |  | 2018-01-01 | 2018-01-01 | N |  |  | 602
1293 | State of NC | State of NC Food Safety Program | Rob Siler | Amanda Coulombe | New Launch | 24 |  |  | 2018-01-03 | 2018-01-03 | N |  |  | #N/A
1294 | WingStop | Wingstop Food Safety Program | Rob Siler | Amanda Coulombe | New Launch | 24 |  |  | 2018-01-03 | 2018-01-03 | N |  |  | 159
1295 | WingStop | Wingstop Brand Standards Program | Rob Siler | Amanda Coulombe | New Launch | 24 |  |  | 2018-01-03 | 2018-01-03 | N |  |  | 159
1296 | Mimi's Café | Mimi's Café Food Safety Program | Michelle Hudson | Tim Cassidy | Relaunch | 24 |  |  | 2018-01-09 | 2018-01-09 | N |  |  | 75
1297 | Taco Mac | Taco Mac Food Safety Program | Rob Siler | Emily Naufel | Relaunch | 24 |  |  | 2018-01-09 | 2018-01-09 | N |  |  | 85
1298 | DineEquity | IHOP Egg Reaudit | Keith Woith | Steve Steinberg | Relaunch | 40 |  |  | 2018-01-12 | 2018-01-12 | N |  |  | 5
1299 | DineEquity | Applebee's eCaPS Program | Keith Woith | Steve Steinberg | Relaunch | 40 |  |  | 2018-01-12 | 2018-01-12 | N |  |  | 5
1300 | DineEquity | Water Filtration Program | Keith Woith | Steve Steinberg | Relaunch | 40 |  |  | 2018-01-12 | 2018-01-12 | N |  |  | 5
1301 | DineEquity | IHOP OAR Program - Spanish | Keith Woith | Steve Steinberg | Relaunch | 40 |  |  | 2018-01-12 | 2018-01-12 | N |  |  | 5
1302 | DineEquity | Applebee's eCaPS Program - Spanish | Keith Woith | Steve Steinberg | Relaunch | 40 |  |  | 2018-01-12 | 2018-01-12 | N |  |  | 5
1303 | DineEquity | IHOP OAR Program | Keith Woith | Steve Steinberg | Relaunch | 40 |  |  | 2018-01-12 | 2018-01-12 | N |  |  | 5
1304 | DineEquity | Transportation Audit | Keith Woith | Steve Steinberg | Relaunch | 40 |  |  | 2018-01-12 | 2018-01-12 | N |  |  | 5
1305 | Popeye's | Popeyes Franchisee Food Safety Program | Rob Siler | Emily Naufel | Relaunch | 100 |  |  | 2018-01-13 | 2018-01-13 | N |  |  | 12
1306 | CKE | CKE Food Safety | John Bestler | Amanda Coulombe | Relaunch | 40 |  |  | 2018-01-15 | 2018-01-15 | N |  |  | 4
1307 | CKE | CKE Playground Program | John Bestler | Amanda Coulombe | Relaunch | 40 |  |  | 2018-01-15 | 2018-01-15 | N |  |  | 4
1308 | CKE | CKE Workplace Safety | John Bestler | Amanda Coulombe | Relaunch | 40 |  |  | 2018-01-15 | 2018-01-15 | N |  |  | 4
1309 | CKE | CKE Mexico | John Bestler | Amanda Coulombe | Relaunch | 40 |  |  | 2018-01-15 | 2018-01-15 | N |  |  | 4
1310 | CKE | CKE Brand Standards | John Bestler | Amanda Coulombe | Relaunch | 40 |  |  | 2018-01-15 | 2018-01-15 | N |  |  | 4
1311 | Bass Pro Shop | Bass Pro 2009 Food Safety Evaluations | John Bestler | Amanda Coulombe | Relaunch | 24 |  |  | 2018-02-01 | 2018-02-01 | N |  |  | 76
1312 | Cotton Patch Café | Cotton Patch Café Food Safety Program | Michelle Hudson | Emily Naufel | Relaunch | 24 |  |  | 2018-02-01 | 2018-02-01 | N |  |  | 97
1313 | Fresh Ideas | Fresh Ideas Food Safety Program | Rob Siler | Amanda Coulombe | Relaunch | 24 |  |  | 2018-02-01 | 2018-02-01 | N |  |  | #N/A
1314 | Honeybaked Ham | Honeybaked Ham Food Safety Program | Rob Siler | Emily Naufel | Relaunch | 80 |  |  | 2018-02-01 | 2018-02-01 | N |  |  | 37
1315 | LaRosa's | LaRosa's Food Safety Program | John Bestler | Steve Steinberg | Relaunch | 24 |  |  | 2018-02-01 | 2018-02-01 | N |  |  | 87
1316 | Metz & Associates | Metz Culinary Management | Brian Nolan | Amanda Coulombe | Relaunch | 24 |  |  | 2018-02-01 | 2018-02-01 | N |  |  | 59
1317 | Pinnacle Entertainment Group | Pinnacle Casino Food Safety Program | Keith Woith | Emily Naufel | Relaunch | 40 |  |  | 2018-02-01 | 2018-02-01 | N |  |  | 73
1318 | Vi | Vi Food Safety Program | John Bestler | Amanda Coulombe | Relaunch | 24 |  |  | 2018-02-01 | 2018-02-01 | N |  |  | 101
1319 | Vi | Vi Beverage Program | John Bestler | Amanda Coulombe | Relaunch | 24 |  |  | 2018-02-01 | 2018-02-01 | N |  |  | 101
1320 | Willow Valley Resort | Willow Valley Food Safety Program | Brian Nolan | Steve Steinberg | Relaunch | 24 |  |  | 2018-02-01 | 2018-02-01 | N |  |  | 146
1321 | Brookdale | Brookdale Senior Living Program | John Bestler | Steve Steinberg | Relaunch | 40 |  |  | 2018-03-01 | 2018-03-01 | N |  |  | 7
1322 | Hyatt Hotels | Hyatt Food Safety Program | John Bestler | Steve Steinberg | Relaunch | 40 |  |  | 2018-03-01 | 2018-03-01 | N |  |  | 53
1323 | Ocean Properties | Ocean Properties Food Safety Program | John Bestler | Steve Steinberg | Relaunch | 40 |  |  | 2018-03-01 | 2018-03-01 | N |  |  | 86
1324 | Peter Piper Pizza | Peter Piper Pizza Mexico Food Safety Audits | Keith Woith | Amanda Coulombe | Relaunch | 40 |  |  | 2018-03-01 | 2018-03-01 | N |  |  | 67
1325 | 85 ᵒC Café | 85 Degrees Celsius Café Food Safety Program | Keith Woith | Steve Steinberg | Relaunch | 24 |  |  | 2018-04-01 | 2018-04-01 | N |  |  | 98
1326 | Aramark | ARAMARK SAFE Food Safety Program | Brian Nolan | Amanda Coulombe | Relaunch | 80 |  |  | 2018-04-01 | 2018-04-01 | N |  |  | 16
1327 | Areas USA | Areas USA Food Safety Program | John Bestler | Steve Steinberg | Relaunch | 80 |  |  | 2018-04-01 | 2018-04-01 | N |  |  | 93
1328 | Benihana | Benihana Food Safety Program | Rob Siler | Steve Steinberg | Relaunch | 32 |  |  | 2018-04-01 | 2018-04-01 | N |  |  | 49
1329 | Bento Sushi | Bento Sushi Factory Program | Justin Prestinario | Amanda Coulombe | Relaunch | 40 |  |  | 2018-04-01 | 2018-04-01 | N |  |  | 61
1330 | Bento Sushi | Bento Sushi Kiosk Program | Justin Prestinario | Amanda Coulombe | Relaunch | 40 |  |  | 2018-04-01 | 2018-04-01 | N |  |  | 61
1331 | Burger King | Burger King Playground Inspection Program | John Bestler | Steve Steinberg | Relaunch | 80 |  |  | 2018-04-01 | 2018-04-01 | N |  |  | 20
1332 | Chipotle | Chipotle Food Safety Program | Keith Woith | Amanda Coulombe | Relaunch | 32 |  |  | 2018-04-01 | 2018-04-01 | N |  |  | 6
1333 | ClubCorp | Club Corp Food Safety | Michelle Hudson | Emily Naufel | Relaunch | 24 |  |  | 2018-04-01 | 2018-04-01 | N |  |  | 63
1334 | Dairy Queen | Dairy Queen Pride Program | Justin Prestinario | Amanda Coulombe | Relaunch | 24 |  |  | 2018-04-01 | 2018-04-01 | N |  |  | 8
1335 | Delaware North | Delaware North Food Safety Program | Brian Nolan | Steve Steinberg | Relaunch | 24 |  |  | 2018-04-01 | 2018-04-01 | N |  |  | 94
1336 | Golden Corral | Golden Corral Food Safety | Brian Nolan | Emily Naufel | Relaunch | 24 |  |  | 2018-04-01 | 2018-04-01 | N |  |  | 21
1337 | Hard Rock Café | Hard Rock Café Food Safety Program | John Bestler | Amanda Coulombe | Relaunch | 24 |  |  | 2018-04-01 | 2018-04-01 | N |  |  | 36
1338 | Jackson's | Jacksons Food Safety Program | Keith Woith | Amanda Coulombe | Relaunch | 40 |  |  | 2018-04-01 | 2018-04-01 | N |  |  | 71
1339 | Medieval Times | Medieval Times Food Safety Program | Michelle Hudson | Amanda Coulombe | Relaunch | 24 |  |  | 2018-04-01 | 2018-04-01 | N |  |  | 153
1340 | Mimi's Café | Mimi's Café Food Safety Program | Michelle Hudson | Tim Cassidy | Relaunch | 24 |  |  | 2018-04-01 | 2018-04-01 | N |  |  | 75
1341 | Newk's | Newks Food Safety Program | Michelle Hudson | Steve Steinberg | Relaunch | 40 |  |  | 2018-04-01 | 2018-04-01 | N |  |  | 69
1342 | Pizzeria Locale | Pizzeria Locale FS Program (Chipotle Subsidiary) | Keith Woith | Amanda Coulombe | Relaunch | 32 |  |  | 2018-04-01 | 2018-04-01 | N |  |  | #N/A
1343 | Pret A Manger | Pret A Manger Food Safety Program | Brian Nolan | Steve Steinberg | Relaunch | 80 |  |  | 2018-04-01 | 2018-04-01 | N |  |  | 64
1344 | RaceTrac | RaceTrac Food Safety Evaluations | Brian Nolan | Emily Naufel | Relaunch | 24 |  |  | 2018-04-01 | 2018-04-01 | N |  |  | 34
1345 | Real Mex | Real Mex Food Safety Program | Keith Woith | Amanda Coulombe | Relaunch | 24 |  |  | 2018-04-01 | 2018-04-01 | N |  |  | 60
1346 | Red Robin | Red Robin Food Safety Program | Keith Woith | Amanda Coulombe | Relaunch | 32 |  |  | 2018-04-01 | 2018-04-01 | N |  |  | 219
1347 | Smokey Bones | Smokey Bones Food Safety Program | Rob Siler | Amanda Coulombe | Relaunch | 24 |  |  | 2018-04-01 | 2018-04-01 | N |  |  | 219
1348 | Snooze | Snooze Food Safety Program | Keith Woith | Amanda Coulombe | Relaunch | 40 |  |  | 2018-04-01 | 2018-04-01 | N |  |  | 112
1349 | Starbucks | Starbucks Company Food Safety Program | Justin Prestinario | Tim Cassidy | Relaunch | 24 |  |  | 2018-04-01 | 2018-04-01 | N |  |  | 1
1350 | Starbucks | Starbucks Company Food Safety Program - French | Justin Prestinario | Tim Cassidy | Relaunch | 24 |  |  | 2018-04-01 | 2018-04-01 | N |  |  | 1
1351 | Starbucks | Starbucks Facilities Program | Justin Prestinario | Tim Cassidy | Relaunch | 24 |  |  | 2018-04-01 | 2018-04-01 | N |  |  | 1
1352 | Starbucks | Starbucks Facilities Program - French | Justin Prestinario | Tim Cassidy | Relaunch | 24 |  |  | 2018-04-01 | 2018-04-01 | N |  |  | 1
1353 | Steak 'n Shake | Steak 'n Shake Food Safety Program | John Bestler | Tim Cassidy | Relaunch | 40 |  |  | 2018-04-01 | 2018-04-01 | N |  |  | 24
1354 | Stripes | Stripes Food Safety Program | Michelle Hudson | Steve Steinberg | Relaunch | 24 |  |  | 2018-04-01 | 2018-04-01 | N |  |  | 26
1355 | Stripes | Sunoco Food Safety Program (Part of Stripes) | Michelle Hudson | Steve Steinberg | Relaunch | 24 |  |  | 2018-04-01 | 2018-04-01 | N |  |  | 26
1356 | Texas Roadhouse | Texas Roadhouse FS & WPS Program | Brian Nolan | Amanda Coulombe | Relaunch | 40 |  |  | 2018-04-01 | 2018-04-01 | N |  |  | 219
1357 | TGI Friday's | TGIF Brand Standards Program | Michelle Hudson | Eric Hightower | Relaunch | 40 |  |  | 2018-04-01 | 2018-04-01 | N |  |  | 17
1358 | TGI Friday's | TGIF Food Safety Program | Michelle Hudson | Eric Hightower | Relaunch | 40 |  |  | 2018-04-01 | 2018-04-01 | N |  |  | 17
1359 | Buffalo Wild Wings | Buffalo Wild Wings - CO & Franchise Food Safety Program | Justin Prestinario | Emily Naufel | Relaunch | 24 |  |  | 2018-05-01 | 2018-05-01 | N |  |  | 15
1360 | Chick-fil-A | Chick-fil-A Dallas Special Study | Rob Siler | Emily Naufel | Relaunch | 24 |  |  | 2018-05-01 | 2018-05-01 | N |  |  | 44
1361 | Corner Bakery | Corner Bakery Food Safery Program | Rob Siler | Amanda Coulombe | Relaunch | 24 |  |  | 2018-05-01 | 2018-05-01 | N |  |  | #N/A
1362 | Corner Store | Corner Store Food Safety Program | Michelle Hudson | Steve Steinberg | Relaunch | 24 |  |  | 2018-05-01 | 2018-05-01 | N |  |  | 27
1363 | DineEquity | Water Filtration Program | Keith Woith | Steve Steinberg | Relaunch | 40 |  |  | 2018-05-01 | 2018-05-01 | N |  |  | 5
1364 | DineEquity | IHOP Egg Reaudit | Keith Woith | Steve Steinberg | Relaunch | 40 |  |  | 2018-05-01 | 2018-05-01 | N |  |  | 5
1365 | DineEquity | IHOP OAR Program | Keith Woith | Steve Steinberg | Relaunch | 40 |  |  | 2018-05-01 | 2018-05-01 | N |  |  | 5
1366 | DineEquity | IHOP OAR Program - Spanish | Keith Woith | Steve Steinberg | Relaunch | 40 |  |  | 2018-05-01 | 2018-05-01 | N |  |  | 5
1367 | Hooters of America | Hooters Food Safety Program | Rob Siler | Emily Naufel | Relaunch | 24 |  |  | 2018-05-01 | 2018-05-01 | N |  |  | 30
1368 | Ocean Properties | Ocean Properties Food Safety Program | John Bestler | Steve Steinberg | Relaunch | 40 |  |  | 2018-05-01 | 2018-05-01 | N |  |  | 86
1369 | Tavistock | Tavistock Food Safety Program | Rob Siler | Amanda Coulombe | Relaunch | 24 |  |  | 2018-05-01 | 2018-05-01 | N |  |  | #N/A
1370 | YUM! Brands | Pizza Hut - Co/FZ Program | Michelle Hudson | Emily Naufel | Relaunch | 120 |  |  | 2018-05-01 | 2018-05-01 | N |  |  | 2
1371 | YUM! Brands | Pizza Hut - Co/Fr Operator App | Michelle Hudson | Emily Naufel | Relaunch | 24 |  |  | 2018-05-01 | 2018-05-01 | N |  |  | 2
1372 | YUM! Brands | Pizza Hut - M Operator App | Michelle Hudson | Emily Naufel | Relaunch | 24 |  |  | 2018-05-01 | 2018-05-01 | N |  |  | 2
1373 | YUM! Brands | Pizza Hut - LIC Program | Michelle Hudson | Emily Naufel | Relaunch | 40 |  |  | 2018-05-01 | 2018-05-01 | N |  |  | 2
1374 | YUM! Brands | Pizza Hut - Maintenance Program | Michelle Hudson | Emily Naufel | Relaunch | 60 |  |  | 2018-05-01 | 2018-05-01 | N |  |  | 2
1375 | YUM! Brands | Pizza Hut - Target Program | Michelle Hudson | Emily Naufel | Relaunch | 24 |  |  | 2018-05-01 | 2018-05-01 | N |  |  | 2
1376 | YUM! Brands | Pizza Hut - Shed Program | Michelle Hudson | Emily Naufel | Relaunch | 24 |  |  | 2018-05-01 | 2018-05-01 | N |  | 7/18 - AT note from 2018 file, this is tentitive--may be removing this form in 2018; | 2
1377 | CKE | CKE Food Safety | John Bestler | Amanda Coulombe | Relaunch | 40 |  |  | 2018-05-15 | 2018-05-15 | N |  |  | 4
1378 | CKE | CKE Playground Program | John Bestler | Amanda Coulombe | Relaunch | 40 |  |  | 2018-05-15 | 2018-05-15 | N |  |  | 4
1379 | CKE | CKE Workplace Safety | John Bestler | Amanda Coulombe | Relaunch | 40 |  |  | 2018-05-15 | 2018-05-15 | N |  |  | 4
1380 | CKE | CKE Brand Standards | John Bestler | Amanda Coulombe | Relaunch | 40 |  |  | 2018-05-15 | 2018-05-15 | N |  |  | 4
1381 | Popeye's | Popeyes Food Safety Excellence Program | Rob Siler | Emily Naufel | Relaunch | 100 |  |  | 2018-05-15 | 2018-05-15 | N |  |  | 12
1382 | Darden Franchise Group | Darden Franchise Group Food Safety Program | Rob Siler | Amanda Coulombe | Relaunch | 32 |  |  | 2018-05-25 | 2018-05-25 | N |  |  | 185
1383 | Red Lobster | Red Lobster Food Safety Program | John Bestler | Amanda Coulombe | Relaunch | 24 |  |  | 2018-05-25 | 2018-05-25 | N |  |  | 23
1384 | Academia Barilla | Academia Barilla Food Safety | John Bestler | Steve Steinberg | Relaunch | 24 |  |  | 2018-06-01 | 2018-06-01 | N |  |  | 157
1385 | Atrium Hospitality | Atrium Hospitality Food Safety Program | Justin Prestinario | Tim Cassidy | Relaunch | 24 |  |  | 2018-06-01 | 2018-06-01 | N |  |  | 174
1386 | Atrium Hospitality | Atrium Hospitality Guest Experience Program | Justin Prestinario | Tim Cassidy | Relaunch | 24 |  |  | 2018-06-01 | 2018-06-01 | N |  |  | 174
1387 | Desert Island Properties | Desert Island Food Safety Program | Keith Woith | Steve Steinberg | Relaunch | 24 |  |  | 2018-06-01 | 2018-06-01 | N |  |  | 120
1388 | DineEquity | Applebee's eCaPS Program | Keith Woith | Steve Steinberg | Relaunch | 40 |  |  | 2018-06-01 | 2018-06-01 | N |  |  | 5
1389 | DineEquity | Applebee's eCaPS Program - Spanish | Keith Woith | Steve Steinberg | Relaunch | 40 |  |  | 2018-06-01 | 2018-06-01 | N |  |  | 5
1390 | Donovan's Steak & Chop House | Donovan's Food Safety Program | Keith Woith | Steve Steinberg | Relaunch | 24 |  |  | 2018-06-01 | 2018-06-01 | N |  |  | 161
1391 | Pret A Manger | Pret A Manger Food Safety Program | Brian Nolan | Steve Steinberg | Relaunch | 80 |  |  | 2018-06-01 | 2018-06-01 | N |  |  | 64
1392 | 4 Rivers Smokehouse | 4 Rivers Smokehouse Food Safety Evaluation | Rob Siler | Amanda Coulombe | Relaunch | 24 |  |  | 2018-07-01 | 2018-07-01 | N |  |  | 144
1393 | 85 ᵒC Café | 85 Degrees Celsius Café Food Safety Program | Keith Woith | Steve Steinberg | Relaunch | 24 |  |  | 2018-07-01 | 2018-07-01 | N |  |  | 98
1394 | Aramark | ARAMARK SAFE Food Safety Program | Brian Nolan | Amanda Coulombe | Relaunch | 80 |  |  | 2018-07-01 | 2018-07-01 | N |  |  | 16
1395 | Areas USA | Areas USA Food Safety Program | John Bestler | Steve Steinberg | Relaunch | 80 |  |  | 2018-07-01 | 2018-07-01 | N |  |  | 93
1396 | Avendra Hospitality | Avendra Hospitality Food Safety Program | Brian Nolan | Amanda Coulombe | Relaunch | 24 |  |  | 2018-07-01 | 2018-07-01 | N |  |  | 74
1397 | Benihana | Benihana Food Safety Program | Rob Siler | Steve Steinberg | Relaunch | 32 |  |  | 2018-07-01 | 2018-07-01 | N |  |  | 49
1398 | Bento Sushi | Bento Sushi Factory Program | Justin Prestinario | Amanda Coulombe | Relaunch | 40 |  |  | 2018-07-01 | 2018-07-01 | N |  |  | 61
1399 | Bento Sushi | Bento Sushi Kiosk Program | Justin Prestinario | Amanda Coulombe | Relaunch | 40 |  |  | 2018-07-01 | 2018-07-01 | N |  |  | 61
1400 | Bloomin' Brands | Bloomin Brands Food Safety Program | Rob Siler | Steve Steinberg | Relaunch | 24 |  |  | 2018-07-01 | 2018-07-01 | N |  |  | 13
1401 | Brookdale | Brookdale Senior Living Program | John Bestler | Steve Steinberg | Relaunch | 40 |  |  | 2018-07-01 | 2018-07-01 | N |  |  | 7
1402 | Burger King | Burger King Playground Inspection Program | John Bestler | Steve Steinberg | Relaunch | 80 |  |  | 2018-07-01 | 2018-07-01 | N |  |  | 20
1403 | CERCA TROVA | CERCA TROVA Food Safety Program | Keith Woith | Steve Steinberg | Relaunch | 32 |  |  | 2018-07-01 | 2018-07-01 | N |  |  | 84
1404 | Checkers | Checkers Food Safety Program | Rob Siler | Steve Steinberg | Relaunch | 24 |  |  | 2018-07-01 | 2018-07-01 | N |  |  | 22
1405 | Checkers | Checkers Food Safety Evaluation - Training Form | Rob Siler | Steve Steinberg | Relaunch | 24 |  |  | 2018-07-01 | 2018-07-01 | N |  |  | 22
1406 | Checkers | Checkers Marketing Audit | Rob Siler | Steve Steinberg | Relaunch | 24 |  |  | 2018-07-01 | 2018-07-01 | N |  |  | 22
1407 | Checkers | Checkers Brand Standards Audit | Rob Siler | Steve Steinberg | Relaunch | 24 |  |  | 2018-07-01 | 2018-07-01 | N |  |  | 22
1408 | Cheddar's | Cheddar's Casual Cafe Food Safety Evaluations | Michelle Hudson | Emily Naufel | Relaunch | 24 |  |  | 2018-07-01 | 2018-07-01 | N |  | 7/18 - AT note from 2018 file, this customer is now on Amanda's team; | 39
1409 | Chipotle | Chipotle Food Safety Program | Keith Woith | Amanda Coulombe | Relaunch | 32 |  |  | 2018-07-01 | 2018-07-01 | N |  |  | 6
1410 | Cinemark | Cinemark Food Safety Program | Michelle Hudson | Tim Cassidy | Relaunch | 24 |  |  | 2018-07-01 | 2018-07-01 | N |  |  | 29
1411 | Cinemark | Cinemark Brand Standards Program | Michelle Hudson | Tim Cassidy | Relaunch | 24 |  |  | 2018-07-01 | 2018-07-01 | N |  |  | 29
1412 | Dairy Queen | Dairy Queen Pride Program | Justin Prestinario | Amanda Coulombe | Relaunch | 24 |  |  | 2018-07-01 | 2018-07-01 | N |  |  | 8
1413 | Delaware North | Delaware North Food Safety Program | Brian Nolan | Steve Steinberg | Relaunch | 24 |  |  | 2018-07-01 | 2018-07-01 | N |  |  | 94
1414 | eatsa | eatsa Food Safety Program | Keith Woith | Steve Steinberg | Relaunch | 32 |  |  | 2018-07-01 | 2018-07-01 | N |  |  | #N/A
1415 | Friendly's | Friendly's Food Safety Program | Brian Nolan | Emily Naufel | Relaunch | 40 |  |  | 2018-07-01 | 2018-07-01 | N |  |  | 41
1416 | Glory Days | Glory Days Food Safety | Brian Nolan | Amanda Coulombe | Relaunch | 24 |  |  | 2018-07-01 | 2018-07-01 | N |  |  | 99
1417 | Golden Corral | Golden Corral Food Safety | Brian Nolan | Emily Naufel | Relaunch | 24 |  |  | 2018-07-01 | 2018-07-01 | N |  |  | 21
1418 | Guckenheimer | Guckenheimer Food Safety & Workplace Safety Program | Keith Woith | Emily Naufel | Relaunch | 40 |  |  | 2018-07-01 | 2018-07-01 | N |  |  | 42
1419 | Hard Rock Café | Hard Rock Café Food Safety Program | John Bestler | Amanda Coulombe | Relaunch | 24 |  |  | 2018-07-01 | 2018-07-01 | N |  |  | 36
1420 | Ignite Restaurants | Ignite Food Safety Evaluation Program | Michelle Hudson | Amanda Coulombe | Relaunch | 40 |  |  | 2018-07-01 | 2018-07-01 | N |  |  | 54
1421 | Jackson's | Jacksons Food Safety Program | Keith Woith | Amanda Coulombe | Relaunch | 40 |  |  | 2018-07-01 | 2018-07-01 | N |  |  | 71
1422 | Kendall Senior Living | Kendal Senior Living Workplace Safety Program | Brian Nolan | Amanda Coulombe | Relaunch | 40 |  |  | 2018-07-01 | 2018-07-01 | N |  |  | 140
1423 | Kendall Senior Living | Kendal Senior Living Food Safety Program | Brian Nolan | Amanda Coulombe | Relaunch | 40 |  |  | 2018-07-01 | 2018-07-01 | N |  |  | 140
1424 | LaRosa's | LaRosa's Food Safety Program | John Bestler | Steve Steinberg | Relaunch | 24 |  |  | 2018-07-01 | 2018-07-01 | N |  |  | 87
1425 | Lazy Dog Café | Lazy Dog Cafe Food Safety Program | Division | Steve Steinberg | Relaunch | 24 |  |  | 2018-07-01 | 2018-07-01 | N |  |  | 83
1426 | Luna Grill | Luna Grill Food Safety Program | Keith Woith | Emily Naufel | Relaunch | 32 |  |  | 2018-07-01 | 2018-07-01 | N |  |  | 90
1427 | Macaroni Grill | MacGrill Food Safety Program | Michelle Hudson | Amanda Coulombe | Relaunch | 40 |  |  | 2018-07-01 | 2018-07-01 | N |  |  | 62
1428 | Margaritaville | Margaritaville Food Safety Program | Rob Siler | Amanda Coulombe | Relaunch | 24 |  |  | 2018-07-01 | 2018-07-01 | N |  |  | 103
1429 | Max Restaurant Group | Max Restaurant Group 2008 Food Safety Evaluation | Brian Nolan | Amanda Coulombe | Relaunch | 24 |  |  | 2018-07-01 | 2018-07-01 | N |  |  | 113
1430 | Mimi's Café | Mimi's Café Food Safety Program | Michelle Hudson | Tim Cassidy | Relaunch | 24 |  |  | 2018-07-01 | 2018-07-01 | N |  |  | 75
1431 | Noodle's | Noodles Food Safety Program | Rob Siler | Amanda Coulombe | Relaunch | 24 |  |  | 2018-07-01 | 2018-07-01 | N |  |  | 32
1432 | Noodle's | Noodles Self-Assessment Program | Rob Siler | Amanda Coulombe | Relaunch | 24 |  |  | 2018-07-01 | 2018-07-01 | N |  |  | 32
1433 | Olga's Kitchen | Olga's Kitchen Food Safety Program | John Bestler | Amanda Coulombe | Relaunch | 24 |  |  | 2018-07-01 | 2018-07-01 | N |  |  | 104
1434 | Omni Hotels | Omni Hotels Food Safety Program | Michelle Hudson | Tim Cassidy | Relaunch | 24 |  |  | 2018-07-01 | 2018-07-01 | N |  |  | 57
1435 | On The Border | On the Border Food Safety Program | Rob Siler | Amanda Coulombe | Relaunch | 24 |  |  | 2018-07-01 | 2018-07-01 | N |  |  | 46
1436 | Peet's Coffee & Tea | Peet's Coffee & Tea Food Safety Evaluations | Keith Woith | Amanda Coulombe | Relaunch | 24 |  |  | 2018-07-01 | 2018-07-01 | N |  |  | 51
1437 | Philz Coffee | Phil Coffee Food Safety Program | Rob Siler | Amanda Coulombe | Relaunch | 24 |  |  | 2018-07-01 | 2018-07-01 | N |  |  | 191
1438 | Pizzeria Locale | Pizzeria Locale FS Program (Chipotle Subsidiary) | Keith Woith | Amanda Coulombe | Relaunch | 32 |  |  | 2018-07-01 | 2018-07-01 | N |  |  | #N/A
1439 | Potbelly's | Potbelly's Food Safety Program | John Bestler | Amanda Coulombe | Relaunch | 24 |  |  | 2018-07-01 | 2018-07-01 | N |  |  | 33
1440 | RaceTrac | RaceTrac Food Safety Evaluations | Brian Nolan | Emily Naufel | Relaunch | 24 |  |  | 2018-07-01 | 2018-07-01 | N |  |  | 34
1441 | Real Mex | Real Mex Food Safety Program | Keith Woith | Amanda Coulombe | Relaunch | 24 |  |  | 2018-07-01 | 2018-07-01 | N |  |  | 60
1442 | Red Robin | Red Robin Food Safety Program | Keith Woith | Amanda Coulombe | Relaunch | 32 |  |  | 2018-07-01 | 2018-07-01 | N |  |  | 219
1443 | Seaport Boston | Seaport Boston Food Safety Program | Brian Nolan | Steve Steinberg | Relaunch | 24 |  |  | 2018-07-01 | 2018-07-01 | N |  |  | 160
1444 | Shopper Events LLC | Shopper Events Food Safety Program | Keith Woith | Steve Steinberg | Relaunch | 24 |  |  | 2018-07-01 | 2018-07-01 | N |  |  | 45
1445 | Smokey Bones | Smokey Bones Food Safety Program | Rob Siler | Amanda Coulombe | Relaunch | 24 |  |  | 2018-07-01 | 2018-07-01 | N |  |  | 219
1446 | Snooze | Snooze Food Safety Program | Keith Woith | Amanda Coulombe | Relaunch | 40 |  |  | 2018-07-01 | 2018-07-01 | N |  |  | 112
1447 | Starbucks | Starbucks LIC Food Safety Program | Justin Prestinario | Tim Cassidy | Relaunch | 24 |  |  | 2018-07-01 | 2018-07-01 | N |  |  | 1
1448 | Starbucks | Starbucks LIC Food Safety Program - French | Justin Prestinario | Tim Cassidy | Relaunch | 24 |  |  | 2018-07-01 | 2018-07-01 | N |  |  | 1
1449 | Steak 'n Shake | Steak 'n Shake Food Safety Program | John Bestler | Tim Cassidy | Relaunch | 40 |  |  | 2018-07-01 | 2018-07-01 | N |  |  | 24
1450 | Stripes | Stripes Food Safety Program | Michelle Hudson | Steve Steinberg | Relaunch | 24 |  |  | 2018-07-01 | 2018-07-01 | N |  |  | 26
1451 | Stripes | Sunoco Food Safety Program (Part of Stripes) | Michelle Hudson | Steve Steinberg | Relaunch | 24 |  |  | 2018-07-01 | 2018-07-01 | N |  |  | 26
1452 | Taco Mac | Taco Mac Food Safety Program | Rob Siler | Emily Naufel | Relaunch | 24 |  |  | 2018-07-01 | 2018-07-01 | N |  |  | 85
1453 | Texas Roadhouse | Texas Roadhouse FS & WPS Program | Brian Nolan | Amanda Coulombe | Relaunch | 40 |  |  | 2018-07-01 | 2018-07-01 | N |  |  | 219
1454 | TGI Friday's | TGIF Brand Standards Program | Michelle Hudson | Eric Hightower | Relaunch | 40 |  |  | 2018-07-01 | 2018-07-01 | N |  |  | 17
1455 | The Procaccianti Group | TPG Food Safety Evaluations | Brian Nolan | Steve Steinberg | Relaunch | 24 |  |  | 2018-07-01 | 2018-07-01 | N |  |  | 109
1456 | Tropical Smoothie Café | Tropical Smoothie Café Food Safety Program | Brian Nolan | Tim Cassidy | Relaunch | 40 |  |  | 2018-07-01 | 2018-07-01 | N |  |  | 31
1457 | Verve Senior Living | Verve Senior Living Food Safety Program | Justin Prestinario | Steve Steinberg | Relaunch | 40 |  |  | 2018-07-01 | 2018-07-01 | N |  |  | 92
1458 | Willow Valley Resort | Willow Valley Food Safety Program | Brian Nolan | Steve Steinberg | Relaunch | 24 |  |  | 2018-07-01 | 2018-07-01 | N |  |  | 146
1459 | Chick-fil-A | Chick-fil-A Catering Program | Rob Siler | Emily Naufel | Relaunch | 24 |  |  | 2018-08-01 | 2018-08-01 | N |  |  | 44
1460 | Chick-fil-A | Chick-fil-A CPE Program | Rob Siler | Emily Naufel | Relaunch | 24 |  |  | 2018-08-01 | 2018-08-01 | N |  |  | 44
1461 | Greenville School System | Greenville Food Safety Program | Rob Siler | Amanda Coulombe | Relaunch | 24 |  |  | 2018-08-01 | 2018-08-01 | N |  |  | 79
1462 | Interstate Hotels and Resorts | Interstate Beverage Program | Brian Nolan | Eric Hightower | Relaunch | 40 |  |  | 2018-08-01 | 2018-08-01 | N |  |  | 48
1463 | Interstate Hotels and Resorts | Interstate Food Safety Program | Brian Nolan | Eric Hightower | Relaunch | 40 |  |  | 2018-08-01 | 2018-08-01 | N |  |  | 48
1464 | Peter Piper Pizza | Peter Piper Pizza Mexico Food Safety Audits | Keith Woith | Amanda Coulombe | Relaunch | 40 |  |  | 2018-08-01 | 2018-08-01 | N |  |  | 67
1465 | Pinnacle Entertainment Group | Pinnacle Casino Food Safety Program | Keith Woith | Emily Naufel | Relaunch | 40 |  |  | 2018-08-01 | 2018-08-01 | N |  |  | 73
1466 | Stanford University | Stanford Food Safety Program | Keith Woith | Eric Hightower | Relaunch | 24 |  |  | 2018-08-01 | 2018-08-01 | N |  | 7/18 - AT note from 2018 file, likely won't need but will keep in for now; | 118
1467 | Stanford University | Stanford Workplace Safety Program | Keith Woith | Eric Hightower | Relaunch | 24 |  |  | 2018-08-01 | 2018-08-01 | N |  | 7/18 - AT note from 2018 file, likely won't need but will keep in for now; | 118
1468 | Bass Pro Shop | Bass Pro 2009 Food Safety Evaluations | John Bestler | Amanda Coulombe | Relaunch | 24 |  |  | 2018-09-01 | 2018-09-01 | N |  |  | 76
1469 | Buffalo Wild Wings | Buffalo Wild Wings - CO & Franchise Food Safety Program | Justin Prestinario | Emily Naufel | Relaunch | 24 |  |  | 2018-09-01 | 2018-09-01 | N |  |  | 15
1470 | Compass Group | Compass Workplace Safety Program #1 | Brian Nolan | Eric Hightower | Relaunch | 80 |  |  | 2018-09-01 | 2018-09-01 | N |  |  | 11
1471 | Compass Group | Compass Workplace Safety Program #2 | Brian Nolan | Eric Hightower | Relaunch | 80 |  |  | 2018-09-01 | 2018-09-01 | N |  |  | 11
1472 | Compass Group | Compass Workplace Safety Program #3 | Brian Nolan | Eric Hightower | Relaunch | 80 |  |  | 2018-09-01 | 2018-09-01 | N |  |  | 11
1473 | Compass Group | Compass Workplace Safety Program #4 | Brian Nolan | Eric Hightower | Relaunch | 80 |  |  | 2018-09-01 | 2018-09-01 | N |  |  | 11
1474 | Compass Group | Compass Workplace Safety Program #5 | Brian Nolan | Eric Hightower | Relaunch | 80 |  |  | 2018-09-01 | 2018-09-01 | N |  |  | 11
1475 | Compass Group | Compass Workplace Safety Program #6 | Brian Nolan | Eric Hightower | Relaunch | 80 |  |  | 2018-09-01 | 2018-09-01 | N |  |  | 11
1476 | Compass Group | Compass Workplace Safety Program #7 | Brian Nolan | Eric Hightower | Relaunch | 80 |  |  | 2018-09-01 | 2018-09-01 | N |  |  | 11
1477 | Compass Group | Compass Workplace Safety Program #8 | Brian Nolan | Eric Hightower | Relaunch | 80 |  |  | 2018-09-01 | 2018-09-01 | N |  |  | 11
1478 | Compass Group | Compass Food Safety Program | Brian Nolan | Eric Hightower | Relaunch | 80 |  |  | 2018-09-01 | 2018-09-01 | N |  |  | 11
1479 | Compass Group | Compass HD Program | Brian Nolan | Eric Hightower | Relaunch | 80 |  |  | 2018-09-01 | 2018-09-01 | N |  |  | 11
1480 | Compass Group | Compass J&W Program | Brian Nolan | Eric Hightower | Relaunch | 80 |  |  | 2018-09-01 | 2018-09-01 | N |  |  | 11
1481 | Compass Group | Compass Workplace Safety Program | Brian Nolan | Eric Hightower | Relaunch | 80 |  |  | 2018-09-01 | 2018-09-01 | N |  |  | 11
1482 | Corner Bakery | Corner Bakery Food Safery Program | Rob Siler | Amanda Coulombe | Relaunch | 24 |  |  | 2018-09-01 | 2018-09-01 | N |  |  | 40
1483 | Corner Store | Corner Store Food Safety Program | Michelle Hudson | Steve Steinberg | Relaunch | 24 |  |  | 2018-09-01 | 2018-09-01 | N |  |  | 27
1484 | DineEquity | Transportation Audit | Keith Woith | Steve Steinberg | Relaunch | 40 |  |  | 2018-09-01 | 2018-09-01 | N |  |  | 5
1485 | DineEquity | IHOP OAR Program | Keith Woith | Steve Steinberg | Relaunch | 40 |  |  | 2018-09-01 | 2018-09-01 | N |  |  | 5
1486 | DineEquity | IHOP OAR Program - Spanish | Keith Woith | Steve Steinberg | Relaunch | 40 |  |  | 2018-09-01 | 2018-09-01 | N |  |  | 5
1487 | DineEquity | IHOP Egg Reaudit | Keith Woith | Steve Steinberg | Relaunch | 40 |  |  | 2018-09-01 | 2018-09-01 | N |  |  | 5
1488 | DineEquity | Water Filtration Program | Keith Woith | Steve Steinberg | Relaunch | 40 |  |  | 2018-09-01 | 2018-09-01 | N |  |  | 5
1489 | Four Winds Casino | Four Winds Casino Food Safety Program | John Bestler | Steve Steinberg | Relaunch | 24 |  |  | 2018-09-01 | 2018-09-01 | N |  |  | 136
1490 | Fresh Ideas | Fresh Ideas Food Safety Program | Rob Siler | Amanda Coulombe | Relaunch | 24 |  |  | 2018-09-01 | 2018-09-01 | N |  |  | 135
1491 | Hooters of America | Hooters Food Safety Program | Rob Siler | Emily Naufel | Relaunch | 24 |  |  | 2018-09-01 | 2018-09-01 | N |  |  | 30
1492 | Metz & Associates | Metz Culinary Management | Brian Nolan | Amanda Coulombe | Relaunch | 24 |  |  | 2018-09-01 | 2018-09-01 | N |  |  | 59
1493 | Sodexo | Sodexo - Food Safety Canada (English Version) | Brian Nolan | Eric Hightower | Relaunch | 80 |  |  | 2018-09-01 | 2018-09-01 | N |  |  | 9
1494 | Sodexo | Sodexo - Food Safety Canada (French Version) | Brian Nolan | Eric Hightower | Relaunch | 80 |  |  | 2018-09-01 | 2018-09-01 | N |  |  | 9
1495 | Sodexo | Sodexo - Health & Safety Canada (English) | Brian Nolan | Eric Hightower | Relaunch | 80 |  |  | 2018-09-01 | 2018-09-01 | N |  |  | 9
1496 | Sodexo | Sodexo - Health & Safety Canada (French) | Brian Nolan | Eric Hightower | Relaunch | 80 |  |  | 2018-09-01 | 2018-09-01 | N |  |  | 9
1497 | Sodexo | Sodexo - Food Safety US | Brian Nolan | Eric Hightower | Relaunch | 80 |  |  | 2018-09-01 | 2018-09-01 | N |  |  | 9
1498 | Sodexo | Sodexo - Health & Safety Food Service US | Brian Nolan | Eric Hightower | Relaunch | 80 |  |  | 2018-09-01 | 2018-09-01 | N |  |  | 9
1499 | Tavistock | Tavistock Food Safety Program | Rob Siler | Amanda Coulombe | Relaunch | 24 |  |  | 2018-09-01 | 2018-09-01 | N |  |  | 106
1500 | YUM! Brands | Pizza Hut - Co/FZ Program | Michelle Hudson | Emily Naufel | Relaunch | 120 |  |  | 2018-09-01 | 2018-09-01 | N |  |  | 2
1501 | YUM! Brands | Pizza Hut - Co/Fr Operator App | Michelle Hudson | Emily Naufel | Relaunch | 24 |  |  | 2018-09-01 | 2018-09-01 | N |  |  | 2
1502 | YUM! Brands | Pizza Hut - M Operator App | Michelle Hudson | Emily Naufel | Relaunch | 24 |  |  | 2018-09-01 | 2018-09-01 | N |  |  | 2
1503 | YUM! Brands | Pizza Hut - LIC Program | Michelle Hudson | Emily Naufel | Relaunch | 40 |  |  | 2018-09-01 | 2018-09-01 | N |  |  | 2
1504 | YUM! Brands | Pizza Hut - Maintenance Program | Michelle Hudson | Emily Naufel | Relaunch | 60 |  |  | 2018-09-01 | 2018-09-01 | N |  |  | 2
1505 | YUM! Brands | Pizza Hut - Target Program | Michelle Hudson | Emily Naufel | Relaunch | 24 |  |  | 2018-09-01 | 2018-09-01 | N |  |  | 2
1506 | YUM! Brands | Pizza Hut - Shed Program | Michelle Hudson | Emily Naufel | Relaunch | 24 |  |  | 2018-09-01 | 2018-09-01 | N |  | 7/18 - AT note from 2018 file, this is tentitive--may be removing this form in 2018; | 2
1507 | Popeye's | Popeyes Food Safety Excellence Program | Rob Siler | Emily Naufel | Relaunch | 100 |  |  | 2018-09-04 | 2018-09-04 | N |  |  | 12
1508 | Popeye's | Popeyes Food Safety Program | Rob Siler | Emily Naufel | Relaunch | 100 |  |  | 2018-09-04 | 2018-09-04 | N |  |  | 12
1509 | CKE | CKE Food Safety | John Bestler | Amanda Coulombe | Relaunch | 40 |  |  | 2018-09-10 | 2018-09-10 | N |  |  | 4
1510 | CKE | CKE Playground Program | John Bestler | Amanda Coulombe | Relaunch | 40 |  |  | 2018-09-10 | 2018-09-10 | N |  |  | 4
1511 | CKE | CKE Workplace Safety | John Bestler | Amanda Coulombe | Relaunch | 40 |  |  | 2018-09-10 | 2018-09-10 | N |  |  | 4
1512 | CKE | CKE Brand Standards | John Bestler | Amanda Coulombe | Relaunch | 40 |  |  | 2018-09-10 | 2018-09-10 | N |  |  | 4
1513 | 85 ᵒC Café | 85 Degrees Celsius Café Food Safety Program | Keith Woith | Steve Steinberg | Relaunch | 24 |  |  | 2018-10-01 | 2018-10-01 | N |  |  | 98
1514 | Aramark | ARAMARK SAFE Food Safety Program | Brian Nolan | Amanda Coulombe | Relaunch | 80 |  |  | 2018-10-01 | 2018-10-01 | N |  |  | 16
1515 | Areas USA | Areas USA Food Safety Program | John Bestler | Steve Steinberg | Relaunch | 80 |  |  | 2018-10-01 | 2018-10-01 | N |  |  | 93
1516 | Benihana | Benihana Food Safety Program | Rob Siler | Steve Steinberg | Relaunch | 32 |  |  | 2018-10-01 | 2018-10-01 | N |  |  | 49
1517 | Burger King | Burger King Playground Inspection Program | John Bestler | Steve Steinberg | Relaunch | 80 |  |  | 2018-10-01 | 2018-10-01 | N |  |  | 20
1518 | Chipotle | Chipotle Food Safety Program | Keith Woith | Amanda Coulombe | Relaunch | 32 |  |  | 2018-10-01 | 2018-10-01 | N |  |  | 6
1519 | Compass Group | Compass Canada English Form | Brian Nolan | Eric Hightower | Relaunch | 80 |  |  | 2018-10-01 | 2018-10-01 | N |  |  | 11
1520 | Compass Group | Compass Canada French Form | Brian Nolan | Eric Hightower | Relaunch | 80 |  |  | 2018-10-01 | 2018-10-01 | N |  |  | 11
1521 | Dairy Queen | Dairy Queen Pride Program | Justin Prestinario | Amanda Coulombe | Relaunch | 24 |  |  | 2018-10-01 | 2018-10-01 | N |  |  | 8
1522 | Hard Rock Café | Hard Rock Café Food Safety Program | John Bestler | Amanda Coulombe | Relaunch | 24 |  |  | 2018-10-01 | 2018-10-01 | N |  |  | 36
1523 | Hyatt Hotels | Hyatt Food Safety Program | John Bestler | Steve Steinberg | Relaunch | 40 |  |  | 2018-10-01 | 2018-10-01 | N |  |  | 53
1524 | Jackson's | Jacksons Food Safety Program | Keith Woith | Amanda Coulombe | Relaunch | 40 |  |  | 2018-10-01 | 2018-10-01 | N |  |  | 71
1525 | Mimi's Café | Mimi's Café Food Safety Program | Michelle Hudson | Tim Cassidy | Relaunch | 24 |  |  | 2018-10-01 | 2018-10-01 | N |  |  | 75
1526 | Newk's | Newks Food Safety Program | Michelle Hudson | Steve Steinberg | Relaunch | 40 |  |  | 2018-10-01 | 2018-10-01 | N |  |  | 69
1527 | Pizzeria Locale | Pizzeria Locale FS Program (Chipotle Subsidiary) | Keith Woith | Amanda Coulombe | Relaunch | 32 |  |  | 2018-10-01 | 2018-10-01 | N |  |  | #N/A
1528 | Pret A Manger | Pret A Manger Food Safety Program | Brian Nolan | Steve Steinberg | Relaunch | 80 |  |  | 2018-10-01 | 2018-10-01 | N |  |  | 64
1529 | RaceTrac | RaceTrac Food Safety Evaluations | Brian Nolan | Emily Naufel | Relaunch | 24 |  |  | 2018-10-01 | 2018-10-01 | N |  |  | 34
1530 | Real Mex | Real Mex Food Safety Program | Keith Woith | Amanda Coulombe | Relaunch | 24 |  |  | 2018-10-01 | 2018-10-01 | N |  |  | 60
1531 | Red Robin | Red Robin Food Safety Program | Keith Woith | Amanda Coulombe | Relaunch | 32 |  |  | 2018-10-01 | 2018-10-01 | N |  |  | 219
1532 | Shopper Events LLC | Shopper Events Food Safety Program | Keith Woith | Steve Steinberg | Relaunch | 24 |  |  | 2018-10-01 | 2018-10-01 | N |  |  | 45
1533 | Smokey Bones | Smokey Bones Food Safety Program | Rob Siler | Amanda Coulombe | Relaunch | 24 |  |  | 2018-10-01 | 2018-10-01 | N |  |  | 219
1534 | Snooze | Snooze Food Safety Program | Keith Woith | Amanda Coulombe | Relaunch | 40 |  |  | 2018-10-01 | 2018-10-01 | N |  |  | 112
1535 | Starbucks | Starbucks Company Food Safety Program | Justin Prestinario | Tim Cassidy | Relaunch | 24 |  |  | 2018-10-01 | 2018-10-01 | N |  |  | 1
1536 | Starbucks | Starbucks Company Food Safety Program - French | Justin Prestinario | Tim Cassidy | Relaunch | 24 |  |  | 2018-10-01 | 2018-10-01 | N |  |  | 1
1537 | Starbucks | Starbucks Facilities Program | Justin Prestinario | Tim Cassidy | Relaunch | 24 |  |  | 2018-10-01 | 2018-10-01 | N |  |  | 1
1538 | Starbucks | Starbucks Facilities Program - French | Justin Prestinario | Tim Cassidy | Relaunch | 24 |  |  | 2018-10-01 | 2018-10-01 | N |  |  | 1
1539 | Steak 'n Shake | Steak 'n Shake Food Safety Program | John Bestler | Tim Cassidy | Relaunch | 40 |  |  | 2018-10-01 | 2018-10-01 | N |  |  | 24
1540 | Stripes | Stripes Food Safety Program | Michelle Hudson | Steve Steinberg | Relaunch | 24 |  |  | 2018-10-01 | 2018-10-01 | N |  |  | 26
1541 | Stripes | Sunoco Food Safety Program (Part of Stripes) | Michelle Hudson | Steve Steinberg | Relaunch | 24 |  |  | 2018-10-01 | 2018-10-01 | N |  |  | 26
1542 | Texas Roadhouse | Texas Roadhouse FS & WPS Program | Brian Nolan | Amanda Coulombe | Relaunch | 40 |  |  | 2018-10-01 | 2018-10-01 | N |  |  | 219
1543 | TGI Friday's | TGIF Brand Standards Program | Michelle Hudson | Eric Hightower | Relaunch | 40 |  |  | 2018-10-01 | 2018-10-01 | N |  |  | 17
1544 | Honeybaked Ham | Honeybaked Ham Holiday Program - Food Safety Program | Rob Siler | Emily Naufel | Relaunch | 80 |  |  | 2018-11-01 | 2018-11-01 | N |  |  | 37
1545 | Honeybaked Ham | Honeybaked Ham Holiday Program - PopUp Retail | Rob Siler | Emily Naufel | Relaunch | 80 |  |  | 2018-11-01 | 2018-11-01 | N |  |  | 37
1546 | Darden Franchise Group | Darden Franchise Group Food Safety Program | Rob Siler | Amanda Coulombe | Relaunch | 32 |  |  | 2018-11-23 | 2018-11-23 | N |  |  | 185
1547 | Red Lobster | Red Lobster Food Safety Program | John Bestler | Amanda Coulombe | Relaunch | 24 |  |  | 2018-11-23 | 2018-11-23 | N |  |  | 23
Formulas:
MaxDate = MAX([TargetDate]:[ReqLaunchDate])
MaxDate = MAX([ReqLaunchDate]:[ReqLaunchDate])

## CustomerLaunchesByYear (hidden)
Hours | (Multiple Items)
Count of Program |  |  | Years2 | MaxDate
|  |  | 2015 | 2016 | 2017 | Grand Total
Customer | Sales | AcctManager |  |  |  |  | 2017 % of Annual FTE Capacity | Est. Cost | Cust. Revenue ($1,000's) | Cost / Revenue
4 Rivers Smokehouse | Rob Siler | Amanda Coulombe |  | 1 | 1 | 2 | 1.667% | 1050 | 9.425 | 11.14%
7-Eleven | Justin Prestinario | Amanda Coulombe | 1 |  |  | 1 | 0% | 0 | 0 | -
85 ᵒC Café | Keith Woith | Steve Steinberg | 1 | 2 | 1 | 4 | 1.667% | 1050 | 26.845 | 3.911%
Academia Barilla | John Bestler | Steve Steinberg |  | 1 | 1 | 2 | 1.667% | 1050 | 6.3 | 16.67%
Ace Restaurant Group | Brian Nolan | Eric Hightower | 1 | 1 |  | 2 | 0% | 0 | 0 | -
Adak Restaurants | John Bestler | Eric Hightower | 1 | 1 |  | 2 | 0% | 0 | 0 | -
Aramark | Brian Nolan | Amanda Coulombe | 1 | 4 | 4 | 9 | 6.667% | 4200 | 1002.9653 | 0.4188%
Arby's | Rob Siler | Amanda Coulombe | 1 | 1 | 2 | 4 | 3.333% | 2100 | 610.32 | 0.3441%
Areas USA | John Bestler | Steve Steinberg | 1 | 1 | 1 | 3 | 1.667% | 1050 | 35.24 | 2.98%
Au Bon Pain | Brian Nolan | Eric Hightower |  |  | 1 | 1 | 1.667% | 1050 | - | -
Avendra Hospitality | Brian Nolan | Amanda Coulombe |  | 1 | 1 | 2 | 1.667% | 1050 | 42.9986 | 2.442%
Bass Pro Shop | John Bestler | Amanda Coulombe | 1 | 1 | 2 | 4 | 3.333% | 2100 | 57.5289 | 3.65%
Batali & Bastianich Hospitality Group | Brian Nolan | Emily Naufel | 1 | 1 |  | 2 | 0% | 0 | 0 | -
Benihana | Rob Siler | Steve Steinberg |  |  | 2 | 2 | 3.333% | 2100 | - | -
Bento Sushi | Justin Prestinario | Amanda Coulombe |  |  | 3 | 3 | 5% | 3150 | 100 | 3.15%
Bloomin' Brands | Rob Siler | Steve Steinberg | 2 | 2 | 1 | 5 | 1.667% | 1050 | 1401.178 | 0.07494%
Brinker | Michelle Hudson | Steve Steinberg | 2 |  |  | 2 | 0% | 0 | 0 | -
Brookdale | John Bestler | Steve Steinberg | 3 | 2 | 1 | 6 | 1.667% | 1050 | 1657.098 | 0.06336%
Brookhaven | Brian Nolan | Amanda Coulombe | 1 |  |  | 1 | 0% | 0 | -1.1183 | 0%
Buffalo Wild Wings | Justin Prestinario | Emily Naufel | 4 | 4 | 3 | 11 | 5% | 3150 | 1046.1071 | 0.3011%
Burger King | John Bestler | Steve Steinberg | 3 | 4 | 4 | 11 | 6.667% | 4200 | 522.3719 | 0.804%
Burgerville | Keith Woith | Emily Naufel |  | 2 |  | 2 | 0% | 0 | 0 | -
Café Zupa's | Keith Woith | Eric Hightower | 1 |  |  | 1 | 0% | 0 | 38.08 | 0%
Caribou / Einstein | Justin Prestinario | Tim Cassidy | 3 | 5 | 8 | 16 | 13.33% | 8400 | 810.9333 | 1.036%
Cattleman's | Keith Woith | Amanda Coulombe |  | 1 |  | 1 | 0% | 0 | 14.35 | 0%
Centerplate | Rob Siler | Emily Naufel |  | 1 | 1 | 2 | 1.667% | 1050 | 10.4 | 10.1%
Checkers | Rob Siler | Steve Steinberg | 1 | 4 | 6 | 11 | 10% | 6300 | 421.19 | 1.496%
Cheddar's | Michelle Hudson | Amanda Coulombe |  | 2 |  | 2 | 0% | 0 | 243.1117 | 0%
Chick-fil-A | Rob Siler | Emily Naufel | 2 | 4 | 3 | 9 | 5% | 3150 | 59.224 | 5.319%
Chipotle | Keith Woith | Amanda Coulombe | 1 | 4 | 5 | 10 | 8.333% | 5250 | 2151.1198 | 0.2441%
Chuck E. Cheese | Michelle Hudson | Amanda Coulombe |  | 1 |  | 1 | 0% | 0 | 0 | -
Cinemark | Michelle Hudson | Tim Cassidy | 2 |  | 2 | 4 | 3.333% | 2100 | 328.2676 | 0.6397%
City BBQ | John Bestler | Emily Naufel | 1 | 1 | 2 | 4 | 3.333% | 2100 | 32.595 | 6.443%
CKE | John Bestler | Amanda Coulombe | 7 | 11 | 12 | 30 | 20% | 12600 | 2731.7826 | 0.4612%
ClubCorp | Michelle Hudson | Emily Naufel | 1 | 1 | 1 | 3 | 1.667% | 1050 | 84.6024 | 1.241%
Compass Group | Brian Nolan | Eric Hightower | 9 | 18 | 20 | 47 | 33.33% | 21000 | 1354.76 | 1.55%
Cornell University | Brian Nolan | Eric Hightower |  | 2 |  | 2 | 0% | 0 | 15.5875 | 0%
Corner Bakery | Michelle Hudson | Steve Steinberg | 1 | 1 | 2 | 4 | 3.333% | 2100 | 154.488 | 1.359%
Corner Store | Michelle Hudson | Steve Steinberg |  | 1 | 3 | 4 | 5% | 3150 | 370.272 | 0.8507%
Cotton Patch Café | Michelle Hudson | Emily Naufel | 1 | 1 |  | 2 | 0% | 0 | 26.5 | 0%
Creative Dining Services | John Bestler | Amanda Coulombe | 1 |  | 2 | 3 | 3.333% | 2100 | 19.6451 | 10.69%
Culinaire Hospitality | Brian Nolan | Eric Hightower |  | 1 |  | 1 | 0% | 0 | 8.484 | 0%
Dairy Queen | Justin Prestinario | Amanda Coulombe | 3 | 2 | 2 | 7 | 3.333% | 2100 | 1661.1923 | 0.1264%
Delaware North | Brian Nolan | Steve Steinberg |  |  | 1 | 1 | 1.667% | 1050 | 39.61 | 2.651%
Delta Hotels and Resort | Justin Prestinario | Steve Steinberg | 1 | 1 |  | 2 | 0% | 0 | 0 | -
Desert Island Properties | Keith Woith | Steve Steinberg |  |  | 1 | 1 | 1.667% | 1050 | 12.296 | 8.539%
Dickey's BBQ | Michelle Hudson | Tim Cassidy | 3 | 1 |  | 4 | 0% | 0 | 0 | -
DineEquity | Keith Woith | Steve Steinberg | 4 | 4 | 10 | 18 | 16.67% | 10500 | 2835.475 | 0.3703%
District Tap | John Bestler | Amanda Coulombe | 1 |  |  | 1 | 0% | 0 | - | -
Donovan's Steak & Chop House | Keith Woith | Steve Steinberg | 1 |  | 1 | 2 | 1.667% | 1050 | 5.22 | 20.11%
EcoSure | All | All | 1 | 1 | 2 | 4 | 3.333% | 2100 | - | -
| Division | All |  | 2 |  | 2 | 0% | 0 | 0 | -
| Shawn Nelson | All |  | 2 |  | 2 | 0% | 0 | 0 | -
Entertainment Cruises | John Bestler | Eric Hightower | 1 | 2 | 2 | 5 | 3.333% | 2100 | 114.464 | 1.835%
Eureka! | Keith Woith | Emily Naufel |  | 1 | 2 | 3 | 3.333% | 2100 | 23.056 | 9.108%
Fairmont Hotels | Justin Prestinario | Eric Hightower | 2 | 1 | 3 | 6 | 5% | 3150 | 130.3546 | 2.416%
Famous Dave's | Justin Prestinario | Eric Hightower |  | 2 | 2 | 4 | 3.333% | 2100 | 150.049 | 1.4%
Fogo De Chao | Michelle Hudson | Eric Hightower |  | 1 | 1 | 2 | 1.667% | 1050 | 109.059 | 0.9628%
Four Winds Casino | John Bestler | Steve Steinberg | 1 | 1 | 1 | 3 | 1.667% | 1050 | 12.048 | 8.715%
Fox Restaurant Concepts | Keith Woith | Tim Cassidy | 4 | 1 | 1 | 6 | 1.667% | 1050 | 69.36 | 1.514%
Fresh Ideas | John Bestler | Steve Steinberg |  | 1 |  | 1 | 0% | 0 | 16.96 | 0%
Friendly's | Brian Nolan | Emily Naufel | 2 | 2 | 2 | 6 | 3.333% | 2100 | 160.2875 | 1.31%
Garbanzo | Keith Woith | Tim Cassidy | 1 | 1 |  | 2 | 0% | 0 | 0.885 | 0%
Genji Inc. | Brian Nolan | Amanda Coulombe |  | 1 | 1 | 2 | 1.667% | 1050 | 1.8719 | 56.09%
Gibson's Steakhouse | John Bestler | Emily Naufel |  | 1 |  | 1 | 0% | 0 | 15.8844 | 0%
Glory Days | Brian Nolan | Amanda Coulombe | 1 | 1 | 1 | 3 | 1.667% | 1050 | 29.9632 | 3.504%
Golden Corral | Brian Nolan | Emily Naufel | 3 | 2 | 3 | 8 | 5% | 3150 | 483.6968 | 0.6512%
Grand American Hotel | Keith Woith | Emily Naufel | 1 |  |  | 1 | 0% | 0 | 4.2 | 0%
Granite City | Justin Prestinario | Tim Cassidy | 1 | 1 | 1 | 3 | 1.667% | 1050 | 122.6024 | 0.8564%
Greenville School System | Rob Siler | Amanda Coulombe |  | 1 | 1 | 2 | 1.667% | 1050 | 50.715 | 2.07%
Guckenheimer | Keith Woith | Emily Naufel | 1 | 2 | 1 | 4 | 1.667% | 1050 | 140.8942 | 0.7452%
Hard Rock Café | John Bestler | Amanda Coulombe |  | 1 | 3 | 4 | 5% | 3150 | 169.3416 | 1.86%
Hilton | Brian Nolan | Eric Hightower | 3 | 3 | 3 | 9 | 5% | 3150 | 472.8494 | 0.6662%
HMS Host | Brian Nolan | Emily Naufel | 2 |  |  | 2 | 0% | 0 | 0 | -
HoneyBaked Ham | Rob Siler | Emily Naufel | 3 | 3 | 4 | 10 | 6.667% | 4200 | 165.1259 | 2.544%
Hooters of America | Rob Siler | Emily Naufel |  | 3 | 2 | 5 | 3.333% | 2100 | 300.16 | 0.6996%
Humber College | Justin Prestinario | Emily Naufel | 1 |  |  | 1 | 0% | 0 | 1.5036 | 0%
Hyatt Hotels | John Bestler | Steve Steinberg | 2 | 1 | 2 | 5 | 3.333% | 2100 | 110.2163 | 1.905%
Ignite Restaurants | Michelle Hudson | Amanda Coulombe | 1 | 2 | 1 | 4 | 1.667% | 1050 | 123.6362 | 0.8493%
Il Fornaio | Michelle Hudson | Tim Cassidy | 1 | 2 |  | 3 | 0% | 0 | 27.808 | 0%
Interstate Hotels and Resorts | Brian Nolan | Eric Hightower | 2 | 2 | 3 | 7 | 5% | 3150 | 108.6755 | 2.899%
iPic Theaters | Rob Siler | Steve Steinberg | 1 |  | 1 | 2 | 1.667% | 1050 | 26.6742 | 3.936%
Jackson's | Keith Woith | Amanda Coulombe |  | 3 | 3 | 6 | 5% | 3150 | 61.6125 | 5.113%
Jamba Juice | Keith Woith | Tim Cassidy |  | 5 | 10 | 15 | 16.67% | 10500 | 337.12 | 3.115%
John's Incredible Pizza | Keith Woith | Tim Cassidy | 1 |  |  | 1 | 0% | 0 | 15.4875 | 0%
Kendall Senior Living | Brian Nolan | Amanda Coulombe |  | 2 |  | 2 | 0% | 0 | 13.5375 | 0%
King's Seafood | Keith Woith | Tim Cassidy |  | 2 |  | 2 | 0% | 0 | 13.5324 | 0%
Kona Grill | Keith Woith | Tim Cassidy | 2 | 1 |  | 3 | 0% | 0 | 51.0777 | 0%
Landry's | Keith Woith | Tim Cassidy |  | 1 |  | 1 | 0% | 0 | 24.3504 | 0%
LaRosa's | John Bestler | Steve Steinberg |  | 2 |  | 2 | 0% | 0 | 38.5841 | 0%
Lawry's | Keith Woith | Emily Naufel | 1 | 1 |  | 2 | 0% | 0 | 8.8956 | 0%
Lazy Dog Café | Division | Steve Steinberg |  |  | 1 | 1 | 1.667% | 1050 | 31.605 | 3.322%
Linchris Hotels | Brian Nolan | Eric Hightower | 1 | 1 |  | 2 | 0% | 0 | 11.514 | 0%
LTP Management Group | Rob Siler | Eric Hightower |  | 1 |  | 1 | 0% | 0 | 3.644 | 0%
Luna Grill | Keith Woith | Emily Naufel |  |  | 1 | 1 | 1.667% | 1050 | - | -
Macaroni Grill | Michelle Hudson | Amanda Coulombe | 1 | 1 | 2 | 4 | 3.333% | 2100 | 84.42 | 2.488%
Mambo | Michelle Hudson | Amanda Coulombe | 1 | 1 |  | 2 | 0% | 0 | 0 | -
Marcus Hotels | John Bestler | Tim Cassidy | 1 | 1 |  | 2 | 0% | 0 | 10.7181 | 0%
Margaritaville | Rob Siler | Amanda Coulombe | 1 | 1 | 2 | 4 | 3.333% | 2100 | 15.4185 | 13.62%
Max Restaurant Group | Brian Nolan | Amanda Coulombe | 1 | 1 | 1 | 3 | 1.667% | 1050 | 21.8196 | 4.812%
McDonald's | Justin Prestinario | Eric Hightower | 2 | 6 | 8 | 16 | 13.33% | 8400 | 1632.8426 | 0.5144%
Medieval Times | Michelle Hudson | Emily Naufel |  |  | 1 | 1 | 1.667% | 1050 | 7.3692 | 14.25%
Metz & Associates | Brian Nolan | Amanda Coulombe |  | 1 | 2 | 3 | 3.333% | 2100 | 105.7177 | 1.986%
Mimi's Café | Michelle Hudson | Tim Cassidy |  | 1 | 2 | 3 | 3.333% | 2100 | 57.2 | 3.671%
Mohonk | Brian Nolan | Emily Naufel | 2 | 2 | 2 | 6 | 3.333% | 2100 | 16.3572 | 12.84%
My Fit Foods | Michelle Hudson | Steve Steinberg |  |  | 1 | 1 | 1.667% | 1050 | 6 | 17.5%
Nando's | Brian Nolan | Amanda Coulombe | 2 |  |  | 2 | 0% | 0 | 0 | -
National Food Laboratory | John Bestler | Tim Cassidy | 1 |  |  | 1 | 0% | 0 | 0 | -
New York Office of Mental Health | Brian Nolan | Emily Naufel | 1 |  |  | 1 | 0% | 0 | 0 | -
Newk's | Michelle Hudson | Steve Steinberg |  | 2 | 1 | 3 | 1.667% | 1050 | 65.508 | 1.603%
Noodle's | Keith Woith | Steve Steinberg | 1 | 4 | 4 | 9 | 6.667% | 4200 | 243.045 | 1.728%
Ocean Properties | John Bestler | Steve Steinberg | 1 | 2 | 2 | 5 | 3.333% | 2100 | 39.0604 | 5.376%
Ohio State University | John Bestler | Eric Hightower |  | 1 |  | 1 | 0% | 0 | 6.0188 | 0%
Old Spaghetti Factory | Keith Woith | Tim Cassidy |  | 1 |  | 1 | 0% | 0 | 0 | -
Olga's Kitchen | John Bestler | Amanda Coulombe |  | 1 | 1 | 2 | 1.667% | 1050 | 27 | 3.889%
Omni Hotels | Michelle Hudson | Tim Cassidy | 1 | 1 |  | 2 | 0% | 0 | 79.6843 | 0%
On The Border | Michelle Hudson | Steve Steinberg | 3 | 2 | 1 | 6 | 1.667% | 1050 | 143.099 | 0.7338%
OTG Management | Brian Nolan | Amanda Coulombe |  | 1 |  | 1 | 0% | 0 | 0 | -
Panera Bread | John Bestler | Tim Cassidy | 1 | 3 | 4 | 8 | 6.667% | 4200 | 1499.7823 | 0.28%
Pantry (Auntie M's) | Brian Nolan | Tim Cassidy | 1 | 1 | 1 | 3 | 1.667% | 1050 | 52.6276 | 1.995%
Peet's Coffee & Tea | Keith Woith | Amanda Coulombe |  | 2 | 1 | 3 | 1.667% | 1050 | 115.6451 | 0.908%
Pepperidge Farm | Brian Nolan | Tim Cassidy |  |  | 1 | 1 | 1.667% | 1050 | 9.318 | 11.27%
Peter Piper Pizza | Keith Woith | Amanda Coulombe | 1 | 1 |  | 2 | 0% | 0 | 59.22 | 0%
Piada Group | John Bestler | Emily Naufel |  | 1 |  | 1 | 0% | 0 | 29.524 | 0%
Pinnacle Entertainment Group | Keith Woith | Emily Naufel |  | 1 | 1 | 2 | 1.667% | 1050 | 54 | 1.944%
Pizza Ranch | Justin Prestinario | Eric Hightower | 2 | 3 | 2 | 7 | 3.333% | 2100 | 108.1649 | 1.941%
Popeye's | Rob Siler | Emily Naufel |  | 4 | 4 | 8 | 6.667% | 4200 | 962.1 | 0.4365%
Potbelly's | John Bestler | Amanda Coulombe |  | 2 | 1 | 3 | 1.667% | 1050 | 223.617 | 0.4696%
Pret A Manger | Brian Nolan | Steve Steinberg |  | 2 | 3 | 5 | 5% | 3150 | 73.84 | 4.266%
Quaker Steak & Lube | Brian Nolan | Steve Steinberg | 1 |  |  | 1 | 0% | 0 | 0 | -
Quest Food Management Services | John Bestler | Emily Naufel |  | 1 |  | 1 | 0% | 0 | 2 | 0%
Quorum | Keith Woith | Eric Hightower | 1 | 1 |  | 2 | 0% | 0 | 1.818 | 0%
RaceTrac | Brian Nolan | Emily Naufel | 1 | 3 | 2 | 6 | 3.333% | 2100 | 165.528 | 1.269%
Real Mex | Keith Woith | Amanda Coulombe |  |  | 3 | 3 | 5% | 3150 | 0 | -
Red Lobster | John Bestler | Amanda Coulombe |  | 2 | 2 | 4 | 3.333% | 2100 | 477.1696 | 0.4401%
Sage Hospitality | Keith Woith | Emily Naufel | 1 | 1 | 1 | 3 | 1.667% | 1050 | 36.96 | 2.841%
Salem Senior | Brian Nolan | Amanda Coulombe | 1 |  |  | 1 | 0% | 0 | 0 | -
Sauce | Keith Woith | Tim Cassidy |  | 2 |  | 2 | 0% | 0 | 13.92 | 0%
Seaport Boston | Brian Nolan | Steve Steinberg | 1 |  | 1 | 2 | 1.667% | 1050 | 5.1865 | 20.24%
Select Restaurants | John Bestler | Eric Hightower | 1 | 1 |  | 2 | 0% | 0 | 10.68 | 0%
Shopper Events LLC | Keith Woith | Steve Steinberg | 1 |  | 1 | 2 | 1.667% | 1050 | 181.2 | 0.5795%
Silver Cloud | Keith Woith | Eric Hightower | 1 | 1 |  | 2 | 0% | 0 | 2.611 | 0%
SilverBirch Hotels | Justin Prestinario | Eric Hightower | 1 |  |  | 1 | 0% | 0 | 3.432 | 0%
Snooze | Keith Woith | Amanda Coulombe |  | 1 | 2 | 3 | 3.333% | 2100 | 22.1 | 9.502%
Sodexo | Brian Nolan | Eric Hightower | 2 | 9 | 6 | 17 | 10% | 6300 | 1719.5254 | 0.3664%
Stanford University | Keith Woith | Eric Hightower |  | 2 |  | 2 | 0% | 0 | 21.488 | 0%
Starbucks | Justin Prestinario | Tim Cassidy | 5 | 7 | 10 | 22 | 16.67% | 10500 | 5469.8765 | 0.192%
Starwood | Brian Nolan | Eric Hightower | 5 | 4 |  | 9 | 0% | 0 | 14.627 | 0%
Steak 'n Shake | John Bestler | Tim Cassidy |  | 1 | 2 | 3 | 3.333% | 2100 | 482.472 | 0.4353%
Stripes | Michelle Hudson | Steve Steinberg | 1 | 3 | 6 | 10 | 10% | 6300 | 362.7247 | 1.737%
Sunkist | Keith Woith | Eric Hightower |  | 1 |  | 1 | 0% | 0 | 36.384 | 0%
Taco Mac | Rob Siler | Emily Naufel | 1 | 1 | 1 | 3 | 1.667% | 1050 | 40.4121 | 2.598%
Tavistock | Keith Woith | Steve Steinberg |  | 1 | 1 | 2 | 1.667% | 1050 | 23.76 | 4.419%
TGI Friday's | Michelle Hudson | Eric Hightower | 1 | 4 | 7 | 12 | 11.67% | 7350 | 390.5828 | 1.882%
The Kitchen | Keith Woith | Amanda Coulombe |  | 1 |  | 1 | 0% | 0 | 3.105 | 0%
The Peninsula Hotel | John Bestler | Amanda Coulombe |  |  | 1 | 1 | 1.667% | 1050 | 4.2126 | 24.93%
The Procaccianti Group | Brian Nolan | Steve Steinberg |  | 1 |  | 1 | 0% | 0 | 48.06 | 0%
Tilted Kilt | Keith Woith | Steve Steinberg | 1 | 1 |  | 2 | 0% | 0 | 3.43 | 0%
Tommy Bahama | Rob Siler | Tim Cassidy |  | 1 | 1 | 2 | 1.667% | 1050 | 13.4663 | 7.797%
Travel Centers of America | John Bestler | Eric Hightower |  | 2 | 2 | 4 | 3.333% | 2100 | 75.514 | 2.781%
Tropical Smoothie Café | Brian Nolan | Tim Cassidy |  | 1 | 2 | 3 | 3.333% | 2100 | 290.598 | 0.7226%
Trusthouse (Aladdin) | Brian Nolan | Eric Hightower | 1 | 1 | 2 | 4 | 3.333% | 2100 | 16.12 | 13.03%
Twin Peaks | Michelle Hudson | Eric Hightower | 3 | 5 | 2 | 10 | 3.333% | 2100 | 114.144 | 1.84%
Unidine | Brian Nolan | Steve Steinberg |  | 1 | 1 | 2 | 1.667% | 1050 | 5.1 | 20.59%
Verve Senior Living | Justin Prestinario | Steve Steinberg |  | 1 | 2 | 3 | 3.333% | 2100 | 34.155 | 6.148%
Veteran's Canteen Services | Rob Siler | Tim Cassidy | 1 | 1 | 2 | 4 | 3.333% | 2100 | 64.3125 | 3.265%
Vi | John Bestler | Amanda Coulombe |  | 2 |  | 2 | 0% | 0 | 23.3377 | 0%
Village Tavern | Rob Siler | Emily Naufel | 4 | 4 |  | 8 | 0% | 0 | 20.8908 | 0%
Weber Grill | John Bestler | Tim Cassidy | 1 | 1 |  | 2 | 0% | 0 | 16.8301 | 0%
White Lodging | John Bestler | Amanda Coulombe |  | 1 |  | 1 | 0% | 0 | 23.3856 | 0%
Willow Valley Resort | Brian Nolan | Steve Steinberg | 1 |  | 1 | 2 | 1.667% | 1050 | 8.6404 | 12.15%
Wyndham Hotels | Brian Nolan | Tim Cassidy | 1 |  | 1 | 2 | 1.667% | 1050 | 24.0078 | 4.374%
YUM! Brands | Michelle Hudson | Emily Naufel | 8 | 15 | 22 | 45 | 36.67% | 23100 | 4650.062 | 0.4968%
Z Foods | Brian Nolan | Amanda Coulombe |  | 1 |  | 1 | 0% | 0 | 2.5666 | 0%
Texas Roadhouse | Brian Nolan | Amanda Coulombe |  |  | 2 | 2 | 3.333% | 2100 | 0 | -
Pizzeria Locale | Keith Woith | Amanda Coulombe |  |  | 1 | 1 | 1.667% | 1050 | - | -
Red Robin | Keith Woith | Amanda Coulombe |  |  | 1 | 1 |  |  | 0 | -
Briad | Keith Woith | Tim Cassidy |  | 1 |  | 1
Boudin Bakery | Keith Woith | Eric Hightower |  |  | 1 | 1
Cerca Trova | Keith Woith | Steve Steinberg |  |  | 2 | 2
Shake Shack | Brian Nolan | Emily Naufel |  |  | 2 | 2
Darden Franchise Group | Rob Siler | Amanda Coulombe |  |  | 2 | 2
Freddy's Frozen Custard | John Bestler | Eric Hightower |  |  | 1 | 1
Eatsa | Keith Woith | Steve Steinberg |  |  | 1 | 1
State of North Carolina | Brian Nolan | Tim Cassidy |  |  | 1 | 1
Cooper's Hawk | John Bestler | Eric Hightower |  |  | 1 | 1
Santiagos | Keith Woith | Eric Hightower |  |  | 1 | 1
Grand Total |  |  | 178 | 296 | 316 | 790

## DeplAssocDeliverableBreakout
Complete | N
Count of TargetDate
Months | TargetDate | DeplAssoc | Total
Jul | 1-Jul | MG | 1
| 20-Jul | BH | 2
Jul Total |  |  | 3
Aug | 1-Aug | AD | 3
|  | AK | 6
|  | AP | 2
|  | BH | 2
|  | MG | 4
|  | NJ | 3
| 11-Aug | AD | 1
Aug Total |  |  | 21
Sep | 1-Sep | AD | 5
|  | BH | 5
|  | MG | 6
|  | NJ | 2
| 4-Sep | AK | 1
| 10-Sep | AK | 4
Sep Total |  |  | 23
Grand Total |  |  | 47

## CustomerLaunchCost
Customer | Sales | AcctManager | 2015 | 2016 | 2017 | Total | 2017 % of Annual FTE Capacity | Est. Cost | Cust. Revenue ($1,000's) | Cost / Revenue
4 Rivers Smokehouse | Rob Siler | Amanda Coulombe |  | 1 | 3 | 4 | 5% | 3150 | 9.425 | 33.42%
7-Eleven | Justin Prestinario | Amanda Coulombe | 1 |  |  | 1 | 0% | 0 | 0 | -
85 ᵒC Café | Keith Woith | Steve Steinberg | 1 | 2 | 1 | 4 | 1.667% | 1050 | 26.845 | 3.911%
Academia Barilla | John Bestler | Steve Steinberg |  | 1 | 1 | 2 | 1.667% | 1050 | 6.3 | 16.67%
Ace Restaurant Group | Brian Nolan | Eric Hightower | 1 | 1 |  | 2 | 0% | 0 | 0 | -
Adak Restaurants | John Bestler | Eric Hightower | 1 | 1 |  | 2 | 0% | 0 | 0 | -
Aramark | Brian Nolan | Amanda Coulombe | 1 | 4 | 6 | 11 | 10% | 6300 | 1002.9653 | 0.6281%
Arby's | Rob Siler | Amanda Coulombe | 1 | 1 | 2 | 4 | 3.333% | 2100 | 610.32 | 0.3441%
Areas USA | John Bestler | Steve Steinberg | 1 | 1 | 3 | 5 | 5% | 3150 | 35.24 | 8.939%
Au Bon Pain | Brian Nolan | Eric Hightower |  |  | 2 | 2 | 3.333% | 2100 | 0 | -
Avendra Hospitality | Brian Nolan | Amanda Coulombe |  | 1 | 2 | 3 | 3.333% | 2100 | 42.9986 | 4.884%
Bass Pro Shop | John Bestler | Amanda Coulombe | 1 | 1 | 3 | 5 | 5% | 3150 | 57.5289 | 5.476%
Batali & Bastianich Hospitality Group | Brian Nolan | Emily Naufel | 1 | 1 |  | 2 | 0% | 0 | 0 | -
Benihana | Rob Siler | Steve Steinberg |  |  | 3 | 3 | 5% | 3150 | 0 | -
Bento Sushi | Justin Prestinario | Amanda Coulombe |  |  | 3 | 3 | 5% | 3150 | 110.416 | 2.853%
Bloomin' Brands | Rob Siler | Steve Steinberg | 2 | 2 | 2 | 6 | 3.333% | 2100 | 1401.178 | 0.1499%
Boudin | Keith Woith | Eric Hightower |  |  | 2 | 2 | 3.333% | 2100 | 0 | -
Briad Group (Zinburger) | Keith Woith | Tim Cassidy |  | 1 |  | 1 | 0% | 0 | #N/A | -
Brinker | Michelle Hudson | Steve Steinberg | 2 |  |  | 2 | 0% | 0 | 0 | -
Brookdale | John Bestler | Steve Steinberg | 3 | 2 | 2 | 7 | 3.333% | 2100 | 1657.098 | 0.1267%
Brookhaven | Brian Nolan | Amanda Coulombe | 1 |  |  | 1 | 0% | 0 | -1.1183 | 0%
Buffalo Wild Wings | Justin Prestinario | Emily Naufel | 4 | 4 | 3 | 11 | 5% | 3150 | 1046.1071 | 0.3011%
Burger King | John Bestler | Steve Steinberg | 3 | 4 | 3 | 10 | 5% | 3150 | 522.3719 | 0.603%
Burgerville | Keith Woith | Emily Naufel |  | 2 |  | 2 | 0% | 0 | 0 | -
Café Zupa's | Keith Woith | Eric Hightower | 1 |  |  | 1 | 0% | 0 | 38.08 | 0%
Caribou / Einstein | Justin Prestinario | Tim Cassidy | 3 | 5 | 9 | 17 | 15% | 9450 | 810.9333 | 1.165%
Cattleman's | Keith Woith | Amanda Coulombe |  | 1 | 2 | 3 | 3.333% | 2100 | 14.35 | 14.63%
Centerplate | Rob Siler | Emily Naufel |  | 1 | 1 | 2 | 1.667% | 1050 | 10.4 | 10.1%
Checkers | Rob Siler | Steve Steinberg | 1 | 4 | 7 | 12 | 11.67% | 7350 | 421.19 | 1.745%
Cheddar's | Michelle Hudson | Emily Naufel |  | 2 | 1 | 3 | 1.667% | 1050 | 243.1117 | 0.4319%
Chick-fil-A | Rob Siler | Tim Cassidy | 2 | 4 | 3 | 9 | 5% | 3150 | 59.224 | 5.319%
Chipotle | Keith Woith | Amanda Coulombe | 1 | 4 | 5 | 10 | 8.333% | 5250 | 2151.1198 | 0.2441%
Chuck E. Cheese | Michelle Hudson | Amanda Coulombe |  | 1 |  | 1 | 0% | 0 | 0 | -
Cinemark | Michelle Hudson | Tim Cassidy | 2 |  | 3 | 5 | 5% | 3150 | 328.2676 | 0.9596%
City BBQ | John Bestler | Emily Naufel | 1 | 1 | 1 | 3 | 1.667% | 1050 | 32.595 | 3.221%
CKE | John Bestler | Amanda Coulombe | 7 | 11 | 14 | 32 | 23.33% | 14700 | 2731.7826 | 0.5381%
ClubCorp | Michelle Hudson | Emily Naufel | 1 | 1 | 1 | 3 | 1.667% | 1050 | 84.6024 | 1.241%
Compass Group | Brian Nolan | Eric Hightower | 9 | 18 | 22 | 49 | 36.67% | 23100 | 1354.76 | 1.705%
Cornell University | Brian Nolan | Eric Hightower |  | 2 |  | 2 | 0% | 0 | 15.5875 | 0%
Corner Bakery | Michelle Hudson | Steve Steinberg | 1 | 1 | 2 | 4 | 3.333% | 2100 | 154.488 | 1.359%
Corner Store | Michelle Hudson | Steve Steinberg |  | 1 | 3 | 4 | 5% | 3150 | 370.272 | 0.8507%
Cotton Patch Café | Michelle Hudson | Emily Naufel | 1 | 1 |  | 2 | 0% | 0 | 26.5 | 0%
Creative Dining Services | John Bestler | Amanda Coulombe | 1 |  | 2 | 3 | 3.333% | 2100 | 19.6451 | 10.69%
Culinaire Hospitality | Brian Nolan | Eric Hightower |  | 1 |  | 1 | 0% | 0 | 8.484 | 0%
Dairy Queen | Justin Prestinario | Amanda Coulombe | 3 | 2 | 3 | 8 | 5% | 3150 | 1667.0723 | 0.189%
Delaware North | Brian Nolan | Steve Steinberg |  |  | 2 | 2 | 3.333% | 2100 | 39.61 | 5.302%
Delta Hotels and Resort | Justin Prestinario | Steve Steinberg | 1 | 1 |  | 2 | 0% | 0 | 0 | -
Desert Island Properties | Keith Woith | Steve Steinberg |  |  | 1 | 1 | 1.667% | 1050 | 12.296 | 8.539%
Dickey's BBQ | Michelle Hudson | Tim Cassidy | 3 | 1 |  | 4 | 0% | 0 | 0 | -
DineEquity | Keith Woith | Steve Steinberg | 4 | 4 | 9 | 17 | 15% | 9450 | 2835.475 | 0.3333%
District Tap | John Bestler | Amanda Coulombe | 1 |  |  | 1 | 0% | 0 | 0 | -
Donovan's Steak & Chop House | Keith Woith | Steve Steinberg | 1 |  | 1 | 2 | 1.667% | 1050 | 5.22 | 20.11%
EcoSure | All | All | 1 | 1 |  | 2 | 0% | 0 | 0 | -
| Division | All |  | 2 |  | 2 | 0% | 0 | 0 | -
| Shawn Nelson | All |  | 2 |  | 2 | 0% | 0 | 0 | -
Entertainment Cruises | John Bestler | Eric Hightower | 1 | 2 | 2 | 5 | 3.333% | 2100 | 114.464 | 1.835%
Eureka! | Keith Woith | Emily Naufel |  | 1 | 1 | 2 | 1.667% | 1050 | 23.056 | 4.554%
Fairmont Hotels | Justin Prestinario | Eric Hightower | 2 | 1 | 3 | 6 | 5% | 3150 | 130.3546 | 2.416%
Famous Dave's | Justin Prestinario | Eric Hightower |  | 2 | 3 | 5 | 5% | 3150 | 150.049 | 2.099%
Fogo De Chao | Michelle Hudson | Eric Hightower |  | 1 | 1 | 2 | 1.667% | 1050 | 109.059 | 0.9628%
Four Winds Casino | John Bestler | Steve Steinberg | 1 | 1 | 1 | 3 | 1.667% | 1050 | 12.048 | 8.715%
Fox Restaurant Concepts | Keith Woith | Tim Cassidy | 4 | 1 | 1 | 6 | 1.667% | 1050 | 69.36 | 1.514%
Fresh Ideas | John Bestler | Steve Steinberg |  | 1 |  | 1 | 0% | 0 | 16.96 | 0%
Friendly's | Brian Nolan | Emily Naufel | 2 | 2 | 2 | 6 | 3.333% | 2100 | 160.2875 | 1.31%
Garbanzo | Keith Woith | Tim Cassidy | 1 | 1 |  | 2 | 0% | 0 | 0.885 | 0%
Genji Inc. | Brian Nolan | Amanda Coulombe |  | 1 | 1 | 2 | 1.667% | 1050 | 1.8719 | 56.09%
Gibson's Steakhouse | John Bestler | Emily Naufel |  | 1 |  | 1 | 0% | 0 | 16.3301 | 0%
Glory Days | Brian Nolan | Amanda Coulombe | 1 | 1 | 3 | 5 | 5% | 3150 | 29.9632 | 10.51%
Golden Corral | Brian Nolan | Emily Naufel | 3 | 2 | 3 | 8 | 5% | 3150 | 483.6968 | 0.6512%
Grand American Hotel | Keith Woith | Emily Naufel | 1 |  |  | 1 | 0% | 0 | 4.2 | 0%
Granite City | Justin Prestinario | Tim Cassidy | 1 | 1 | 1 | 3 | 1.667% | 1050 | 122.6024 | 0.8564%
Greenville School System | Rob Siler | Amanda Coulombe |  | 1 | 1 | 2 | 1.667% | 1050 | 50.715 | 2.07%
Guckenheimer | Keith Woith | Emily Naufel | 1 | 2 | 1 | 4 | 1.667% | 1050 | 140.8942 | 0.7452%
Hard Rock Café | John Bestler | Amanda Coulombe |  | 1 | 4 | 5 | 6.667% | 4200 | 169.3416 | 2.48%
Hilton | Brian Nolan | Eric Hightower | 3 | 3 | 6 | 12 | 10% | 6300 | 472.8494 | 1.332%
HMS Host | Brian Nolan | Emily Naufel | 2 |  |  | 2 | 0% | 0 | 0 | -
HoneyBaked Ham | Rob Siler | Emily Naufel | 3 | 3 | 3 | 9 | 5% | 3150 | 165.1259 | 1.908%
Hooters of America | Rob Siler | Emily Naufel |  | 3 | 3 | 6 | 5% | 3150 | 300.16 | 1.049%
Humber College | Justin Prestinario | Emily Naufel | 1 |  |  | 1 | 0% | 0 | 1.5036 | 0%
Hyatt Hotels | John Bestler | Steve Steinberg | 2 | 1 | 2 | 5 | 3.333% | 2100 | 110.2163 | 1.905%
Ignite Restaurants | Michelle Hudson | Amanda Coulombe | 1 | 2 | 2 | 5 | 3.333% | 2100 | 123.6362 | 1.699%
Il Fornaio | Michelle Hudson | Tim Cassidy | 1 | 2 |  | 3 | 0% | 0 | 27.808 | 0%
Interstate Hotels and Resorts | Brian Nolan | Eric Hightower | 2 | 2 | 5 | 9 | 8.333% | 5250 | 108.6755 | 4.831%
iPic Theaters | Rob Siler | Steve Steinberg | 1 |  | 1 | 2 | 1.667% | 1050 | 26.6742 | 3.936%
Jackson's | Keith Woith | Amanda Coulombe |  | 3 | 4 | 7 | 6.667% | 4200 | 61.6125 | 6.817%
Jamba Juice | Keith Woith | Tim Cassidy |  | 5 | 10 | 15 | 16.67% | 10500 | 337.12 | 3.115%
John's Incredible Pizza | Keith Woith | Tim Cassidy | 1 |  |  | 1 | 0% | 0 | 15.4875 | 0%
Kendall Senior Living | Brian Nolan | Amanda Coulombe |  | 2 | 2 | 4 | 3.333% | 2100 | 13.5375 | 15.51%
King's Seafood | Keith Woith | Tim Cassidy |  | 2 | 1 | 3 | 1.667% | 1050 | 13.5324 | 7.759%
Kona Grill | Keith Woith | Tim Cassidy | 2 | 1 |  | 3 | 0% | 0 | 51.0777 | 0%
Landry's | Keith Woith | Tim Cassidy |  | 1 |  | 1 | 0% | 0 | 24.3504 | 0%
LaRosa's | John Bestler | Steve Steinberg |  | 2 |  | 2 | 0% | 0 | 38.5841 | 0%
Lawry's | Keith Woith | Emily Naufel | 1 | 1 |  | 2 | 0% | 0 | 8.8956 | 0%
Lazy Dog Café | Division | Steve Steinberg |  |  | 1 | 1 | 1.667% | 1050 | 31.605 | 3.322%
Linchris Hotels | Brian Nolan | Eric Hightower | 1 | 1 |  | 2 | 0% | 0 | 11.514 | 0%
LTP Management Group | Rob Siler | Eric Hightower |  | 1 |  | 1 | 0% | 0 | 3.644 | 0%
Luna Grill | Keith Woith | (blank) |  |  | 1 | 1 | 1.667% | 1050 | 0 | -
Macaroni Grill | Michelle Hudson | Amanda Coulombe | 1 | 1 | 2 | 4 | 3.333% | 2100 | 84.42 | 2.488%
Mambo | Michelle Hudson | Amanda Coulombe | 1 | 1 |  | 2 | 0% | 0 | 0 | -
Marcus Hotels | John Bestler | Tim Cassidy | 1 | 1 |  | 2 | 0% | 0 | 10.7181 | 0%
Margaritaville | Rob Siler | Amanda Coulombe | 1 | 1 | 3 | 5 | 5% | 3150 | 22.9629 | 13.72%
Max Restaurant Group | Brian Nolan | Amanda Coulombe | 1 | 1 | 2 | 4 | 3.333% | 2100 | 21.8196 | 9.624%
McDonald's | Justin Prestinario | Eric Hightower | 2 | 6 | 5 | 13 | 8.333% | 5250 | 1632.8426 | 0.3215%
Metz & Associates | Brian Nolan | Amanda Coulombe |  | 1 | 2 | 3 | 3.333% | 2100 | 105.7177 | 1.986%
Mimi's Café | Michelle Hudson | Tim Cassidy |  | 1 | 3 | 4 | 5% | 3150 | 57.2 | 5.507%
Mohonk | Brian Nolan | Emily Naufel | 2 | 2 | 2 | 6 | 3.333% | 2100 | 16.3572 | 12.84%
My Fit Foods | Michelle Hudson | Steve Steinberg |  |  | 1 | 1 | 1.667% | 1050 | 6 | 17.5%
Nando's | Brian Nolan | Amanda Coulombe | 2 |  |  | 2 | 0% | 0 | 0 | -
National Food Laboratory | John Bestler | Tim Cassidy | 1 |  |  | 1 | 0% | 0 | 0 | -
New York Office of Mental Health | Brian Nolan | Emily Naufel | 1 |  |  | 1 | 0% | 0 | 0 | -
Newk's | Michelle Hudson | Steve Steinberg |  | 2 |  | 2 | 0% | 0 | 65.508 | 0%
Noodle's | Keith Woith | Steve Steinberg | 1 | 4 | 4 | 9 | 6.667% | 4200 | 243.045 | 1.728%
Ocean Properties | John Bestler | Steve Steinberg | 1 | 2 | 2 | 5 | 3.333% | 2100 | 39.0604 | 5.376%
Ohio State University | John Bestler | Eric Hightower |  | 1 |  | 1 | 0% | 0 | 6.0188 | 0%
Old Spaghetti Factory | Keith Woith | Tim Cassidy |  | 1 |  | 1 | 0% | 0 | 0 | -
Olga's Kitchen | John Bestler | Amanda Coulombe |  | 1 | 1 | 2 | 1.667% | 1050 | 27 | 3.889%
Omni Hotels | Michelle Hudson | Tim Cassidy | 1 | 1 | 1 | 3 | 1.667% | 1050 | 79.6843 | 1.318%
On The Border | Michelle Hudson | Steve Steinberg | 3 | 2 | 2 | 7 | 3.333% | 2100 | 143.099 | 1.468%
OTG Management | Brian Nolan | Amanda Coulombe |  | 1 |  | 1 | 0% | 0 | 0 | -
Panera Bread | John Bestler | Tim Cassidy | 1 | 3 | 5 | 9 | 8.333% | 5250 | 1499.7823 | 0.3501%
Pantry (Auntie M's) | Brian Nolan | Tim Cassidy | 1 | 1 | 1 | 3 | 1.667% | 1050 | 52.6276 | 1.995%
Peet's Coffee & Tea | Keith Woith | Amanda Coulombe |  | 2 | 2 | 4 | 3.333% | 2100 | 115.6451 | 1.816%
Pepperidge Farm | Brian Nolan | Tim Cassidy |  |  | 1 | 1 | 1.667% | 1050 | 9.318 | 11.27%
Peter Piper Pizza | Keith Woith | Amanda Coulombe | 1 | 1 | 1 | 3 | 1.667% | 1050 | 59.22 | 1.773%
Piada Group | John Bestler | Emily Naufel |  | 1 | 1 | 2 | 1.667% | 1050 | 29.524 | 3.556%
Pinnacle Entertainment Group | Keith Woith | Emily Naufel |  | 1 | 1 | 2 | 1.667% | 1050 | 54 | 1.944%
Pizza Ranch | Justin Prestinario | Eric Hightower | 2 | 3 | 2 | 7 | 3.333% | 2100 | 108.1649 | 1.941%
Popeye's | Rob Siler | Emily Naufel |  | 4 | 3 | 7 | 5% | 3150 | 962.1 | 0.3274%
Potbelly's | John Bestler | Amanda Coulombe |  | 2 | 2 | 4 | 3.333% | 2100 | 223.617 | 0.9391%
Pret A Manger | Brian Nolan | Steve Steinberg |  | 2 | 4 | 6 | 6.667% | 4200 | 73.84 | 5.688%
Quaker Steak & Lube | Brian Nolan | Steve Steinberg | 1 |  |  | 1 | 0% | 0 | 0 | -
Quest Food Management Services | John Bestler | Emily Naufel |  | 1 |  | 1 | 0% | 0 | 2 | 0%
Quorum | Keith Woith | Eric Hightower | 1 | 1 |  | 2 | 0% | 0 | 1.818 | 0%
RaceTrac | Brian Nolan | Emily Naufel | 1 | 3 | 2 | 6 | 3.333% | 2100 | 165.528 | 1.269%
Real Mex | Keith Woith | Amanda Coulombe |  |  | 3 | 3 | 5% | 3150 | 0 | -
Red Lobster | John Bestler | Amanda Coulombe |  | 2 | 2 | 4 | 3.333% | 2100 | 477.1696 | 0.4401%
Sage Hospitality | Keith Woith | Emily Naufel | 1 | 1 | 1 | 3 | 1.667% | 1050 | 36.96 | 2.841%
Salem Senior | Brian Nolan | Amanda Coulombe | 1 |  |  | 1 | 0% | 0 | 0 | -
Sauce | Keith Woith | Tim Cassidy |  | 2 |  | 2 | 0% | 0 | 13.92 | 0%
Seaport Boston | Brian Nolan | Steve Steinberg | 1 |  | 1 | 2 | 1.667% | 1050 | 5.1865 | 20.24%
Select Restaurants | John Bestler | Eric Hightower | 1 | 1 |  | 2 | 0% | 0 | 10.68 | 0%
Shopper Events LLC | Keith Woith | Steve Steinberg | 1 |  | 1 | 2 | 1.667% | 1050 | 181.2 | 0.5795%
Silver Cloud | Keith Woith | Eric Hightower | 1 | 1 |  | 2 | 0% | 0 | 2.611 | 0%
SilverBirch Hotels | Justin Prestinario | Eric Hightower | 1 |  |  | 1 | 0% | 0 | 3.432 | 0%
Snooze | Keith Woith | Amanda Coulombe |  | 1 | 4 | 5 | 6.667% | 4200 | 22.1 | 19%
Sodexo | Brian Nolan | Eric Hightower | 2 | 9 | 8 | 19 | 13.33% | 8400 | 1719.5254 | 0.4885%
Stanford University | Keith Woith | Eric Hightower |  | 2 | 2 | 4 | 3.333% | 2100 | 21.488 | 9.773%
Starbucks | Justin Prestinario | Tim Cassidy | 5 | 7 | 10 | 22 | 16.67% | 10500 | 5469.8765 | 0.192%
Starwood | Brian Nolan | Eric Hightower | 5 | 4 |  | 9 | 0% | 0 | 14.627 | 0%
Steak 'n Shake | John Bestler | Tim Cassidy |  | 1 | 4 | 5 | 6.667% | 4200 | 482.472 | 0.8705%
Stripes | Michelle Hudson | Steve Steinberg | 1 | 3 | 6 | 10 | 10% | 6300 | 362.7247 | 1.737%
Sunkist | Keith Woith | Eric Hightower |  | 1 |  | 1 | 0% | 0 | 36.384 | 0%
Taco Mac | Rob Siler | Emily Naufel | 1 | 1 | 1 | 3 | 1.667% | 1050 | 40.4121 | 2.598%
Tavistock | Keith Woith | Steve Steinberg |  | 1 | 1 | 2 | 1.667% | 1050 | 23.76 | 4.419%
T-Birds | Keith Woith | Steve Steinberg |  |  | 2 | 2 | 3.333% | 2100 | 42.656 | 4.923%
TGI Friday's | Michelle Hudson | Eric Hightower | 1 | 4 | 12 | 17 | 20% | 12600 | 390.5828 | 3.226%
The Kitchen | Keith Woith | Amanda Coulombe |  | 1 |  | 1 | 0% | 0 | 18.975 | 0%
The Peninsula Hotel | John Bestler | Amanda Coulombe |  |  | 1 | 1 | 1.667% | 1050 | 4.2126 | 24.93%
The Procaccianti Group | Brian Nolan | Steve Steinberg |  | 1 | 1 | 2 | 1.667% | 1050 | 48.06 | 2.185%
Tilted Kilt | Keith Woith | Steve Steinberg | 1 | 1 |  | 2 | 0% | 0 | 3.43 | 0%
Tommy Bahama | Rob Siler | Tim Cassidy |  | 1 | 1 | 2 | 1.667% | 1050 | 13.4663 | 7.797%
Travel Centers of America | John Bestler | Eric Hightower |  | 2 | 1 | 3 | 1.667% | 1050 | 75.514 | 1.39%
Tropical Smoothie Café | Brian Nolan | Tim Cassidy |  | 1 | 3 | 4 | 5% | 3150 | 290.598 | 1.084%
Trusthouse (Aladdin) | Brian Nolan | Eric Hightower | 1 | 1 | 2 | 4 | 3.333% | 2100 | 16.12 | 13.03%
Twin Peaks | Michelle Hudson | Eric Hightower | 3 | 5 | 3 | 11 | 5% | 3150 | 114.144 | 2.76%
Unidine | Brian Nolan | Steve Steinberg |  | 1 | 1 | 2 | 1.667% | 1050 | 5.1 | 20.59%
Verve Senior Living | Justin Prestinario | Steve Steinberg |  | 1 | 2 | 3 | 3.333% | 2100 | 34.155 | 6.148%
Veteran's Canteen Services | Rob Siler | Tim Cassidy | 1 | 1 | 2 | 4 | 3.333% | 2100 | 64.3125 | 3.265%
Vi | John Bestler | Amanda Coulombe |  | 2 | 2 | 4 | 3.333% | 2100 | 23.3377 | 8.998%
Village Tavern | Rob Siler | Emily Naufel | 4 | 4 |  | 8 | 0% | 0 | 22.1183 | 0%
Weber Grill | John Bestler | Tim Cassidy | 1 | 1 |  | 2 | 0% | 0 | 16.8301 | 0%
White Lodging | John Bestler | Amanda Coulombe |  | 1 |  | 1 | 0% | 0 | 23.3856 | 0%
Willow Valley Resort | Brian Nolan | Steve Steinberg | 1 |  | 1 | 2 | 1.667% | 1050 | 8.6404 | 12.15%
Wyndham Hotels | Brian Nolan | Tim Cassidy | 1 |  | 1 | 2 | 1.667% | 1050 | 24.0078 | 4.374%
YUM! Brands | Michelle Hudson | Emily Naufel | 8 | 15 | 18 | 41 | 30% | 18900 | 4650.062 | 0.4064%
Z Foods | Brian Nolan | Amanda Coulombe |  | 1 |  | 1 | 0% | 0 | 2.5666 | 0%

## MonthlyLauchesByCAM & AT
MONTHLY LAUNCHES BY CAM
Hours | (Multiple Items)
Count of MaxDate | Column Labels
| 2017 | [10 empty] | Grand Total
Row Labels | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov
Brian Nolan | 15 | 4 | 9 | 3 | 6 | 3 | 5 | 8 | 11 | 7 |  | 71
John Bestler | 19 | 2 | 2 | 1 | 5 | 3 | 5 |  | 10 | 2 | 1 | 50
Justin Prestinario | 12 | 3 |  | 9 | 3 | 1 | 4 | 3 | 3 | 6 |  | 44
Keith Woith | 12 | 8 | 3 | 5 | 2 | 4 | 8 | 8 | 2 | 5 |  | 57
Michelle Hudson | 16 | 3 | 2 | 6 | 8 | 3 | 3 | 2 | 6 | 6 |  | 55
Rob Siler | 13 | 2 | 1 | 3 | 4 | 1 | 3 |  | 4 | 2 | 3 | 36
Grand Total | 87 | 22 | 17 | 27 | 28 | 15 | 28 | 21 | 36 | 28 | 4 | 313
MONTHLY LAUNCHES BY AT
Hours | 2017 Jan: (Multiple Items)
Count of MaxDate | 2017 Jan: Column Labels
| 2017 Jan: 2017 | Grand Total
Row Labels | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov
All | [11 empty] | 2 | bar: 2017 Mar; 2017 Sep
Amanda Coulombe | 20 | 3 | 2 | 7 | 4 | 2 | 6 | 1 | 10 | 11 | 2 | 68
Emily Naufel | 17 | 4 | 1 | 5 | 13 | 4 | 4 |  | 10 | 1 | 2 | 61
Eric Hightower | 11 | 5 | 7 | 5 | 4 | 3 | 6 | 13 | 9 | 5 |  | 68
Steve Steinberg | 26 | 10 | 2 | 4 | 2 | 5 | 11 | 1 | 4 | 3 |  | 68
Tim Cassidy | 14 |  | 5 | 6 | 5 | 1 | 1 | 6 | 3 | 8 |  | 49
Grand Total | 88 | 22 | 18 | 27 | 28 | 15 | 28 | 21 | 37 | 28 | 4 | 316

## Data_ReqByMonth (hidden)
Hours | (Multiple Items)
Count of MaxDate | Column Labels
| 2017 | Grand Total
Row Labels
Jan | 88 | 88
Feb | 22 | 22
Mar | 18 | 18
Apr | 27 | 27
May | 28 | 28
Jun | 15 | 15
Jul | 28 | 28
Aug | 21 | 21
Sep | 37 | 37
Oct | 28 | 28
Nov | 4 | 4
Grand Total | 316 | 316

## DataValidation (hidden)
AssocList | RequestType | Status
AD | New Launch | Y
AK | Relaunch | N
AP | Request
JF
MG
NJ
RM
AT
BA
BH
JFH
KY
RD
TA
Cont. 1
Cont. 2
Cont. 3
Cont. 4
-

## Projections_Data
SalesPerson | OpsManager | Customer | ClientID | ? | 2017_ProjectedBusiness | Projected_On_7/7/2017 | ----> Current as of 7/2017 |  | Row Labels | Sum of 2017_ProjectedBusiness | Rank
Justin Prestinario | Open - Northeast | Starbucks | 169 | 1 | 5392.0104 | 5392.0104 |  | This data is from the 'Customers and Prospects' tab in the 2017 Projections file (root folder of Monthly Reports) | 4 Rivers Smokehouse | 9.75 | 144 | Update Steps: | 1) Copy / paste Columns A - G from most-current 'month' folder in Shared Files > Monthly Reports > 20XX
Michelle Hudson | Emily | YUM! Brands | 90 | 1 | 4658.5388 | 4658.5388 |  | File Modified Date: 4/13/17 | 7-Eleven | 0 | 219 |  | 2) Refresh Pivot table in Column K
Justin Prestinario | Eric | McDonald's | 62 | 1 | 3887.1882 | 3887.1882 |  |  | 85 ᵒC Café | 29.985 | 98 |  | 3) Update formula in M2 so last row in range is last customer cell in pivot table (ingore the grand total row at bottom)
John Bestler | Amanda | CKE | 45 | 1 | 3084.2205 | 2904.0205 |  |  | A.F. GILMORE | 0 | 219 |  | 4) Update same formula in 'Customers Not in Projections' table below pivot table
Keith Woith | Steve | DineEquity | 139 | 1 | 2881.345 | 2881.345 |  |  | AAFES | 0 | 219
Keith Woith | Amanda | Chipotle | 119 | 1 | 2190.0046 | 2186.6446 |  |  | Abuelo's | 0 | 219
John Bestler | Steve | Brookdale | 846 | 1 | 1760.0117 | 1760.0117 |  |  | Academia Barilla | 6.3 | 157
Justin Prestinario | Amanda | Dairy Queen | 48 | 1 | 1660.2895 | 1660.2895 |  |  | Accor Hotels | 0 | 219
Brian Nolan | Eric | Sodexo | 1437 | 1 | 1617.5854 | 1617.5854 |  |  | Ace Restaurant Group | 0 | 219
John Bestler | Open - Northeast | Panera Bread | 154 | 1 | 1608.3016 | 1608.3016 |  |  | Active Learning | 0 | 219
Brian Nolan | Eric | Compass Group | 672 | 1 | 1373.6837 | 1373.6837 |  |  | Adak Restaurants | 0 | 219
Rob Siler | Emily | Popeye's | 1573 | 1 | 1341.01 | 1341.01 |  |  | Affiniti Golf Partners, Inc | 0 | 219
Rob Siler | Steve | Bloomin' Brands | 1430 | 1 | 1227.8982 | 1227.8982 |  |  | Air Culinaire | 0 | 219
John Bestler | Amanda | Darden | 26 | 1 | 1137.0146 | 1137.0146 |  |  | Air Force | 0 | 219
Justin Prestinario | Emily | Buffalo Wild Wings | 638 | 1 | 1110.7753 | 1110.7753 |  |  | AIR NATIONAL GUARD | 0 | 219
Brian Nolan | Amanda | Aramark | 102 | 1 | 1019.3772 | 1019.3772 |  |  | Aliante | 0 | 219
Michelle Hudson | Eric | TGI Friday's | 338 | 1 | 946.3264 | 946.3264 |  |  | Alicarte | 0 | 219
Justin Prestinario | Open - Northeast | Caribou / Einstein | 1463 | 1 | 833.2063 | 833.2063 |  |  | Amazing Jake's Pizza | 0 | 219
Rob Siler | Amanda | Arby's | 4 | 1 | 572.004 | 572.004 |  |  | American Blue Ribbon Holdings | 0 | 219
John Bestler | Steve | Burger King | 9 | 1 | 526.8223 | 526.8223 |  |  | American Pie Pizza Company | 0 | 219
Brian Nolan | Emily | Golden Corral | 136 | 1 | 484.9309 | 484.9309 |  |  | America's Incredible Pizza | 0 | 219
Rob Siler | Steve | Checkers | 297 | 1 | 479.568 | 479.568 |  |  | Amici's East Coast Pizzeria | 0 | 219
John Bestler | Amanda | Red Lobster | 273 | 1 | 472.7816 | 472.7816 |  |  | Anaheim White House | 0 | 219
John Bestler | Open - Northeast | Steak 'n Shake | 436 | 1 | 458.2264 | 458.2264 |  |  | Anthology | 0 | 219
Brian Nolan | Eric | Hilton | 395 | 1 | 397.3699 | 397.3699 |  |  | APIO, Inc. | 0 | 219
Michelle Hudson | Steve | Stripes | 1555 | 1 | 385.8783 | 385.8783 |  |  | Apple Metro- Chevy's and Zanaro's | 0 | 219
Michelle Hudson | Steve | Corner Store | 1036 | 1 | 376.678 | 376.678 |  |  | Applewood | 0 | 219
Keith Woith | Open - Northeast | Jamba Juice | 1564 | 1 | 351.42 | 351.42 |  |  | Aramark | 1019.3772 | 16
Michelle Hudson | Open - Northeast | Cinemark | 949 | 1 | 323.8303 | 323.8303 |  |  | Arby's | 572.004 | 19
Rob Siler | Emily | Hooters of America | 440 | 1 | 293.44 | 293.44 |  |  | Areas USA | 34.4586 | 93
Brian Nolan | Open - Northeast | Tropical Smoothie Café | 1583 | 1 | 271.337 | 271.337 |  |  | Armadillo Willy's | 0 | 219
Keith Woith | Steve | Noodle's | 1561 | 1 | 250.1746 | 250.1746 |  |  | Arni's Restaurants | 0 | 219
John Bestler | Amanda | Potbelly's | 1553 | 1 | 207.317 | 207.317 |  |  | Avado Brands | 0 | 219
Brian Nolan | Emily | Racetrac | 1474 | 1 | 186.728 | 186.728 |  |  | Avendra Hospitality | 57.4339 | 74
Rob Siler | Open - Northeast | State of North Carolina | 1703 | 1 | 175.63 | 175.63 |  |  | Back Bay Restaurants | 0 | 219
John Bestler | Amanda | Hard Rock Café | 44 | 1 | 172.6134 | 172.6134 |  |  | Backyard Burgers | 0 | 219
Rob Siler | Emily | Honeybaked Ham | 1350 | 1 | 169.5307 | 169.5307 |  |  | Bakers Buddy | 0.84 | 208
Brian Nolan | Eric | Au Bon Pain | 1654 | 1 | 165.52 | 165.52 |  |  | Barnes & Noble Café | 0 | 219
Michelle Hudson | Emily | Cheddar's | 815 | 1 | 163.4867 | 163.4867 |  |  | Bass Pro Shop | 54.7881 | 76
Michelle Hudson | Steve | Corner Bakery | 296 | 1 | 160.476 | 160.476 |  |  | Batali & Bastianich Hospitality Group | 0 | 219
Brian Nolan | Emily | Friendly's | 1486 | 1 | 155.4498 | 155.4498 |  |  | BBL Hospitality | 0 | 219
Keith Woith | Emily | Guckenheimer | 669 | 1 | 150.4388 | 150.4388 |  |  | bd Mongolian Grill | 0 | 219
Justin Prestinario | Eric | Famous Dave's | 639 | 1 | 139.464 | 139.464 |  |  | Beef O' Brady's | 0 | 219
Rob Siler | Open - Northeast | Chick-fil-A | 19 | 1 | 135.84 | 135.84 |  |  | Ben Lomond Market | 0 | 219
Keith Woith | Steve | Shopper Events LLC | 1540 | 1 | 134.843 | 134.843 |  |  | Biaggi's | 0 | 219
Michelle Hudson | Steve | On The Border | 292 | 1 | 132.8836 | 132.8836 |  |  | Bice Ristorante | 0 | 219
Justin Prestinario | Eric | Fairmont Hotels | 224 | 1 | 128.0874 | 128.0874 |  |  | Bicos Restaurant Group | 0.9672 | 203
Brian Nolan | Eric | Interstate Hotels and Resorts | 871 | 1 | 127.3146 | 127.3146 |  |  | BJ's | 0 | 219
Rob Siler | Steve | Benihana | 1644 | 1 | 123.5699 | 123.5699 |  |  | Black Angus | 0 | 219
Justin Prestinario | Open - Northeast | Granite City | 1050 | 1 | 122.0796 | 122.0796 |  |  | Blaines No Way Joes | 0 | 219
Keith Woith | Amanda | Peet's Coffee & Tea | 629 | 1 | 120.7974 | 120.7974 |  |  | Bloomin' Brands | 1227.8982 | 13
Michelle Hudson | Eric | Twin Peaks | 1510 | 1 | 119.712 | 119.712 |  |  | Blue Mermaid Chowder House | 0 | 219
John Bestler | Steve | Hyatt Hotels | 396 | 1 | 119.3503 | 119.3503 |  |  | Blue Star Resort And Golf | 19.488 | 116
Michelle Hudson | Amanda | Ignite Restaurants | 1375 | 1 | 118.067 | 118.067 |  |  | BMG Restaurant Group | 0 | 219
Michelle Hudson | Eric | Fogo de Chao | 1507 | 1 | 113.385 | 113.385 |  |  | Bobby Cox | 0 | 219
John Bestler | Eric | Entertainment Cruises | 911 | 1 | 106.232 | 106.232 |  |  | Boddie-Noell, Inc. | 0 | 219
Michelle Hudson | Open - Northeast | Omni Hotels | 196 | 1 | 105.2747 | 105.2747 |  |  | Boise Consumer Cooperative | 4.5552 | 165
Justin Prestinario | Eric | Pizza Ranch | 1386 | 1 | 101.3851 | 101.3851 |  |  | Bokampers Sports Bar | 0.624 | 211
Brian Nolan | Amanda | Metz & Associates | 902 | 1 | 95.2403 | 95.2403 |  |  | Bond Street | 0 | 219
Keith Woith | Amanda | Real Mex | 1661 | 1 | 92.4 | 92.4 |  |  | Boston Market | 0 | 219
Justin Prestinario | Amanda | Bento Sushi | 1665 | 1 | 90.878 | 90.878 |  |  | Boykin | 0 | 219
Michelle Hudson | Amanda | Macaroni Grill | 1544 | 1 | 84.4294 | 84.4294 |  |  | Bravo | 0 | 219
Michelle Hudson | Emily | ClubCorp | 21 | 1 | 84.3107 | 84.3107 |  |  | Breckenridge Group | 0 | 219
Brian Nolan | Steve | Pret A Manger | 1574 | 1 | 81.015 | 81.015 |  |  | Brent's Deli | 0 | 219
John Bestler | Eric | Travel Centers of America | 1062 | 1 | 76.164 | 76.164 |  |  | Briad | 20.73 | 115
Keith Woith | Eric | Boudin Bakery | 1648 | 1 | 71.68 | 71.68 |  |  | Brinker | 0 | 219
Keith Woith | Amanda | Peter Piper Pizza | 569 | 1 | 71.3284 | 71.3284 |  |  | British Petroleum | 0 | 219
Keith Woith | Open - Northeast | Fox Restaurant Concepts | 940 | 1 | 70.3188 | 70.3188 |  |  | Brookdale | 1760.0117 | 7
Michelle Hudson | Steve | Newk's | 1399 | 1 | 69.007 | 69.007 |  |  | Brookhaven | -1.1183 | 603
Rob Siler | Open - Northeast | Veteran's Canteen Services | 1515 | 1 | 64.3125 | 64.3125 |  |  | Bruegger's | 0 | 219
Keith Woith | Amanda | Jackson's | 1569 | 1 | 61.6375 | 61.6375 |  |  | BTD Capital Partners | 0 | 219
Keith Woith | CORE | Pacifica Hotels | 1628 | 1 | 58.201 | 58.201 |  |  | Buca Di Beppo | 0 | 219
Keith Woith | Emily | Pinnacle Entertainment Group | 1593 | 1 | 57.8554 | 57.8554 |  |  | Buddy's Kitchen | 0 | 219
Brian Nolan | Amanda | Avendra Hospitality | 1487 | 1 | 57.4339 | 57.4339 |  |  | Buffalo Wild Wings | 1110.7753 | 15
Michelle Hudson | Open - Northeast | Mimi's Café | 1611 | 1 | 57.2 | 57.2 |  |  | Burger King | 526.8223 | 20
John Bestler | Amanda | Bass Pro Shop | 985 | 1 | 54.7881 | 54.7881 |  |  | Burgerville | 0 | 219
Keith Woith | Open - Northeast | Kona Grill | 1410 | 1 | 53.4261 | 53.4261 |  |  | Cadillac Ranch | 0 | 219
Brian Nolan | Open - Northeast | Pantry (Auntie M's) | 1442 | 1 | 52.6276 | 52.6276 |  |  | Café Rio | 0 | 219
Rob Siler | Amanda | Greenville School System | 1484 | 1 | 50.2771 | 50.2771 |  |  | Café Zupa's | 45.64 | 81
Brian Nolan | Open - Northeast | Wyndham Hotels | 518 | 1 | 46.2676 | 46.2676 |  |  | Campell Soup Co | 0 | 219
Keith Woith | Eric | Café Zupa's | 1563 | 1 | 45.64 | 45.64 |  |  | Cantex Senior Communities | 0 | 219
Keith Woith | Eric | Sunkist | 1183 | 1 | 43.417 | 43.417 |  |  | Captain D's | 0 | 219
Division | Steve | Lazy Dog Café | 1122 | 1 | 43.125 | 43.125 |  |  | Caribou / Einstein | 833.2063 | 18
Keith Woith | Steve | Cerca Trova | 1482 | 1 | 42.656 | 42.656 |  |  | Caritas St. Elizabeth's Medical Center | 0 | 219
Rob Siler | Emily | Taco Mac | 1541 | 1 | 41.9697 | 41.9697 |  |  | Carlson Hotels Worldwide | 0 | 219
John Bestler | Steve | Ocean Properties | 881 | 1 | 38.7064 | 38.7064 |  |  | Catch Restaurant | 0 | 219
John Bestler | Steve | LaRosa's | 1458 | 1 | 38.3102 | 38.3102 |  |  | Cathedral Hill Hotel | 0 | 219
Keith Woith | Emily | Sage Hospitality | 1224 | 1 | 37.5942 | 37.5942 |  |  | Cattleman's | 14.76 | 129
Brian Nolan | Emily | Mohonk | 1519 | 1 | 36.7272 | 36.7272 |  |  | Cedar Ridge Country Club | 0 | 219
Keith Woith | Emily | Luna Grill | 1678 | 1 | 35.88 | 35.88 |  |  | Centerplate | 6.4738 | 156
Michelle Hudson | Emily | Main Event | 1668 | 1 | 35.52 | 35.52 |  |  | Champ's Sports Bar & Grille | 0 | 219
Justin Prestinario | Steve | Verve Senior Living | 1584 | 1 | 34.7863 | 34.7863 |  |  | Charles Town Race & Slots | 0 | 219
John Bestler | Steve | Areas USA | 1450 | 1 | 34.4586 | 34.4586 |  |  | Checkers | 479.568 | 22
Brian Nolan | Steve | Delaware North | 1360 | 1 | 34.429 | 34.429 |  |  | Cheddar's | 163.4867 | 39
John Bestler | Emily | City BBQ | 1568 | 1 | 34.2906 | 34.2906 |  |  | Chicago City Centre Hotel | 0 | 219
John Bestler | Emily | Piada Group | 1591 | 1 | 30.492 | 30.492 |  |  | Chicago Paper Testing Laboratory | 0 | 219
Michelle Hudson | Emily | Cotton Patch Café | 1371 | 1 | 30.25 | 30.25 |  |  | Chick-fil-A | 135.84 | 44
Keith Woith | Steve | 85 ᵒC Café | 1524 | 1 | 29.985 | 29.985 |  |  | Children's Services Department | 0 | 219
Brian Nolan | Amanda | Glory Days | 1403 | 1 | 29.2645 | 29.2645 |  |  | Chipotle | 2190.0046 | 6
Michelle Hudson | Open - Northeast | Il Fornaio | 532 | 1 | 28.4748 | 28.4748 |  |  | Chiringo's Grayton Beach | 1.1832 | 199
John Bestler | Amanda | VI | 1401 | 1 | 27.9836 | 27.9836 |  |  | Christina's Fine Mexican Restaurant | 0 | 219
Rob Siler | Steve | iPic Theaters | 1565 | 1 | 27.9322 | 27.9322 |  |  | Chuck E. Cheese | 0 | 219
Rob Siler | Amanda | Margaritaville | 1440 | 1 | 26.4924 | 26.4924 |  |  | Cinemark | 323.8303 | 29
John Bestler | Amanda | Olga's Kitchen | 1608 | 1 | 25.025 | 25.025 |  |  | City BBQ | 34.2906 | 95
Brian Nolan | Emily | Shake Shack | 1662 | 1 | 24.3 | 24.3 |  |  | CKE | 3084.2205 | 4
Keith Woith | Steve | Tavistock | 1448 | 1 | 23.97 | 23.97 |  |  | ClubCorp | 84.3107 | 63
Keith Woith | Open - Northeast | Landry's | 418 | 1 | 23.8116 | 23.8116 |  |  | Coast Hotels and Resorts | 0 | 219
John Bestler | Amanda | White Lodging | 1459 | 1 | 23.6941 | 23.6941 |  |  | Coca-Cola | 0 | 219
Brian Nolan | Steve | The Procaccianti Group | 1612 | 1 | 22.8 | 22.8 |  |  | Cock of the Walk | 0 | 219
Brian Nolan | Eric | Cornell University | 1452 | 1 | 22.495 | 22.495 |  |  | Coffee Bean & Tea Leaf | 0 | 219
Keith Woith | Emily | Eureka! | 1595 | 1 | 22.27 | 22.27 |  |  | College of Holy Cross | 0 | 219
Keith Woith | Amanda | Snooze | 1589 | 1 | 22.1325 | 22.1325 |  |  | Colton's Steak House | 0 | 219
Brian Nolan | Amanda | Max Restaurant Group | 879 | 1 | 21.7006 | 21.7006 |  |  | Compass Group | 1373.6837 | 11
Rob Siler | Emily | Village Tavern | 945 | 1 | 20.7816 | 20.7816 |  |  | Con Agra | 0 | 219
Keith Woith | Open - Northeast | Briad | 1599 | 1 | 20.73 | 20.73 |  |  | Concessions Management Services | 0 | 219
Keith Woith | CORE | Blue Star Resort And Golf | 1617 | 1 | 19.488 | 19.488 |  |  | Connie's Pizza | 0 | 219
John Bestler | Open - Northeast | Weber Grill | 990 | 1 | 19.4058 | 19.4058 |  |  | Consolidated Restaurant Operations | 0 | 219
Keith Woith | Eric | Stanford University | 1495 | 1 | 19.314 | 19.314 |  |  | Copelands | 0 | 219
Michelle Hudson | Eric | Cooper's Hawk | 1690 | 1 | 18.424 | 18.424 |  |  | Cornell University | 22.495 | 110
Keith Woith | Steve | Desert Island Properties | 1518 | 1 | 18.232 | 18.232 |  |  | Corner Bakery | 160.476 | 40
Justin Prestinario | CORE | Crave America | 1653 | 1 | 18.2 | 18.2 |  |  | Corner Store | 376.678 | 27
Rob Siler | Emily | Popeyes - Idora Inc | 1632 | 1 | 18 | 18 |  |  | Cotton Patch Café | 30.25 | 97
John Bestler | Amanda | Creative Dining Services | 1404 | 1 | 17.251 | 17.251 |  |  | Craftworks | 0 | 219
Michelle Hudson | Emily | Truluck's | 1142 | 1 | 17.24 | 17.24 |  |  | Creative Dining Services | 17.251 | 123
Keith Woith | Open - Northeast | John's Incredible Pizza | 1558 | 1 | 16.8875 | 16.8875 |  |  | Culinaire Hospitality | 7.878 | 152
Brian Nolan | CORE | Carnegie Mellon University | 1641 | 1 | 16.0841 | 16.0841 |  |  | Cumberland Farms | 0 | 219
John Bestler | Emily | Gibson's Steakhouse | 1455 | 1 | 15.8024 | 15.8024 |  |  | Cups Frozen Yogurt | 0 | 219
John Bestler | CORE | Hopcat | 1671 | 1 | 14.84 | 14.84 |  |  | CWI | 0 | 219
Keith Woith | Amanda | Cattleman's | 1607 | 1 | 14.76 | 14.76 |  |  | Dairy Queen | 1660.2895 | 8
Keith Woith | Open - Northeast | Sauce | 1585 | 1 | 13.92 | 13.92 |  |  | Darden | 1137.0146 | 14
John Bestler | Open - Northeast | Marcus Hotels | 1525 | 1 | 13.853 | 13.853 |  |  | Dawn International | 0 | 219
Keith Woith | Open - Northeast | King's Seafood | 1352 | 1 | 13.7858 | 13.7858 |  |  | Deans Foods | 0 | 219
Brian Nolan | Open - Northeast | Pepperidge Farm | 1112 | 1 | 13.76 | 13.76 |  |  | DeCicco Food Market | 0 | 219
Rob Siler | Open - Northeast | Tommy Bahama | 898 | 1 | 13.4663 | 13.4663 |  |  | Delaware North | 34.429 | 94
John Bestler | Steve | Fresh Ideas | 1619 | 1 | 12.89 | 12.89 |  |  | Delmonico | 0 | 219
John Bestler | Steve | Four Winds Casino | 1037 | 1 | 12.7615 | 12.7615 |  |  | Delta Hotels and Resort | 0 | 219
Brian Nolan | Eric | Trusthouse (Aladdin) | 1562 | 1 | 12.69 | 12.69 |  |  | Denny's | 0 | 219
Brian Nolan | Eric | Linchris Hotels | 1492 | 1 | 11.79 | 11.79 |  |  | Desert Island Properties | 18.232 | 120
Justin Prestinario | CORE | Babalu Tacos & Tapas | 1698 | 1 | 11.275 | 11.275 |  |  | Detroit Entertainment | 0 | 219
Brian Nolan | Amanda | Kendall Senior Living | 1587 | 1 | 10.9725 | 10.9725 |  |  | Dickey's BBQ | 0 | 219
John Bestler | CORE | Select Restaurants | 76 | 1 | 10.68 | 10.68 |  |  | DineEquity | 2881.345 | 5
Division | Eric | General Mills | 38 | 1 | 10.575 | 10.575 |  |  | Disneyland | 0 | 219
Keith Woith | Amanda | The Kitchen | 1629 | 1 | 10.35 | 10.35 |  |  | Dole | 0 | 219
Rob Siler | Amanda | 4 Rivers Smokehouse | 1610 | 1 | 9.75 | 9.75 |  |  | Dollar General | 0 | 219
Brian Nolan | CORE | Guest Services | 1660 | 1 | 9.4046 | 9.4046 |  |  | Dollywood | 0 | 219
Brian Nolan | Steve | Willow Valley Resort | 835 | 1 | 9.072 | 9.072 |  |  | Donovan's Steak & Chop House | 5.22 | 161
Keith Woith | Emily | Lawry's | 1246 | 1 | 8.7844 | 8.7844 |  |  | Dreyer's Grand Ice Cream | 0 | 219
Keith Woith | CORE | Hotel Del Coronado | 1669 | 1 | 8.575 | 8.575 |  |  | Duffy | 0 | 219
John Bestler | CORE | BLD Brands | 1681 | 1 | 8.0649 | 8.0649 |  |  | Dunkin Brands | 0 | 219
Keith Woith | CORE | The Resort at Pelican Hill | 1160 | 1 | 8.008 | 8.008 |  |  | Dutch Wonderland | 0 | 219
Keith Woith | CORE | SR Restaurant Holdings Group | 1635 | 1 | 7.9 | 7.9 |  |  | E.A. Sween Company | 0 | 219
Brian Nolan | Eric | Culinaire Hospitality | 1493 | 1 | 7.878 | 7.878 |  |  | Eat N Park | 0 | 219
Michelle Hudson | CORE | Medieval Times | 1616 | 1 | 7.507 | 7.507 |  |  | Eatzi's | 0 | 219
Michelle Hudson | CORE | Walk-On's Enterprises | 1630 | 1 | 7.2 | 7.2 |  |  | ECOLAB FOOD SAFETY & HYGIENE SOLUTIONS | 0 | 219
Keith Woith | CORE | Spirit Mountain Casino | 1606 | 1 | 6.8544 | 6.8544 |  |  | ECOLAB INDONESIA | 0 | 219
Rob Siler | Emily | Centerplate | 1051 | 1 | 6.4738 | 6.4738 |  |  | ECOLAB KOREA | 0 | 219
John Bestler | Steve | Academia Barilla | 1504 | 1 | 6.3 | 6.3 |  |  | Ecolab Protect Healthcare | 0 | 219
Rob Siler | CORE | Offerdahl's Café & Grill | 1604 | 1 | 6.24 | 6.24 |  |  | Eggland's Best | 0 | 219
Division | CORE | Wingstop | 1701 | 1 | 6.125 | 6.125 |  |  | El Paso Grill & Bar-B-Que | 0 | 219
Brian Nolan | Steve | Seaport Boston | 1328 | 1 | 5.383 | 5.383 |  |  | Elbow River Casino | 0 | 219
Keith Woith | Steve | Donovan's Steak & Chop House | 816 | 1 | 5.22 | 5.22 |  |  | Elephant Bar | 0 | 219
John Bestler | Eric | Ohio State University | 1494 | 1 | 5.1759 | 5.1759 |  |  | Emeritus | 0 | 219
John Bestler | CORE | Anna's House | 1650 | 1 | 4.648 | 4.648 |  |  | Entertainment Cruises | 106.232 | 56
Keith Woith | CORE | Graduate Tempe | 1600 | 1 | 4.634 | 4.634 |  |  | Epiri Foods | 0 | 219
Keith Woith | CORE | Boise Consumer Cooperative | 1621 | 1 | 4.5552 | 4.5552 |  |  | Esplanade Restaurants LTD | 0 | 219
Brian Nolan | Eric | Starwood | 829 | 1 | 4.4633 | 4.4633 |  |  | ESPN Zone | 0 | 219
Justin Prestinario | Eric | SilverBirch Hotels | 1187 | 1 | 4.29 | 4.29 |  |  | Executive Caterers | 0 | 219
John Bestler | Amanda | The Peninsula Hotel | 1252 | 1 | 4.2126 | 4.2126 |  |  | Fairmont Hotels | 128.0874 | 47
Rob Siler | CORE | Fox Bros BBQ | 1633 | 1 | 4.15 | 4.15 |  |  | Famous Dave's | 139.464 | 43
Rob Siler | CORE | Daly Seven Inc. | 1686 | 1 | 4.06 | 4.06 |  |  | Fazoli's | 0 | 219
Brian Nolan | Steve | Unidine | 1577 | 1 | 3.838 | 3.838 |  |  | Feld Entertainment | 0 | 219
Keith Woith | CORE | Chinook Winds Casino Resort | 1624 | 1 | 3.8292 | 3.8292 |  |  | Flat Out Crazy | 0 | 219
John Bestler | CORE | Quest Food Management Services | 1536 | 1 | 3.6 | 3.6 |  |  | Flying Food Group | 0 | 219
Justin Prestinario | Open - Northeast | Atrium Hospitality | 1666 | 1 | 3.51 | 3.51 |  |  | Flying J | 0 | 219
Keith Woith | CORE | Magee's Kitchen | 1615 | 1 | 3.427 | 3.427 |  |  | Fogo de Chao | 113.385 | 55
Rob Siler | Eric | LTP Management Group | 1498 | 1 | 3.18 | 3.18 |  |  | Food and Beverage Concepts, Inc. | 0 | 219
Brian Nolan | CORE | Schick Manufacturing Inc | 1638 | 1 | 3.025 | 3.025 |  |  | Food Brand IDS | 0 | 219
Keith Woith | Eric | Silver Cloud | 1427 | 1 | 2.611 | 2.611 |  |  | Food Marketing Institute | 0 | 219
Keith Woith | CORE | Rebecca Jean Catering | 1643 | 1 | 2.55 | 2.55 |  |  | Four M Capital LLC - BWW | 0 | 219
Keith Woith | Emily | Grand American Hotel | 1538 | 1 | 2.504 | 2.504 |  |  | Four Seasons Hotel | 0 | 219
Justin Prestinario | CORE | PizzaRev | 1642 | 1 | 2.4 | 2.4 |  |  | Four Winds Casino | 12.7615 | 136
Rob Siler | CORE | Posto 9 | 1627 | 1 | 2.3 | 2.3 |  |  | Fox Bros BBQ | 4.15 | 169
Keith Woith | CORE | Shore | 1699 | 1 | 2.1 | 2.1 |  |  | Fox Restaurant Concepts | 70.3188 | 68
Justin Prestinario | CORE | MLY Investments | 1605 | 1 | 2.028 | 2.028 |  |  | Frankie Bones | 0 | 219
Rob Siler | Amanda | Darden Franchise Group | 1682 | 1 | 2.0074 | 2.0074 |  |  | Fransican Communities | 0 | 219
Brian Nolan | Amanda | Genji Inc. | 1069 | 1 | 1.8718 | 1.8718 |  |  | Fresh City | 0 | 219
Keith Woith | Eric | Quorum | 1355 | 1 | 1.818 | 1.818 |  |  | Fresh Ideas | 12.89 | 135
Brian Nolan | CORE | Lobster Place Seafood Market | 1603 | 1 | 1.7952 | 1.7952 |  |  | Friendly's | 155.4498 | 41
Brian Nolan | CORE | Best Western Premier - The Central Hotel | 1625 | 1 | 1.7 | 1.7 |  |  | Frito-Lay | 0 | 219
Michelle Hudson | CORE | Georgia Blue | 1676 | 1 | 1.7 | 1.7 |  |  | Furr's Family Dining | 0 | 219
Keith Woith | CORE | Philz Coffee | 1685 | 1 | 1.589 | 1.589 |  |  | Galli Produce | 0 | 219
Justin Prestinario | Emily | Humber College | 1523 | 1 | 1.5036 | 1.5036 |  |  | Garbanzo | 0.93 | 205
Rob Siler | CORE | Mangos Tropical Cafe | 1623 | 1 | 1.48 | 1.48 |  |  | Gateway Golf & Country Club | 0 | 219
Brian Nolan | CORE | Velvet Taco | 1696 | 1 | 1.45 | 1.45 |  |  | Gaylord D.C. | 0 | 219
Justin Prestinario | CORE | PhaseNext Hospitality | 1651 | 1 | 1.4 | 1.4 |  |  | Gaylord Palm | 0 | 219
Keith Woith | Steve | Tilted Kilt | 1222 | 1 | 1.372 | 1.372 |  |  | Gaylord TX | 0 | 219
Rob Siler | CORE | Plantation Village | 1649 | 1 | 1.36 | 1.36 |  |  | General Mills | 10.575 | 142
Michelle Hudson | CORE | Mad Taco | 1667 | 1 | 1.26 | 1.26 |  |  | Genji Inc. | 1.8718 | 186
Rob Siler | CORE | Chiringo's Grayton Beach | 1614 | 1 | 1.1832 | 1.1832 |  |  | GFSI | 0 | 219
Rob Siler | CORE | Mi Casa | 1688 | 1 | 1.1 | 1.1 |  |  | Gibson's Steakhouse | 15.8024 | 127
John Bestler | CORE | Roy Rogers | 1657 | 1 | 1.08 | 1.08 |  |  | Glory Days | 29.2645 | 99
Rob Siler | CORE | Bagel King Bakery | 1655 | 1 | 0.98 | 0.98 |  |  | Golden Corral | 484.9309 | 21
Keith Woith | Eric | Bicos Restaurant Group | 1245 | 1 | 0.9672 | 0.9672 |  |  | Google | 0 | 219
Keith Woith | CORE | CNR Enterprises Inc | 1674 | 1 | 0.954 | 0.954 |  |  | Graduate Tempe | 4.634 | 164
Keith Woith | Open - Northeast | Garbanzo | 1370 | 1 | 0.93 | 0.93 |  |  | Grand American Hotel | 2.504 | 180
Keith Woith | CORE | PFC at Omni Resorts LaCosta | 1670 | 1 | 0.9 | 0.9 |  |  | Grandma's Restaurant Company | 0 | 219
Brian Nolan | Eric Hightower | Freddy's Frozen Custard | 1693 | 1 | 0.88 | 0.88 |  |  | Granite City | 122.0796 | 50
John Bestler | CORE | Bakers Buddy | 1613 | 1 | 0.84 | 0.84 |  |  | Great American Diner | 0 | 219
John Bestler | CORE | Holiday Inn Resort Orlando | 1694 | 1 | 0.8 | 0.8 |  |  | Great Wolf Lodge | 0 | 219
Brian Nolan | CORE | 716 Bar & Grill | 1672 | 1 | 0.69 | 0.69 |  |  | Green Mill | 0 | 219
Rob Siler | CORE | Bokampers Sports Bar | 1601 | 1 | 0.624 | 0.624 |  |  | Greenville School System | 50.2771 | 79
Brian Nolan | CORE | AXA US | 1640 | 1 | 0.6 | 0.6 |  |  | Guckenheimer | 150.4388 | 42
Michelle Hudson | Steve | My Fit FOODS | 1473 | 1 | 0.49984 | 0.49984 |  |  | Hard Rock Café | 172.6134 | 36
John Bestler | CORE | Columbia County Jail | 1658 | 1 | 0.4 | 0.4 |  |  | Hard Rock Hotel Las Vegas | 0 | 219
John Bestler | CORE | The Violet Hour | 1656 | 1 | 0.4 | 0.4 |  |  | Harrah's | 0 | 219
Brian Nolan | CORE | Copperhead Grille | 1663 | 1 | 0.375 | 0.375 |  |  | Hartsfield Hospitality | 0 | 219
Keith Woith | CORE | The Scarlet Huntington | 1684 | 1 | 0.365 | 0.365 |  |  | Harvard Club of Boston | 0 | 219
John Bestler | CORE | Restoration Hardware | 1675 | 1 | 0.338 | 0.338 |  |  | Health Alliance | 0 | 219
Brian Nolan | Amanda | OTG Management | 977 | 1 | 0 | 0 |  |  | H-E-B Grocery Co. | 0 | 219
Keith Woith | Amanda | Pizza Rev | 1490 | 1 | 0 | 0 |  |  | Hershey's | 0 | 219
Keith Woith | Amanda | Pinkberry | 1454 | 1 | 0 | 0 |  |  | Hillstone Retaurant Group | 0 | 219
Rob Siler | Amanda | Tim Drum | 1436 | 1 | 0 | 0 |  |  | Hilton | 397.3699 | 25
Yalcin Oksal | Amanda | Villa Enterprises | 1407 | 1 | 0 | 0 |  |  | HMQ | 0 | 219
Yalcin Oksal | Amanda | Fresh City | 1397 | 1 | 0 | 0 |  |  | HMS Host | 0 | 219
Michelle Hudson | Amanda | Sonic | 1396 | 1 | 0 | 0 |  |  | Holiday Inn - Saratoga Springs | 0 | 219
Michelle Hudson | Amanda | Valley Hospitality | 1393 | 1 | 0 | 0 |  |  | Honeybaked Ham | 169.5307 | 37
Brian Nolan | Amanda | New England Development | 1392 | 1 | 0 | 0 |  |  | HoneyBaked Ham California | 0 | 219
Michelle Hudson | Amanda | Bobby Cox | 1380 | 1 | 0 | 0 |  |  | Hooters of America | 293.44 | 30
Yalcin Oksal | Amanda | Hillstone Retaurant Group | 1362 | 1 | 0 | 0 |  |  | Hootwinc | 0 | 219
John Bestler | Amanda | Arni's Restaurants | 1347 | 1 | 0 | 0 |  |  | Houlihan's | 0 | 219
John Bestler | Steve | Twisted Rooster | 1428 | 1 | 0 | 0 |  |  | HuHot Mongolian Grill | 0 | 219
Brian Nolan | Amanda | Dollywood | 1343 | 1 | 0 | 0 |  |  | Humber College | 1.5036 | 192
Division | Division | Other Historical customers/adjustments | N/A | 1 | 0 | 0 |  |  | Hurricane Brands | 0 | 219
Miriam Eisenberg | Steve | Norovirus Project | 2284 | 1 | 0 | 0 |  |  | Hyatt Hotels | 119.3503 | 53
Division | Eric | Protect Healthcare | 2233 | 1 | 0 | 0 |  |  | Ignite Restaurants | 118.067 | 54
Michelle Hudson | Steve | Sunoco | 1618 | 1 | 0 | 0 |  |  | Il Fornaio | 28.4748 | 100
John Bestler | Steve | Chicago Paper Testing Laboratory | 1502 | 1 | 0 | 0 |  |  | Imagin Asia | 0 | 219
John Bestler | Open - Northeast | National Food Laboratory | 1501 | 1 | 0 | 0 |  |  | Indel Warehouse | 0 | 219
Yalcin Oksal | Amanda | Back Bay Restaurants | 1326 | 1 | 0 | 0 |  |  | Indigo Joe's | 0 | 219
Keith Woith | Emily | The Tao Group | 1485 | 1 | 0 | 0 |  |  | Intercontinental Hotel Group | 0 | 219
Brian Nolan | Eric | MapCo | 1478 | 1 | 0 | 0 |  |  | Interstate Hotels and Resorts | 127.3146 | 48
Brian Nolan |  | Scarborough Town Centre | 1470 | 1 | 0 | 0 |  |  | Intrawest | 0 | 219
Keith Woith | Open - Northeast | Johnny Rockets | 1468 | 1 | 0 | 0 |  |  | iPic Theaters | 27.9322 | 102
Michelle Hudson | Emily | Red Mango | 1460 | 1 | 0 | 0 |  |  | Ippolitos | 0 | 219
Yalcin Oksal | Emily | Cumberland Farms | 1456 | 1 | 0 | 0 |  |  | Isle of Capri | 0 | 219
Brian Nolan | Amanda | Ping Pong | 1323 | 1 | 0 | 0 |  |  | ISTITUTO CULINARIO % C BAUTISTA | 0 | 219
Michelle Hudson | Eric | Cups Frozen Yogurt | 1451 | 1 | 0 | 0 |  |  | J Alexanders | 0 | 219
Keith Woith | Emily | Google | 1447 | 1 | 0 | 0 |  |  | J. Leek Associates | 0 | 219
Brian Nolan | Amanda | Epiri Foods | 1320 | 1 | 0 | 0 |  |  | Jackson's | 61.6375 | 71
Keith Woith |  | Madison Holdings | 1420 | 1 | 0 | 0 |  |  | Jamba Juice | 351.42 | 28
John Bestler | Amanda | Round the Clock Restaurants | 1305 | 1 | 0 | 0 |  |  | Johnny Rockets | 0 | 219
Brian Nolan | Amanda | Duffy | 1250 | 1 | 0 | 0 |  |  | John's Incredible Pizza | 16.8875 | 125
Yalcin Oksal | Amanda | Woods Services | 1209 | 1 | 0 | 0 |  |  | Johnson and Wales | 0 | 219
Division | Amanda | MotoMart | 1180 | 1 | 0 | 0 |  |  | Jucy's Hamburgers | 0 | 219
Brian Nolan | Amanda | Salem Senior | 1176 | 1 | 0 | 0 |  |  | Kabuki Japaneese Restaurant | 0 | 219
Yalcin Oksal |  | BBL Hospitality | 1391 | 1 | 0 | 0 |  |  | Karger Libri | 0 | 219
Michelle Hudson | Eric | Delmonico | 1390 | 1 | 0 | 0 |  |  | K-Bob's | 0 | 219
Michelle Hudson | Steve | Air Force | 1388 | 1 | 0 | 0 |  |  | Keller Army Community Hospital | 0 | 219
John Bestler | Eric | Adak Restaurants | 1387 | 1 | 0 | 0 |  |  | Kellogg's | 0 | 219
Keith Woith | Eric | Rolling Stone | 1385 | 1 | 0 | 0 |  |  | Kendall Senior Living | 10.9725 | 140
Brian Nolan | Steve | Penn National Gaming | 1384 | 1 | 0 | 0 |  |  | Kendall Village Diner | 0 | 219
Brian Nolan |  | Ovation Brands | 1383 | 1 | 0 | 0 |  |  | King's Seafood | 13.7858 | 132
Brian Nolan | Amanda | Blaines No Way Joes | 1156 | 1 | 0 | 0 |  |  | Kirro LLC | 0 | 219
Division |  | Ecolab Protect Healthcare | 1373 | 1 | 0 | 0 |  |  | Kisco Senior Living | 0 | 219
Brian Nolan |  | Gaylord Palm | 1368 | 1 | 0 | 0 |  |  | Kona Grill | 53.4261 | 77
Keith Woith | Eric | Millenium Resorts | 1364 | 1 | 0 | 0 |  |  | Kraft Foods | 0 | 219
Brian Nolan | Amanda | Tumbleweed | 1154 | 1 | 0 | 0 |  |  | Krispy Kreme | 0 | 219
Michelle Hudson | Emily | Studio Movie Grill | 1356 | 1 | 0 | 0 |  |  | Kroger | 0 | 219
John Bestler |  | Flat Out Crazy | 1351 | 1 | 0 | 0 |  |  | Krome Detention Center | 0 | 219
Keith Woith | Amanda | Pasta Pomodoro | 1148 | 1 | 0 | 0 |  |  | La Costa Resort | 0 | 219
Yalcin Oksal | Amanda | Caritas St. Elizabeth's Medical Center | 1145 | 1 | 0 | 0 |  |  | La Tasca | 0 | 219
Brian Nolan | Steve | Royal Sonesta Hotel | 1339 | 1 | 0 | 0 |  |  | Labo's Roadhouse | 0 | 219
Yalcin Oksal |  | Ship & Anchor | 1338 | 1 | 0 | 0 |  |  | Lake Las Vegas | 0 | 219
Yalcin Oksal | Eric | Parsole | 1334 | 1 | 0 | 0 |  |  | Land O Lakes | 0 | 219
Division |  | J. Leek Associates | 1332 | 1 | 0 | 0 |  |  | Landry's | 23.8116 | 107
Brian Nolan | Amanda | Nando's | 1105 | 1 | 0 | 0 |  |  | Larchmont Tavern | 0 | 219
Keith Woith |  | Pollo Campero | 1325 | 1 | 0 | 0 |  |  | LaRosa's | 38.3102 | 87
Division |  | Connie's Pizza | 1324 | 1 | 0 | 0 |  |  | Lattanzi Ristorante | 0 | 219
Brian Nolan | Amanda | J Alexanders | 1097 | 1 | 0 | 0 |  |  | Lawry's | 8.7844 | 147
Brian Nolan | Amanda | Labo's Roadhouse | 1093 | 1 | 0 | 0 |  |  | Lazy Dog Café | 43.125 | 83
Division |  | E.A. Sween Company | 1318 | 1 | 0 | 0 |  |  | Leprino | 0 | 219
Keith Woith |  | Bice Ristorante | 1317 | 1 | 0 | 0 |  |  | Linchris Hotels | 11.79 | 138
Keith Woith |  | Value Cold Storage | 1307 | 1 | 0 | 0 |  |  | Lobster Place Seafood Market | 1.7952 | 188
Elizabeth Johnston | Amanda | S & S Cafeteria | 1086 | 1 | 0 | 0 |  |  | Logan's Roadhouse | 0 | 219
Yalcin Oksal | Steve | Prospera Hospitality | 1292 | 1 | 0 | 0 |  |  | LoneStar Group of Companies | 0 | 219
Yalcin Oksal |  | Margaritas | 1278 | 1 | 0 | 0 |  |  | LSG Sky Chef | 0 | 219
|  | Fransican Communities | 1277 | 1 | 0 | 0 |  |  | LTP Management Group | 3.18 | 176
Keith Woith |  | ESPN Zone | 1271 | 1 | 0 | 0 |  |  | Luxury Resorts | 0 | 219
John Bestler | Eric | O'Reilly Group | 1259 | 1 | 0 | 0 |  |  | M&M Mars | 0 | 219
Keith Woith |  | Three Square | 1258 | 1 | 0 | 0 |  |  | Macaroni Grill | 84.4294 | 62
Keith Woith |  | Sprouts | 1257 | 1 | 0 | 0 |  |  | Madison Holdings | 0 | 219
Yalcin Oksal |  | MGM Grand | 1251 | 1 | 0 | 0 |  |  | Magee's Kitchen | 3.427 | 175
Brian Nolan | Amanda | Turner | 1082 | 1 | 0 | 0 |  |  | Main Street Restaurant Group | 0 | 219
Keith Woith |  | Terranea Resorts | 1249 | 1 | 0 | 0 |  |  | Malt-O-Meal | 0 | 219
Keith Woith |  | Willow Creek Assisted Living | 1248 | 1 | 0 | 0 |  |  | Mambo | -1.158 | 604
|  | Obento-ya | 1247 | 1 | 0 | 0 |  |  | Mandarian House | 0 | 219
Yalcin Oksal |  | RLB | 1243 | 1 | 0 | 0 |  |  | Mangos Tropical Cafe | 1.48 | 193
Yalcin Oksal |  | Sea to You | 1242 | 1 | 0 | 0 |  |  | MapCo | 0 | 219
Keith Woith | Eric | PB&J Restaurants | 1241 | 1 | 0 | 0 |  |  | Marcus Hotels | 13.853 | 131
Michelle Hudson | Emily | Air Culinaire | 1240 | 1 | 0 | 0 |  |  | Margaritas | 0 | 219
Yalcin Oksal |  | Wawa | 1239 | 1 | 0 | 0 |  |  | Margaritaville | 26.4924 | 103
Keith Woith | Eric | Smashburger | 1237 | 1 | 0 | 0 |  |  | Mario Batali's Restaurants | 0 | 219
Division | Division | Karger Libri | 1234 | 1 | 0 | 0 |  |  | Marx Hotel | 0 | 219
Yalcin Oksal |  | Cadillac Ranch | 1231 | 1 | 0 | 0 |  |  | Mary Ruth Inc. | 0 | 219
Yalcin Oksal | Steve | Four M Capital LLC - BWW | 1230 | 1 | 0 | 0 |  |  | Mastro's Restaurants | 0 | 219
Yalcin Oksal |  | Taj Mahal Columbus | 1227 | 1 | 0 | 0 |  |  | Max Restaurant Group | 21.7006 | 113
Yalcin Oksal |  | RIT - Dining Services | 1226 | 1 | 0 | 0 |  |  | McDonald's | 3887.1882 | 3
Keith Woith |  | Rancherito's Mexican Foods | 1225 | 1 | 0 | 0 |  |  | Meadowood | 0 | 219
Keith Woith |  | Revolution Foods | 1223 | 1 | 0 | 0 |  |  | MedAssets | 0 | 219
Keith Woith |  | Kisco Senior Living | 1221 | 1 | 0 | 0 |  |  | Medieval Times | 7.507 | 153
Yalcin Oksal |  | Galli Produce | 1216 | 1 | 0 | 0 |  |  | Metz & Associates | 95.2403 | 59
Division |  | Smithfield | 1214 | 1 | 0 | 0 |  |  | Metz Enterprises | 0 | 219
Justin Prestinario |  | Tortoise Restaurant Group | 1213 | 1 | 0 | 0 |  |  | MGM Grand | 0 | 219
Brian Nolan | Amanda | Puleos | 1077 | 1 | 0 | 0 |  |  | Midopa Asian Market | 0 | 219
Keith Woith |  | El Paso Grill & Bar-B-Que | 1195 | 1 | 0 | 0 |  |  | Mike's Restaurants | 0 | 219
|  | CWI | 1194 | 1 | 0 | 0 |  |  | Millenium Resorts | 0 | 219
John Bestler | Steve | Feld Entertainment | 1191 | 1 | 0 | 0 |  |  | Miller Oil Company | 0 | 219
| Steve | Kendall Village Diner | 1190 | 1 | 0 | 0 |  |  | Mimi's Café | 57.2 | 75
Elizabeth Johnston | Steve | The Florida Hotel and Conference Center | 1189 | 1 | 0 | 0 |  |  | Mission Valley Resorts | 0 | 219
| Steve | Hootwinc | 1185 | 1 | 0 | 0 |  |  | MLY Investments | 2.028 | 184
Yalcin Oksal | Amanda | Harvard Club of Boston | 1038 | 1 | 0 | 0 |  |  | Mohonk | 36.7272 | 89
Yalcin Oksal |  | Peter Geyer's Steakhouse | 1179 | 1 | 0 | 0 |  |  | Montage Resort and Spa | 0 | 219
Yalcin Oksal | Steve | bd Mongolian Grill | 1177 | 1 | 0 | 0 |  |  | MORTON'S OF CHICAGO | 0 | 219
| Amanda | Blue Mermaid Chowder House | 974 | 1 | 0 | 0 |  |  | MotoMart | 0 | 219
John Bestler |  | Plum Hollow Country Club | 1165 | 1 | 0 | 0 |  |  | My Fit FOODS | 0.49984 | 213
Keith Woith |  | Sapphire | 1163 | 1 | 0 | 0 |  |  | Nando's | 0 | 219
Keith Woith |  | Tiggos | 1162 | 1 | 0 | 0 |  |  | Nantucket Island Resorts | 0 | 219
Keith Woith | Eric | Anaheim White House | 1159 | 1 | 0 | 0 |  |  | National Food Laboratory | 0 | 219
Keith Woith |  | Aliante | 1158 | 1 | 0 | 0 |  |  | NATIONAL RESTAURANT ASSOC | 0 | 219
Justin Prestinario | Amanda | 7-Eleven | 845 | 1 | 0 | 0 |  |  | Nestle | 0 | 219
Michelle Hudson | Amanda | Accor Hotels | 804 | 1 | 0 | 0 |  |  | NEW CASTLE HOTELS | 0 | 219
Yalcin Oksal |  | Executive Caterers | 1151 | 1 | 0 | 0 |  |  | New England Development | 0 | 219
Keith Woith | Open - Northeast | Mastro's Restaurants | 1149 | 1 | 0 | 0 |  |  | New Seasons Market | 0 | 219
Brian Nolan | Amanda | La Tasca | 734 | 1 | 0 | 0 |  |  | New York Office of Mental Health | 0 | 219
John Bestler | Amanda | Boddie-Noell, Inc. | 590 | 1 | 0 | 0 |  |  | Newk's | 69.007 | 69
John Bestler |  | Smokey Bones | 1130 | 1 | 0 | 0 |  |  | Niagra Hospitality | 0 | 219
Division |  | Supply Chain | 1129 | 1 | 0 | 0 |  |  | Noodle's | 250.1746 | 32
Division |  | GFSI | 1128 | 1 | 0 | 0 |  |  | Norovirus Project | 0 | 219
|  | Sybergs | 1127 | 1 | 0 | 0 |  |  | Northland Cranberries | 0 | 219
Yalcin Oksal |  | Flying Food Group | 1126 | 1 | 0 | 0 |  |  | Northwestern Hospital | 0 | 219
Yalcin Oksal |  | Food and Beverage Concepts, Inc. | 1124 | 1 | 0 | 0 |  |  | NRA | 0 | 219
|  | NYPD Pizza | 1123 | 1 | 0 | 0 |  |  | NYPD Pizza | 0 | 219
|  | Patton State Hospital | 1121 | 1 | 0 | 0 |  |  | Obento-ya | 0 | 219
Keith Woith |  | Emeritus | 1120 | 1 | 0 | 0 |  |  | Ocean Properties | 38.7064 | 86
Elizabeth Johnston | Steve | Trinity Group | 1116 | 1 | 0 | 0 |  |  | O'Charley's | 0 | 219
Yalcin Oksal |  | Pettibone's Grille | 1114 | 1 | 0 | 0 |  |  | Offerdahl's Café & Grill | 6.24 | 158
|  | Cock of the Walk | 1113 | 1 | 0 | 0 |  |  | Ohio State University | 5.1759 | 162
|  | Mandarian House | 1111 | 1 | 0 | 0 |  |  | Old Spaghetti Factory | 0 | 219
Division |  | Leprino | 1109 | 1 | 0 | 0 |  |  | Olga's Kitchen | 25.025 | 104
Division |  | Tommy Doyle | 1108 | 1 | 0 | 0 |  |  | Omni Hotels | 105.2747 | 57
|  | Dutch Wonderland | 1107 | 1 | 0 | 0 |  |  | On The Border | 132.8836 | 46
Brian Nolan |  | Gaylord TX | 1106 | 1 | 0 | 0 |  |  | One Sunset | 0 | 219
Justin Prestinario | Amanda | Westmont Hospitality | 556 | 1 | 0 | 0 |  |  | Open Classes | 0 | 219
Michelle Hudson |  | Cantex Senior Communities | 1104 | 1 | 0 | 0 |  |  | Orange County Schools | 0 | 219
Brian Nolan |  | Captain D's | 1103 | 1 | 0 | 0 |  |  | O'Reilly Group | 0 | 219
Yalcin Oksal |  | Ristorante Toscano | 1098 | 1 | 0 | 0 |  |  | OTG Management | 0 | 219
Brian Nolan | Amanda | Fazoli's | 334 | 1 | 0 | 0 |  |  | Other Historical customers/adjustments | 0 | 219
|  | Applewood | 1096 | 1 | 0 | 0 |  |  | Ovation Brands | 0 | 219
|  | Frankie Bones | 1094 | 1 | 0 | 0 |  |  | Pacifica Hotels | 58.201 | 72
Brian Nolan | Amanda | Ruby Tuesday | 163 | 1 | 0 | 0 |  |  | Palermo's Pizza | 0 | 219
Yalcin Oksal |  | Mario Batali's Restaurants | 1091 | 1 | 0 | 0 |  |  | Panera Bread | 1608.3016 | 10
|  | Rhodes Ranch Golf Club | 1089 | 1 | 0 | 0 |  |  | Pantry (Auntie M's) | 52.6276 | 78
Division | Amanda | Eggland's Best | 31 | 1 | 0 | 0 |  |  | Parsole | 0 | 219
Brian Nolan |  | Gaylord D.C. | 1085 | 1 | 0 | 0 |  |  | Pasta Pomodoro | 0 | 219
Yalcin Oksal |  | Nantucket Island Resorts | 1084 | 1 | 0 | 0 |  |  | Pasta Resources | 0 | 219
Yalcin Oksal |  | The Venetian Hotel | 1083 | 1 | 0 | 0 |  |  | Patton State Hospital | 0 | 219
Rob Siler | Amanda | Coca-Cola | 22 | 1 | 0 | 0 |  |  | Paul Lee's Chinese Kitchen | 0 | 219
Michelle Hudson |  | BJ's | 1081 | 1 | 0 | 0 |  |  | PB&J Restaurants | 0 | 219
|  | Anthology | 1080 | 1 | 0 | 0 |  |  | Peet's Coffee & Tea | 120.7974 | 51
Michelle Hudson | Amanda | Chuck E. Cheese | 1596 | 1 | 0 | 0 |  |  | Penn National Gaming | 0 | 219
Elizabeth Johnston |  | Rita Restaurant Corp | 1076 | 1 | 0 | 0 |  |  | Pepperidge Farm | 13.76 | 133
Keith Woith |  | Kabuki Japaneese Restaurant | 1075 | 1 | 0 | 0 |  |  | Perkins | 0 | 219
Brian Nolan |  | Smokey Mountain | 1074 | 1 | 0 | 0 |  |  | Peter Geyer's Steakhouse | 0 | 219
Yalcin Oksal |  | Buddy's Kitchen | 1073 | 1 | 0 | 0 |  |  | Peter Piper Pizza | 71.3284 | 67
Brian Nolan |  | Kirro LLC | 1072 | 1 | 0 | 0 |  |  | Pettibone's Grille | 0 | 219
|  | Uwink | 1071 | 1 | 0 | 0 |  |  | PF Chang's | 0 | 219
|  | Ippolitos | 1067 | 1 | 0 | 0 |  |  | Piada Group | 30.492 | 96
Keith Woith |  | Elephant Bar | 1066 | 1 | 0 | 0 |  |  | PICCADILLY | 0 | 219
Yalcin Oksal |  | Waterside Group | 1065 | 1 | 0 | 0 |  |  | Pick Up Stix | 0 | 219
Elizabeth Johnston | Steve | Gateway Golf & Country Club | 1064 | 1 | 0 | 0 |  |  | Pickle Barrel | 0 | 219
|  | Bond Street | 1063 | 1 | 0 | 0 |  |  | Pierce's Supermarkets | 0 | 219
Keith Woith |  | Roka Akor | 1060 | 1 | 0 | 0 |  |  | Ping Pong | 0 | 219
Yalcin Oksal |  | Red Coach Inn | 1059 | 1 | 0 | 0 |  |  | Pinkberry | 0 | 219
Yalcin Oksal |  | DeCicco Food Market | 1055 | 1 | 0 | 0 |  |  | Pinnacle Entertainment Group | 57.8554 | 73
Michelle Hudson |  | Jucy's Hamburgers | 1054 | 1 | 0 | 0 |  |  | Pizza Ranch | 101.3851 | 58
|  | Food Marketing Institute | 1053 | 1 | 0 | 0 |  |  | Pizza Rev | 0 | 219
Yalcin Oksal |  | Intrawest | 1047 | 1 | 0 | 0 |  |  | Plaza International | 0 | 219
Keith Woith |  | HuHot Mongolian Grill | 1045 | 1 | 0 | 0 |  |  | Plum Hollow Country Club | 0 | 219
Division |  | Sargento | 1043 | 1 | 0 | 0 |  |  | Pollo Campero | 0 | 219
Yalcin Oksal |  | Catch Restaurant | 1042 | 1 | 0 | 0 |  |  | Pollo Tropical | 0 | 219
John Bestler |  | Chicago City Centre Hotel | 1040 | 1 | 0 | 0 |  |  | Popeye's | 1341.01 | 12
John Bestler | Amanda | BTD Capital Partners | 1620 | 1 | 0 | 0 |  |  | Portsmouth Public Schools | 0 | 219
Division |  | Rockford Park District | 1034 | 1 | 0 | 0 |  |  | Posto 9 | 2.3 | 182
|  | Richie's Diner | 1033 | 1 | 0 | 0 |  |  | Potbelly's | 207.317 | 33
Michelle Hudson |  | Souper Salad | 1031 | 1 | 0 | 0 |  |  | Premiere Yachts, Inc. | 0 | 219
|  | Grandma's Restaurant Company | 1028 | 1 | 0 | 0 |  |  | Pret A Manger | 81.015 | 64
Elizabeth Johnston | Steve | America's Incredible Pizza | 1026 | 1 | 0 | 0 |  |  | Prospera Hospitality | 0 | 219
Yalcin Oksal |  | Holiday Inn - Saratoga Springs | 1025 | 1 | 0 | 0 |  |  | Protect Healthcare | 0 | 219
|  | Ben Lomond Market | 1024 | 1 | 0 | 0 |  |  | Puleos | 0 | 219
|  | Scotts Valley Market | 1023 | 1 | 0 | 0 |  |  | Quaker Steak & Lube | 0 | 219
Yalcin Oksal |  | Coast Hotels and Resorts | 1022 | 1 | 0 | 0 |  |  | Quest Food Management Services | 3.6 | 173
Rob Siler | Steve | Wild Wing Cafe | 1019 | 1 | 0 | 0 |  |  | Quizno's | 0 | 219
|  | Children's Services Department | 1017 | 1 | 0 | 0 |  |  | Quorum | 1.818 | 187
Michelle Hudson |  | Spaghetti Warehouse | 1016 | 1 | 0 | 0 |  |  | Racetrac | 186.728 | 34
|  | Northwestern Hospital | 1015 | 1 | 0 | 0 |  |  | Rancherito's Mexican Foods | 0 | 219
Michelle Hudson | Eric | Copelands | 1014 | 1 | 0 | 0 |  |  | RARE HOSPITALITY | 0 | 219
Yalcin Oksal | Steve | Esplanade Restaurants LTD | 1013 | 1 | 0 | 0 |  |  | Real Mex | 92.4 | 60
Michelle Hudson | Eric | K-Bob's | 1012 | 1 | 0 | 0 |  |  | Red Coach Inn | 0 | 219
|  | Valle Vista Health Systems | 1011 | 1 | 0 | 0 |  |  | Red Lobster | 472.7816 | 23
Yalcin Oksal |  | Elbow River Casino | 1009 | 1 | 0 | 0 |  |  | Red Mango | 0 | 219
Michelle Hudson |  | H-E-B Grocery Co. | 1008 | 1 | 0 | 0 |  |  | Red Robin | 0 | 219
Keith Woith |  | La Costa Resort | 1007 | 1 | 0 | 0 |  |  | Restaurant Management Group | 0 | 219
Yalcin Oksal |  | Portsmouth Public Schools | 1006 | 1 | 0 | 0 |  |  | Revolution Foods | 0 | 219
Yalcin Oksal |  | Apple Metro- Chevy's and Zanaro's | 1005 | 1 | 0 | 0 |  |  | Rhodes Ranch Golf Club | 0 | 219
Michelle Hudson | Eric | Carlson Hotels Worldwide | 1003 | 1 | 0 | 0 |  |  | Richie's Diner | 0 | 219
Michelle Hudson |  | Indel Warehouse | 1002 | 1 | 0 | 0 |  |  | Rio West | 0 | 219
Yalcin Oksal |  | Alicarte | 1001 | 1 | 0 | 0 |  |  | Rising Roll | 0 | 219
Michelle Hudson |  | Shamar Hope Haven | 999 | 1 | 0 | 0 |  |  | Ristorante Toscano | 0 | 219
Michelle Hudson |  | Rio West | 998 | 1 | 0 | 0 |  |  | RIT - Dining Services | 0 | 219
|  | Concessions Management Services | 997 | 1 | 0 | 0 |  |  | Rita Restaurant Corp | 0 | 219
|  | Amici's East Coast Pizzeria | 994 | 1 | 0 | 0 |  |  | RLB | 0 | 219
Keith Woith |  | Montage Resort and Spa | 993 | 1 | 0 | 0 |  |  | Rockford Park District | 0 | 219
Division |  | Pierce's Supermarkets | 992 | 1 | 0 | 0 |  |  | Roka Akor | 0 | 219
John Bestler | Steve | Imagin Asia | 991 | 1 | 0 | 0 |  |  | Rolf Jensen & Associates | 0 | 219
Elizabeth Johnston | Steve | Disneyland | 989 | 1 | 0 | 0 |  |  | Rolling Stone | 0 | 219
Michelle Hudson |  | Christina's Fine Mexican Restaurant | 988 | 1 | 0 | 0 |  |  | Round the Clock Restaurants | 0 | 219
|  | Cathedral Hill Hotel | 987 | 1 | 0 | 0 |  |  | Royal Sonesta Hotel | 0 | 219
Keith Woith | Eric | Coffee Bean & Tea Leaf | 986 | 1 | 0 | 0 |  |  | Ruby Tuesday | 0 | 219
John Bestler | Eric | Rolf Jensen & Associates | 984 | 1 | 0 | 0 |  |  | Ruth's Chris Steak House | 0 | 219
Yalcin Oksal |  | Lattanzi Ristorante | 982 | 1 | 0 | 0 |  |  | S & S Cafeteria | 0 | 219
Yalcin Oksal | Steve | Pickle Barrel | 981 | 1 | 0 | 0 |  |  | Saddle Back Ranch Chop House | 0 | 219
|  | HMQ | 980 | 1 | 0 | 0 |  |  | Sage Hospitality | 37.5942 | 88
|  | One Sunset | 979 | 1 | 0 | 0 |  |  | Salem Senior | 0 | 219
|  | Tbonz | 978 | 1 | 0 | 0 |  |  | Sapphire | 0 | 219
Yalcin Oksal |  | Pasta Resources | 975 | 1 | 0 | 0 |  |  | Sara Lee | 0 | 219
Brian Nolan | Emily | Craftworks | 972 | 1 | 0 | 0 |  |  | Sargento | 0 | 219
Michelle Hudson | Steve | Colton's Steak House | 971 | 1 | 0 | 0 |  |  | Sauce | 13.92 | 130
Brian Nolan |  | Texas Roadhouse | 970 | 1 | 0 | 0 |  |  | SBARRO | 0 | 219
|  | Tacaza, Inc | 968 | 1 | 0 | 0 |  |  | Scarborough Town Centre | 0 | 219
|  | Breckenridge Group | 966 | 1 | 0 | 0 |  |  | Scott Airforce Base | 0 | 219
John Bestler | Steve | Boykin | 965 | 1 | 0 | 0 |  |  | Scotts Valley Market | 0 | 219
|  | Champ's Sports Bar & Grille | 962 | 1 | 0 | 0 |  |  | Sea to You | 0 | 219
Yalcin Oksal | Steve | LoneStar Group of Companies | 960 | 1 | 0 | 0 |  |  | Seaport Boston | 5.383 | 160
Keith Woith | Eric | White Chocolate Grill | 958 | 1 | 0 | 0 |  |  | Select Restaurants | 10.68 | 141
Yalcin Oksal |  | BMG Restaurant Group | 956 | 1 | 0 | 0 |  |  | Shamar Hope Haven | 0 | 219
Michelle Hudson |  | Mary Ruth Inc. | 952 | 1 | 0 | 0 |  |  | Ship & Anchor | 0 | 219
|  | Warner Brothers | 948 | 1 | 0 | 0 |  |  | Shopper Events LLC | 134.843 | 45
|  | Stonewood Grill | 946 | 1 | 0 | 0 |  |  | Silliker Laboratories | 0 | 219
Yalcin Oksal |  | Metz Enterprises | 941 | 1 | 0 | 0 |  |  | Silver Cloud | 2.611 | 178
Yalcin Oksal |  | The Distillery | 939 | 1 | 0 | 0 |  |  | SilverBirch Hotels | 4.29 | 167
Yalcin Oksal |  | Larchmont Tavern | 938 | 1 | 0 | 0 |  |  | Sizzler | 0 | 219
|  | Saddle Back Ranch Chop House | 936 | 1 | 0 | 0 |  |  | Smashburger | 0 | 219
|  | Armadillo Willy's | 925 | 1 | 0 | 0 |  |  | Smithfield | 0 | 219
Elizabeth Johnston | Steve | Hartsfield Hospitality | 924 | 1 | 0 | 0 |  |  | Smokey Bones | 0 | 219
|  | Affiniti Golf Partners, Inc | 923 | 1 | 0 | 0 |  |  | Smokey Mountain | 0 | 219
Elizabeth Johnston |  | Beef O' Brady's | 915 | 1 | 0 | 0 |  |  | SMUCKERS | 0 | 219
|  | American Pie Pizza Company | 914 | 1 | 0 | 0 |  |  | Snooze | 22.1325 | 112
Michelle Hudson |  | Furr's Family Dining | 910 | 1 | 0 | 0 |  |  | Sodexo | 1617.5854 | 9
|  | Turley's Restaurant | 909 | 1 | 0 | 0 |  |  | Sonic | 0 | 219
Keith Woith | Steve | Café Rio | 908 | 1 | 0 | 0 |  |  | Souper Salad | 0 | 219
Brian Nolan | Steve | Quaker Steak & Lube | 907 | 1 | 0 | 0 |  |  | Spaghetti Warehouse | 0 | 219
Michelle Hudson |  | Cedar Ridge Country Club | 904 | 1 | 0 | 0 |  |  | SPECTRUM REST GRP | 0 | 219
Yalcin Oksal |  | Marx Hotel | 903 | 1 | 0 | 0 |  |  | Spirit Cruises | 0 | 219
|  | Szechuan House | 901 | 1 | 0 | 0 |  |  | Spirit Mountain Casino | 6.8544 | 155
|  | Miller Oil Company | 895 | 1 | 0 | 0 |  |  | Sprouts | 0 | 219
|  | Restaurant Management Group | 894 | 1 | 0 | 0 |  |  | Stanford University | 19.314 | 118
Yalcin Oksal |  | Perkins | 893 | 1 | 0 | 0 |  |  | Starbucks | 5392.0104 | 1
|  | The Keg | 892 | 1 | 0 | 0 |  |  | Starwood | 4.4633 | 166
Division |  | Active Learning | 891 | 1 | 0 | 0 |  |  | Steak 'n Shake | 458.2264 | 24
|  | Biaggi's | 889 | 1 | 0 | 0 |  |  | Stonewood Grill | 0 | 219
Keith Woith |  | Indigo Joe's | 887 | 1 | 0 | 0 |  |  | Stripes | 385.8783 | 26
|  | Hurricane Brands | 884 | 1 | 0 | 0 |  |  | Studio Movie Grill | 0 | 219
|  | Bravo | 878 | 1 | 0 | 0 |  |  | Sunkist | 43.417 | 82
|  | Palermo's Pizza | 877 | 1 | 0 | 0 |  |  | Sunoco | 0 | 219
|  | Health Alliance | 876 | 1 | 0 | 0 |  |  | Supply Chain | 0 | 219
|  | APIO, Inc. | 874 | 1 | 0 | 0 |  |  | Swissotel | 0 | 219
Brian Nolan | Emily | New York Office of Mental Health | 872 | 1 | 0 | 0 |  |  | Sybergs | 0 | 219
Michelle Hudson | Steve | AAFES | 869 | 1 | 0 | 0 |  |  | SYSCO | 0 | 219
Yalcin Oksal |  | Pettibone's Grille | 868 | 1 | 0 | 0 |  |  | Szechuan House | 0 | 219
|  | Wallis Companies | 866 | 1 | 0 | 0 |  |  | T C C | 0 | 219
|  | Lake Las Vegas | 865 | 1 | 0 | 0 |  |  | Tacaza, Inc | 0 | 219
|  | Mission Valley Resorts | 864 | 1 | 0 | 0 |  |  | Taco Bueno | 0 | 219
Yalcin Oksal |  | Mike's Restaurants | 863 | 1 | 0 | 0 |  |  | Taco Mac | 41.9697 | 85
| Emily | Niagra Hospitality | 861 | 1 | 0 | 0 |  |  | Taj Mahal Columbus | 0 | 219
|  | Johnson and Wales | 854 | 1 | 0 | 0 |  |  | Target | 0 | 219
Brian Nolan | Eric | Ace Restaurant Group | 852 | 1 | 0 | 0 |  |  | Tavistock | 23.97 | 106
|  | Luxury Resorts | 850 | 1 | 0 | 0 |  |  | Tbonz | 0 | 219
|  | Midopa Asian Market | 849 | 1 | 0 | 0 |  |  | Ted's Montana Grill | 0 | 219
|  | Plaza International | 848 | 1 | 0 | 0 |  |  | Terranea Resorts | 0 | 219
|  | Hard Rock Hotel Las Vegas | 843 | 1 | 0 | 0 |  |  | Texas Roadhouse | 0 | 219
Division | Eric | Premiere Yachts, Inc. | 842 | 1 | 0 | 0 |  |  | TGI Friday's | 946.3264 | 17
|  | Great American Diner | 838 | 1 | 0 | 0 |  |  | The Distillery | 0 | 219
Michelle Hudson |  | Abuelo's | 837 | 1 | 0 | 0 |  |  | The Florida Hotel and Conference Center | 0 | 219
Keith Woith |  | Flying J | 833 | 1 | 0 | 0 |  |  | The Keg | 0 | 219
|  | Amazing Jake's Pizza | 830 | 1 | 0 | 0 |  |  | THE OLIVE GROUP | 0 | 219
|  | Detroit Entertainment | 826 | 1 | 0 | 0 |  |  | The Peninsula Hotel | 4.2126 | 168
|  | Main Street Restaurant Group | 825 | 1 | 0 | 0 |  |  | The Procaccianti Group | 22.8 | 109
John Bestler |  | Great Wolf Lodge | 824 | 1 | 0 | 0 |  |  | The Resort at Pelican Hill | 8.008 | 150
|  | Orange County Schools | 821 | 1 | 0 | 0 |  |  | The Tao Group | 0 | 219
|  | Meadowood | 814 | 1 | 0 | 0 |  |  | The Venetian Hotel | 0 | 219
Yalcin Oksal | Steve | Charles Town Race & Slots | 813 | 1 | 0 | 0 |  |  | Three Square | 0 | 219
Division |  | Dawn International | 811 | 1 | 0 | 0 |  |  | Tiggos | 0 | 219
|  | Scott Airforce Base | 808 | 1 | 0 | 0 |  |  | Tilted Kilt | 1.372 | 196
|  | Isle of Capri | 806 | 1 | 0 | 0 |  |  | Tim Drum | 0 | 219
|  | Z'Tejas | 802 | 1 | 0 | 0 |  |  | Todai Restaurants | 0 | 219
|  | British Petroleum | 800 | 1 | 0 | 0 |  |  | Tommy Bahama | 13.4663 | 134
|  | Krome Detention Center | 757 | 1 | 0 | 0 |  |  | Tommy Doyle | 0 | 219
|  | SPECTRUM REST GRP | 755 | 1 | 0 | 0 |  |  | Tony Roma's | 0 | 219
|  | Brent's Deli | 744 | 1 | 0 | 0 |  |  | Tortoise Restaurant Group | 0 | 219
Elizabeth Johnston | Steve | Ted's Montana Grill | 742 | 1 | 0 | 0 |  |  | Travel Centers of America | 76.164 | 65
|  | A.F. GILMORE | 741 | 1 | 0 | 0 |  |  | Trinity Group | 0 | 219
Elizabeth Johnston | Emily | Pick Up Stix | 740 | 1 | 0 | 0 |  |  | Tropical Smoothie Café | 271.337 | 31
|  | Paul Lee's Chinese Kitchen | 739 | 1 | 0 | 0 |  |  | Truluck's | 17.24 | 124
|  | MedAssets | 736 | 1 | 0 | 0 |  |  | Trusthouse (Aladdin) | 12.69 | 137
John Bestler |  | US Foodservice | 735 | 1 | 0 | 0 |  |  | Tumbleweed | 0 | 219
|  | AIR NATIONAL GUARD | 731 | 1 | 0 | 0 |  |  | Turley's Restaurant | 0 | 219
|  | Keller Army Community Hospital | 728 | 1 | 0 | 0 |  |  | Turner | 0 | 219
|  | Barnes & Noble Café | 724 | 1 | 0 | 0 |  |  | Twin Peaks | 119.712 | 52
Yalcin Oksal |  | THE OLIVE GROUP | 694 | 1 | 0 | 0 |  |  | Twisted Rooster | 0 | 219
|  | PF Chang's | 693 | 1 | 0 | 0 |  |  | Unidine | 3.838 | 171
Michelle Hudson |  | LSG Sky Chef | 684 | 1 | 0 | 0 |  |  | US Foodservice | 0 | 219
Michelle Hudson |  | Eatzi's | 683 | 1 | 0 | 0 |  |  | Uwink | 0 | 219
Elizabeth Johnston | Steve | Intercontinental Hotel Group | 678 | 1 | 0 | 0 |  |  | Valle Vista Health Systems | 0 | 219
Division |  | NRA | 662 | 1 | 0 | 0 |  |  | Valley Hospitality | 0 | 219
Yalcin Oksal |  | Green Mill | 640 | 1 | 0 | 0 |  |  | Value Cold Storage | 0 | 219
Keith Woith | Eric | Todai Restaurants | 627 | 1 | 0 | 0 |  |  | Verve Senior Living | 34.7863 | 92
Yalcin Oksal |  | NEW CASTLE HOTELS | 622 | 1 | 0 | 0 |  |  | Veteran's Canteen Services | 64.3125 | 70
Yalcin Oksal | Steve | Eat N Park | 611 | 1 | 0 | 0 |  |  | VI | 27.9836 | 101
Division |  | SMUCKERS | 593 | 1 | 0 | 0 |  |  | Villa Enterprises | 0 | 219
Michelle Hudson | Steve | SYSCO | 578 | 1 | 0 | 0 |  |  | Village Tavern | 20.7816 | 114
|  | Pollo Tropical | 570 | 1 | 0 | 0 |  |  | Wallis Companies | 0 | 219
Keith Woith |  | New Seasons Market | 560 | 1 | 0 | 0 |  |  | Walt Disney World | 0 | 219
Elizabeth Johnston |  | MORTON'S OF CHICAGO | 559 | 1 | 0 | 0 |  |  | Warner Brothers | 0 | 219
|  | College of Holy Cross | 553 | 1 | 0 | 0 |  |  | Waterside Group | 0 | 219
Elizabeth Johnston |  | Buca Di Beppo | 542 | 1 | 0 | 0 |  |  | Wawa | 0 | 219
Division | Division | Open Classes | 539 | 1 | 0 | 0 |  |  | Weber Grill | 19.4058 | 117
|  | Consolidated Restaurant Operations | 498 | 1 | 0 | 0 |  |  | Wendy's | 0 | 219
Elizabeth Johnston |  | Houlihan's | 477 | 1 | 0 | 0 |  |  | Westmont Hospitality | 0 | 219
Michelle Hudson |  | Ruth's Chris Steak House | 475 | 1 | 0 | 0 |  |  | Whataburger | 0 | 219
John Bestler | Steve | Tony Roma's | 471 | 1 | 0 | 0 |  |  | White Chocolate Grill | 0 | 219
Brian Nolan |  | O'Charley's | 463 | 1 | 0 | 0 |  |  | White Lodging | 23.6941 | 108
Michelle Hudson | Division | PICCADILLY | 448 | 1 | 0 | 0 |  |  | Whole Foods | 0 | 219
Keith Woith |  | American Blue Ribbon Holdings | 434 | 1 | 0 | 0 |  |  | Wild Wing Cafe | 0 | 219
|  | Avado Brands | 423 | 1 | 0 | 0 |  |  | Willow Creek Assisted Living | 0 | 219
Brian Nolan |  | Logan's Roadhouse | 330 | 1 | 0 | 0 |  |  | Willow Valley Resort | 9.072 | 146
|  | Black Angus | 323 | 1 | 0 | 0 |  |  | Wolfgang Puck | 0 | 219
|  | SBARRO | 314 | 1 | 0 | 0 |  |  | Woods Services | 0 | 219
Elizabeth Johnston | Steve | Denny's | 308 | 1 | 0 | 0 |  |  | Wyndham Hotels | 46.2676 | 80
Michelle Hudson | Steve | Taco Bueno | 267 | 1 | 0 | 0 |  |  | YUM! Brands | 4658.5388 | 2
Brian Nolan | Emily | Dunkin Brands | 263 | 1 | 0 | 0 |  |  | Z Foods | -0.3636 | 602
John Bestler | Emily | Wendy's | 257 | 1 | 0 | 0 |  |  | Z'Tejas | 0 | 219
Michelle Hudson | Steve | Whole Foods | 220 | 1 | 0 | 0 |  |  | (blank) |  | 219
Yalcin Oksal |  | Harrah's | 209 | 1 | 0 | 0 |  |  | Bento Sushi | 90.878 | 61
Michelle Hudson | Steve | Whataburger | 179 | 1 | 0 | 0 |  |  | Carnegie Mellon University | 16.0841 | 126
Elizabeth Johnston | Steve | Walt Disney World | 177 | 1 | 0 | 0 |  |  | SR Restaurant Holdings Group | 7.9 | 151
Keith Woith |  | Sizzler | 167 | 1 | 0 | 0 |  |  | The Kitchen | 10.35 | 143
Keith Woith | Eric | Red Robin | 162 | 1 | 0 | 0 |  |  | Chinook Winds Casino Resort | 3.8292 | 172
Elizabeth Johnston | Steve | RARE HOSPITALITY | 161 | 1 | 0 | 0 |  |  | Popeyes - Idora Inc | 18 | 122
Keith Woith | Eric | Quizno's | 159 | 1 | 0 | 0 |  |  | Bagel King Bakery | 0.98 | 202
Division |  | Nestle | 150 | 1 | 0 | 0 |  |  | Eureka! | 22.27 | 111
Brian Nolan |  | Krispy Kreme | 146 | 1 | 0 | 0 |  |  | Au Bon Pain | 165.52 | 38
Division |  | Kellogg's | 144 | 1 | 0 | 0 |  |  | Benihana | 123.5699 | 49
Division |  | Hershey's | 137 | 1 | 0 | 0 |  |  | Boudin Bakery | 71.68 | 66
|  | Four Seasons Hotel | 135 | 1 | 0 | 0 |  |  | Shake Shack | 24.3 | 105
Division |  | Dole | 129 | 1 | 0 | 0 |  |  | Walk-On's Enterprises | 7.2 | 154
|  | Deans Foods | 126 | 1 | 0 | 0 |  |  | Guest Services | 9.4046 | 145
Brian Nolan | Eric | Bruegger's | 115 | 1 | 0 | 0 |  |  | Anna's House | 4.648 | 163
Michelle Hudson | Steve | Brinker | 114 | 1 | 0 | 0 |  |  | Rebecca Jean Catering | 2.55 | 179
Keith Woith |  | Boston Market | 113 | 1 | 0 | 0 |  |  | PizzaRev | 2.4 | 181
Brian Nolan |  | Backyard Burgers | 106 | 1 | 0 | 0 |  |  | PhaseNext Hospitality | 1.4 | 195
Division |  | Dreyer's Grand Ice Cream | 95 | 1 | 0 | 0 |  |  | Plantation Village | 1.36 | 197
Elizabeth Johnston | Emily | Wolfgang Puck | 94 | 1 | 0 | 0 |  |  | AXA US | 0.6 | 212
Division |  | T C C | 86 | 1 | 0 | 0 |  |  | The Violet Hour | 0.4 | 214
Yalcin Oksal |  | Target | 85 | 1 | 0 | 0 |  |  | Luna Grill | 35.88 | 90
Division |  | Silliker Laboratories | 78 | 1 | 0 | 0 |  |  | Main Event | 35.52 | 91
Division |  | Sara Lee | 75 | 1 | 0 | 0 |  |  | Crave America | 18.2 | 121
Division |  | Northland Cranberries | 68 | 1 | 0 | 0 |  |  | Schick Manufacturing Inc | 3.025 | 177
Division |  | Malt-O-Meal | 59 | 1 | 0 | 0 |  |  | Best Western Premier - The Central Hotel | 1.7 | 189
Division |  | M&M Mars | 58 | 1 | 0 | 0 |  |  | Roy Rogers | 1.08 | 201
Division |  | Land O Lakes | 56 | 1 | 0 | 0 |  |  | Columbia County Jail | 0.4 | 214
Division |  | Kroger | 54 | 1 | 0 | 0 |  |  | Copperhead Grille | 0.375 | 216
Division |  | Kraft Foods | 52 | 1 | 0 | 0 |  |  | Hotel Del Coronado | 8.575 | 148
Division |  | Frito-Lay | 36 | 1 | 0 | 0 |  |  | PFC at Omni Resorts LaCosta | 0.9 | 206
Division |  | Food Brand IDS | 35 | 1 | 0 | 0 |  |  | State of North Carolina | 175.63 | 35
Division |  | Open Classes | 29 | 1 | 0 | 0 |  |  | Cooper's Hawk | 18.424 | 119
Division |  | Con Agra | 23 | 1 | 0 | 0 |  |  | Hopcat | 14.84 | 128
Division |  | Campell Soup Co | 11 | 1 | 0 | 0 |  |  | Babalu Tacos & Tapas | 11.275 | 139
Division |  | ECOLAB FOOD SAFETY & HYGIENE SOLUTIONS |  | 0 | 0 | 0 |  |  | BLD Brands | 8.0649 | 149
Division |  | ECOLAB INDONESIA |  | 0 | 0 | 0 |  |  | Wingstop | 6.125 | 159
Division |  | ECOLAB KOREA |  | 0 | 0 | 0 |  |  | Daly Seven Inc. | 4.06 | 170
Division |  | ISTITUTO CULINARIO % C BAUTISTA |  | 0 | 0 | 0 |  |  | Atrium Hospitality | 3.51 | 174
Division |  | NATIONAL RESTAURANT ASSOC |  | 0 | 0 | 0 |  |  | Shore | 2.1 | 183
Division |  | Rising Roll | 1061 | 1 | 0 | 0 |  |  | Darden Franchise Group | 2.0074 | 185
Division | Eric | Spirit Cruises | 80 | 1 | 0 | 0 |  |  | Georgia Blue | 1.7 | 190
John Bestler | Emily | Swissotel | 1441 | 1 | 0 | 0 |  |  | Philz Coffee | 1.589 | 191
Brian Nolan | Emily | Batali & Bastianich Hospitality Group | 1333 | 1 | 0 | 0 |  |  | Velvet Taco | 1.45 | 194
Brian Nolan | Emily | HMS Host | 138 | 1 | 0 | 0 |  |  | Mad Taco | 1.26 | 198
Brian Nolan | Open - Northeast | Dollar General | 9994 | 1 | 0 | 0 |  |  | Mi Casa | 1.1 | 200
Rob Siler | Emily | HoneyBaked Ham California | 1609 | 1 | 0 | 0 |  |  | CNR Enterprises Inc | 0.954 | 204
Keith Woith | Open - Northeast | Old Spaghetti Factory | 746 | 1 | 0 | 0 |  |  | Freddy's Frozen Custard | 0.88 | 207
Justin Prestinario | Steve | Delta Hotels and Resort | 1303 | 1 | 0 | 0 |  |  | Holiday Inn Resort Orlando | 0.8 | 209
Michelle Hudson | Open - Northeast | Dickey's BBQ | 1353 | 1 | 0 | 0 |  |  | 716 Bar & Grill | 0.69 | 210
Keith Woith | Emily | Burgerville | 1508 | 1 | 0 | 0 |  |  | The Scarlet Huntington | 0.365 | 217
Brian Nolan | Amanda | Z Foods | 900 | 1 | -0.3636 | -0.3636 |  |  | Restoration Hardware | 0.338 | 218
Brian Nolan | Amanda | Brookhaven | 1048 | 1 | -1.1183 | -1.1183 |  |  | Cerca Trova | 42.656 | 84
Michelle Hudson | Amanda | Mambo | 1088 | 1 | -1.158 | -1.158 |  |  | Grand Total | 50278.7206
CUSTOMER NOT IN PROJECTIONS
[9 empty] | Row Labels | Sum of USRevenue2016 | $$$_Rank
[9 empty] | EcoSure | 0 | 603
[9 empty] | District Tap | 0 | 603
[9 empty] | Arcis Golf | 0 | 603
[10 empty] | 0 | 603
[10 empty] | 0 | 603
[10 empty] | 0 | 603
[10 empty] | 0 | 603
[10 empty] | 0 | 603
[10 empty] | 0 | 603
[10 empty] | 0 | 603
Note on D18: Hall, Steve (Ecosure - USA): Einstein client ID is 1637; using Caribou client ID in projections only to roll up revenue under ENRG parent company
Note on D56: Hall, Steve (Ecosure - USA): using 9999 until actual client ID is created